## Booking
Id | Field | IAP_ID | SML_ID | Platform | Department | Project_Description | Project_Owner | Vendor | POB | PlanStart | PlanFinish | Duration | InterField | MobCode | DeMobCode | Mob_By_Code | De-mob_By_Code | L_Remarks
1 | G11 | 25-0023 |  |  | DRI | NYA (3D+1A) | Drilling |  |  | 2025-05-23 | 2025-07-08 | 47 | S-FT | S-OUT | S-IN
2 | JAS | 25-0244 |  | PPB2 | OPS | TNS/Expert suport GTG operation (Jun 25 - Jan 26) | Somsak | TNS/Expert | 1 | 2025-06-01 | 2026-01-01 | 215 | N-FT | N-OUT | N-IN
3 | JAS | 25-0005 | 934, 958, 980 | ALL PF | AIM | Maintenance Painting #1 [Experteam+AI Sup ] | Mittrapa | EXPT / AI Sup | 9 | 2025-06-08 | 2025-07-01 | 24 | N-FT | N-OUT | N-IN | V-MC-STH:06/07 > JAS:06/08 | V-GY-JAS:07/02 > STH:07/03
4 | JAS | 25-0006 |  | ALL PF | AIM | TSI: Topside Inspection [Dexon-RA] | Pradit | DEXON | 4 | 2025-06-08 | 2025-07-01 | 24 | N-FT | N-OUT | N-IN | V-MC-STH:06/07 > JAS:06/08 | V-GY-JAS:07/02 > STH:07/03
5 | G1 | 25-0075 | 843, 845 |  | WSV | Work Over : MNA-16&27 | Asadawut | Work Over | 4 | 2025-06-12 | 2025-06-29 | 18 | N-FT | N-OUT | N-IN |  |  | reroute demob MN on 22 Jun
6 | G10 | 25-0017 | 998, 997 | MOPU | BFT | [BFT] WAS051 Additional VSD 18, WAS083 Gen 5, SCADA Upgrade | Wason | Experteam+VE Supt. | 10 | 2025-06-15 | 2025-06-30 | 16 | S-FT | S-OUT | S-IN | V-SM-SKL:06/14 > G10:06/15 | V-SM-G10:07/01 > G11:07/01 > SKL:07/02 | demob to skl by galaxy on 20 Jul
7 | G10 | 25-0048 | 996 | MOPU | MNT | ABB pump Air-Cooling Fan Cover VFD & MG#7 & #8 Insulation exhaust | Ohmmanas | Expert | 12 | 2025-06-15 | 2025-07-05 | 21 | S-FT | S-OUT | S-IN | V-SM-SKL:06/14 > G10:06/15 | V-UV-G11:07/06 > G10:07/06 > SKL:07/07 | Reqeust Reroute to WAS
8 | JAS | 25-0233 | 982 | ALL PF | AIM | Maintenance Painting #3 [Experteam] | Mittrapa | EXPT | 8 | 2025-06-17 | 2025-07-01 | 15 | N-FT | N-OUT | N-IN | V-TC-STH:06/16 > G1:06/17 | V-GY-JAS:07/02 > STH:07/03
9 | G11 | 25-0013 | 402, 882, 903, 963, 977 | NYA | BFT | [BFT] NYA Well Hookup | Somkiat | Tantawan , BAKER , VE Supt | 9 | 2025-06-19 | 2025-07-05 | 17 | S-FT | S-OUT | S-IN | V-GX-SKL:06/18 > G11:06/19 | V-UV-G11:07/06 > G10:07/06 > SKL:07/07
10 | G11 | 25-0231 | 979 | NYC | OPS | [OPS] Extra cattering support activity#1 | Pitsanu |  | 1 | 2025-06-19 | 2025-07-22 | 34 | S-FT | S-OUT | S-IN | V-GX-SKL:06/18 > G11:06/19 | V-SM-G10:07/23 > G11:07/23 > SKL:07/24
11 | G11 | 25-0015 | 789 | NYC | BFT | [BFT] NY171 NYC additional wells mob 1 team 1 | Somkiat | TNS | 17 | 2025-06-23 | 2025-07-19 | 27 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > G11:06/23 | V-GX-G11:07/20 > G10:07/20 > SKL:07/21 | Reroute GX WN-SKL to WN-NY-SKL
12 | G11 | 25-0234 | 1138, 1201 | NYC | BFT | [BFT] NY171 NYC additional well VE supt no. 1 | Somkiat | VE Supt | 1 | 2025-06-23 | 2025-07-19 | 27 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > G11:06/23 | V-GX-G11:07/20 > G10:07/20 > SKL:07/21
13 | G11 | 25-0015 |  | NYC | BFT | [BFT] NY171 NYC additional wells mob 1 team 2 | Somkiat | TNS | 7 | 2025-06-23 | 2025-07-19 | 27 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > G11:06/23 | V-GX-G11:07/20 > G10:07/20 > SKL:07/21
14 | G10 | 25-0076 |  |  | WSV | Work Over : WSA-01i | Asadawut | Work Over | 8 | 2025-07-03 | 2025-07-14 | 12 | S-FT | S-OUT | S-IN
15 | G11 | 25-0116 |  | FSO | FSO | OMNI Suptds visit /OMNI HSE Audit / 10 Year Ceremony#3 | OMNI | OMNI | 1 | 2025-06-23 | 2025-07-04 | 12 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > G11:06/23 | C-HS-G11:07/05 > SKL:07/05
16 | G11 | 25-0122 |  | FSO | FSO | Metering Skid 2 Yearly Prover Calibration with DMF verification (Tentative 23 Jun - 07 Jul) | OMNI | OMNI | 2 | 2025-06-23 | 2025-07-04 | 12 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > G11:06/23 | V-UV-G11:07/06 > SKL:07/07
17 | JAS | 25-0196 |  | FSO | FSO | Pre-Mooring Wire Replacement: 200T Turret hydraulic winch inspection | Petrofac | Sparrow | 1 | 2025-08-02 | 2025-08-08 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:08/02 > JAS:08/02 | C-HN-JAS:08/09 > UTP:08/09
18 | G11 | 25-0212 | 785, 1141 | WPP | OPS | fiscal meter recalibration 2025 DMF (1), VE (1), Flowlabs (6) | Benjachai | DMF+VE+Flowlab | 8 | 2025-06-24 | 2025-07-04 | 11 | S-FT | S-OUT | S-IN |  |  | wait for special flight mob and demob
19 | JAS | 25-0197 | 1162 | FSO | FSO | General Remedial Repairs and Fabric Maintenance & Chipping and Painting -Mob 6 | Petrofac | Tindy | 6 | 2025-06-25 | 2025-07-17 | 23 | N-FT | N-OUT | N-IN | V-AT-STH:06/24 > JAS:06/25 | V-GY-JAS:07/18 > STH:07/19
20 | JAS | 25-0218 | 1211 | BYA | MNT | BYA Bi-Fuel survey | Pruang | Comap | 1 | 2025-07-03 | 2025-07-06 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:07/03 > JAS:07/03 | C-HN-JAS:07/07 > UTP:07/07
21 | JAS | 25-0246 | 1199 | WPA, PPB2, WPD, BYA | MNT | Jasmine UPS, Charger and Battery 3 Year Service Maintenance. | Ohmmanas | SR | 2 | 2025-06-30 | 2025-07-09 | 10 | N-FT | N-OUT | N-IN | C-HN-UTP:06/30 > JAS:06/30 | C-HN-JAS:07/10 > UTP:07/10
22 | JAS | 25-0042 | 1163 | FSO | FSO | Annual Main Turret Bearing Inspection -OEM | Petrofac | Thyssenkrupp | 1 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
23 | JAS | 25-0128 | 973, 1001 | FSO | OFF | Offtake JC-685 | Benjachai |  | 3 | 2025-06-28 | 2025-07-02 | 5 | N-FT | N-OUT | N-IN
24 | JAS | 25-0149 | 791 | FSO | FSO | Petrofac Managemnt visit (M Danish Merchant /Josie Philips ) | Petrofac | Petrofac | 2 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
25 | JAS | 25-0150 | 628 | FSO | FSO | Annual Main Turret Bearing Inspection -OEM | Petrofac | ABS | 1 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
26 | JAS | 25-0198 | 1121 | FSO | FSO | Annual Main Turret Bearing Inspection -Petrofac Operation & Integrity Engineer | Petrofac | Petrofac | 1 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
27 | G10 | 25-0156 | 1048 | MOPU | MNT | Aggreko MG#7 and MG#8 service | Ekawit | Aggreko | 2 | 2025-07-01 | 2025-07-05 | 5 | S-FT | S-OUT | S-IN | V-GX-SKL:06/30 > G10:07/01 |  | Request reroute vessel SC UNIVERSE on 6 July from "NY - SKL" to "NY - WAS - SKL"
28 | G11 | 25-0136 |  | NYC | AIM | [AIM] NYC MOPU annual classification survey #1 [Itt+ABS] | Atthapong | ABS/VE | 3 | 2025-08-12 | 2025-08-18 | 7 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > G11:08/12 | V-SM-G11:08/19 > G10:08/19 | Request Reroute to NY
29 | G1 | 25-0171 |  | FSO | FSO | OMNI Suptds visit /ISM/HSE Audit Jun | OMNI | OMNI | 1 | 2025-07-05 | 2025-07-11 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:07/05 > G1:07/05 | C-HN-G1:07/12 > UTP:07/12
30 | G11 | 25-0175 |  | NYC | AIM | [AIM] NYC MOPU annual classification survey #2 [SMC] | Atthapong | SMC | 2 | 2025-08-12 | 2025-08-18 | 7 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > G11:08/12 | V-SM-G11:08/19 > G10:08/19 | Request Reroute to NY
31 | G11 | 25-0176 |  | NYC | AIM | [AIM] NYC MOPU annual classification survey #3 [Brilliant] | Atthapong | Brilliant | 1 | 2025-08-12 | 2025-08-18 | 7 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > G11:08/12 | V-SM-G11:08/19 > G10:08/19 | Request Reroute to NY
32 | G10 | 25-0249 |  | MOPU | MNT | ABB pump VSD major 6Y PM#1 | Ohmmanas | VE | 1 | 2025-07-04 | 2025-07-13 | 10 | S-FT | S-OUT | S-IN | V-SM-SKL:07/03 > G10:07/04 | V-GX-G10:07/14 > SKL:07/15
33 | JAS | 25-0183 |  | ALL PF | ITM | JAS-2nd DT PM | Pichit | LBS | 1 | 2025-07-03 | 2025-07-11 | 9 | N-FT | N-OUT | N-IN | C-HN-UTP:07/03 > JAS:07/03 | V-AT-JAS:07/12 > G1:07/13 > JAS:07/18
34 | G10 | 25-0049 |  | MOPU | MNT | ABB pump VSD major 6Y PM#2 | Ohmmanas | ABB | 2 | 2025-07-04 | 2025-07-13 | 10 | S-FT | S-OUT | S-IN | V-SM-SKL:07/03 > G10:07/04 | V-GX-G10:07/14 > SKL:07/15
35 | JAS | 25-0039 |  | FSO | FSO | Replace Provsion Crane Boom Tip - Scaffolding | Petrofac | EMC | 5 | 2025-07-05 | 2025-07-17 | 13 | N-FT | N-OUT | N-IN | V-GY-STH:07/04 > JAS:07/05 | V-GY-JAS:07/18 > STH:07/19 | postpone demob on 22 Jun to 26 due seat not enough
36 | JAS | 25-0101 |  | WPB | MNT | WPB WPD BYA HVAC Replacement [Expert] | Pruang | Expert | 10 | 2025-07-05 | 2025-08-01 | 28 | N-FT | N-OUT | N-IN | V-GY-STH:07/04 > JAS:07/05 | V-NT-JAS:08/02 > G1:08/02 > JAS:08/05 | back to STH by Neptune on 2 Aug
37 | G1 | 25-0250 |  |  | FSO | ABS Class Survey / Flag Inspection | OMNI | ABS | 1 | 2025-07-05 | 2025-07-07 | 3 | N-FT | N-OUT | N-IN
38 | JAS | 25-0184 |  | ALL PF | ITM | JAS-2nd VSAT PM, Radio PM and Replacement new equipment | Pichit | Infonet+UMT | 4 | 2025-07-07 | 2025-07-11 | 5 | N-FT | N-OUT | N-IN | V-G5-STH:07/07 > JAS:07/07 | V-AT-JAS:07/12 > G1:07/13 > JAS:07/18
39 | G10 | 25-0207 |  | MOPU | WSV | Work Over : WSA-20H | Asadawut | Work Over | 4 | 2025-07-14 | 2025-07-26 | 13 | S-FT | S-OUT | S-IN
40 | G11 | 25-0074 |  |  | DRI | NYC (1D+1A/D+2WI) | Drilling |  |  | 2025-07-08 | 2025-08-15 |  | S-FT | S-OUT | S-IN
41 | G10 | 25-0251 |  | MOPU | BFT | [BFT] Workover support (WSA-01i) | Somkiat | Experteam+VE Supt. | 8 | 2025-07-09 | 2025-07-25 | 17 | S-FT | S-OUT | S-IN | V-UV-SKL:07/08 > G11:07/09 | V-UV-G11:07/26 > SKL:07/27
42 | G10 | 25-0132 |  | FSO | OFF | Offtake WC-047 | Benjachai |  | 3 | 2025-07-09 | 2025-07-15 | 7 | S-FT | S-OUT | S-IN
43 | G1 | 25-0252 |  | WPP-A | AIM | Maintenance Painting [Experteam+AI Sup ] | Mittrapa | EXPT / AI Sup | 18 | 2025-09-02 | 2025-09-24 | 23 | N-FT | N-OUT | N-IN | V-GY-STH:09/01 > G1:09/02 > JAS:09/02 | V-TC-G1:09/25 > STH:09/26 | Request to reroute GY via MN.
44 | G1 | 25-0011 | 950 | WPP-A | BFT | [BFT] MN131 Manora debottleneck mob + S/D, MN136 PWIP check valve, MN137 Annulus vent, MN138 Gen Bellow, change SDV manifold, repair pipe leak, Closed drain header scale cleaning | Somkiat | TNS+VE Sup | 31 | 2025-07-02 | 2025-07-26 | 25 | N-FT | N-OUT | N-IN |  | V-GY-JAS:07/27 > G1:07/27 > STH:07/28 | Mob via G5
45 | G1 | 25-0253 |  | WPP-A | BFT | [BFT] MN131 Manora debottleneck mob post S/D | Somkiat | TNS+VE Sup | 12 | 2025-07-27 | 2025-08-01 | 6 | N-FT | N-OUT | N-IN | V-G5-STH:07/26 > JAS:07/27 | V-TC-G1:08/02 > STH:08/03
46 | JAS | 25-0254 |  | ALL PF | AIM | Maintenance Painting #4 [Experteam+AI Sup ] | Mittrapa | EXPT / AI Sup | 18 | 2025-09-18 | 2025-10-15 | 28 | N-FT | N-OUT | N-IN | V-GY-STH:09/17 > JAS:09/18
47 | G1 | 25-0185 |  | ALL PF | ITM | MAN - 2nd Radio PM | Pichit | UMT | 2 | 2025-07-13 | 2025-07-18 | 6 | N-FT | N-OUT | N-IN | V-AT-JAS:07/12 > G1:07/13 > JAS:07/18 | C-HN-G1:07/19 > UTP:07/19
48 | G1 | 25-0186 |  | ALL PF | ITM | MAN-2nd DT and VSAT PM + ICS Power cord replacement during MAN S/D#1 | Pichit | LBS+Infonet | 2 | 2025-07-13 | 2025-07-26 | 14 | N-FT | N-OUT | N-IN | V-AT-JAS:07/12 > G1:07/13 > JAS:07/18 | C-HN-G1:07/26 > UTP:07/26
49 | G1 | 25-0238 |  | ALL PF | ITM | MAN-2nd DT and VSAT PM + ICS Power cord replacement during MAN S/D#2 | Pichit | Infonet | 1 | 2025-07-13 | 2025-07-20 | 8 | N-FT | N-OUT | N-IN | V-AT-JAS:07/12 > G1:07/13 > JAS:07/18 | C-HN-G1:07/21 > UTP:07/21
50 | G1 | 25-0001 |  | WPP-A | AIM | [SD] Flare & GEN Exhaust Line Inspection [Dexon] | Pradit | DEXON | 4 | 2025-07-14 | 2025-08-01 | 19 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > G1:07/14 | V-TC-G1:08/02 > STH:08/03
51 | G1 | 25-0061 |  | WPP-A | AIM | AI Supervisor [AI Sup] | Mittrapa | VE | 1 | 2025-07-14 | 2025-08-01 | 19 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > G1:07/14 | V-TC-G1:08/02 > STH:08/03
52 | G1 | 25-0063 |  | WPP-A | AIM | [SD] GEN Exhaust Insulation Repair [TNS] | Pradit | TNS | 4 | 2025-07-14 | 2025-08-01 | 19 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > G1:07/14 | V-TC-G1:08/02 > STH:08/03
53 | G1 | 25-0214 |  |  | OPS | [SD] Operation extra manpower (Opt ) | Puwat | VE | 2 | 2025-07-14 | 2025-07-25 | 12 | N-FT | N-OUT | N-IN
54 | G1 | 25-0255 |  | WPP | MNT | ICSS DCS MODIFICATION FOR MN DBN Phase 3 Project | Warakorn | Yokogawa | 1 | 2025-07-14 | 2025-08-02 | 20 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > G1:07/14 | V-TC-G1:08/02 > STH:08/03
55 | G11 | 25-0236 |  | NYC | BFT | [BFT] NY171 NYC additional wells mob 3-1 (MV) | Somkiat | ABB MV Term | 2 | 2025-07-16 | 2025-07-19 | 4 | S-FT | S-OUT | S-IN | V-GX-SKL:07/15 > G11:07/16 | V-GX-G11:07/20 > G10:07/20 > SKL:07/21
56 | G11 | 25-0159 | 1106 | NYC | MNT | [MNT] NYC CM works with lacing replacement | Ekawit | TOS | 6 | 2025-07-16 | 2025-07-25 | 10 | S-FT | S-OUT | S-IN | V-GX-SKL:07/15 > G11:07/16 | V-UV-G11:07/26 > SKL:07/27 | Use same TOS crews of row 84
57 | G11 | 25-0160 | 1008/1009 | NY | MNT | NYB2 Crank seal replacement | Ekawit | METRO CAT + Tantawan | 7 | 2025-07-16 | 2025-07-28 | 13 | S-FT | S-OUT | S-IN | V-GX-SKL:07/15 > G11:07/16 | V-SM-G11:07/29 > G10:07/29 > SKL:07/30 | TBC
58 | G1 | 25-0130 |  | FSO | OFF | Offtake MC-133#1 | Benjachai |  | 3 | 2025-07-15 | 2025-07-19 | 5 | N-FT | N-OUT | N-IN
59 | G11 | 25-0131 |  | FSO | OFF | Offtake NC-128 | Benjachai |  | 3 | 2025-07-15 | 2025-07-19 | 5 | S-FT | S-OUT | S-IN
60 | G11 | 25-0235 |  | NYC | BFT | [BFT] NY171 NYC additional well VE supt no. 2 | Somkiat | VE Supt | 1 | 2025-07-26 | 2025-08-11 | 17 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > G11:07/26 | V-UV-G11:08/12 > SKL:08/13
61 | G11 | 25-0256 |  | NYC | MNT | [MNT] NYC ICSS ADDITIONAL WELL DCS PROGRAM MODIFICATION#1 | Warakorn | Infinite | 1 | 2025-07-16 | 2025-07-30 | 15 |  |  |  | C-HS-SKL:07/16 > G11:07/16 | C-HS-G11:07/30 > SKL:07/30
62 | G11 | 25-0257 |  | NYC | MNT | [MNT] NYC ICSS ADDITIONAL WELL DCS PROGRAM MODIFICATION#2 | Warakorn | VE | 1 | 2025-07-16 | 2025-07-26 | 11 |  |  |  | C-HS-SKL:07/16 > G11:07/16 | C-HS-G11:07/26 > SKL:07/26
63 | JAS | 25-0098 |  | FSO | FSO | Pest Control Year 2025 Mob 3 | Petrofac | Johnson | 1 | 2025-07-17 | 2025-07-18 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:07/17 > JAS:07/17 | C-HN-JAS:07/19 > UTP:07/19
64 | JAS | 25-0151 |  | FSO | FSO | Replace Provsion Crane Boom Tip -ABS | Petrofac | ABS | 1 | 2025-07-17 | 2025-07-20 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:07/17 > JAS:07/17 | C-HN-JAS:07/21 > UTP:07/21
65 | JAS | 25-0199 |  | FSO | FSO | Replace Provsion Crane Boom Tip -Operation & Integrity Enginee Visit | Petrofac | Petrofac | 1 | 2025-07-17 | 2025-07-20 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:07/17 > JAS:07/17 | C-HN-JAS:07/21 > UTP:07/21
66 | G1 | 25-0216 |  |  | OPS | [SD] Operation extra manpower (EIO + MECH ) | Puwat | VE | 4 | 2025-07-19 | 2025-07-25 | 7 | N-FT | N-OUT | N-IN
67 | G1 | 25-0258 |  | WPP-A | BFT | [BFT] SD MN131 Manora debottleneck ABB #1 | Wason | ABB | 2 | 2025-07-20 | 2025-07-26 | 7 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-GY-JAS:07/27 > G1:07/27 > STH:07/28
68 | G1 | 25-0007 |  | WPP-A | BFT | [BFT] POST SD MN131 Manora debottleneck GEBH & Schneider | Wason | Baker /Schneider | 4 | 2025-07-20 | 2025-07-29 | 10 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20
69 | G1 | 25-0062 |  | WPP-A | AIM | [SD] PSV rectification (Night shift) / SDV passing rate testing and Valve Greasing | Atthapong | Systech | 8 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
70 | G1 | 25-0173 |  | WPP | MNT | [SD] ICSS ANNUAL PM 2025#1 and DCS operator workstation upgrade | Warakorn | Yokogawa | 1 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
71 | G1 | 25-0179 |  | WPP | MNT | [SD] LV-MV Switchgear PM (3 year PM) | Ohmmanas | VE+ABB+MARC | 7 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
72 | G1 | 25-0180 |  | WPP | MNT | [SD] MV Transformer PM | Ohmmanas | MARC | 3 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
73 | G1 | 25-0208 |  | WPP | MNT | [SD] VSD PM | Suwitcha | BHGE | 3 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
74 | G1 | 25-0210 |  | WPP | WSV | Well Service (Valves Greasing and BV Test) | Atisuda | Well Service | 6 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
75 | G1 | 25-0239 |  | WPP-A | AIM | [SD] Tantawan extra crews to support operations for hydrocyclone cleaning | Atthapong | TBC | 4 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
76 | G1 | 25-0172 |  | FSO | FSO | Extra Manpower for shutdown works | OMNI | OMNI | 5 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
77 | G1 | 25-0174 |  | WPP | MNT | [SD] ICSS ANNUAL PM 2025#2 (Warakorn+Ohmmanas) | Warakorn | VE | 2 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN | C-HN-UTP:07/21 > G1:07/21 | C-HN-G1:07/26 > UTP:07/26
78 | G1 | 25-0209 |  | WPP | OPS | OM + Shutdown Co. | Puwat | VE | 2 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN |  | C-HN-G1:07/26 > UTP:07/26 | mob special flight on 21 Jul 25
79 | G1 | 25-0215 |  |  | OPS | [SD] Operation extra manpower Safety Eng | Puwat | VE | 1 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN
80 | G10 | 25-0237 | 1039 | MOPU | BFT | [BFT] WAS083 Generator #5 Replacement + Test Separator upgrade | Somkiat | TNS+Expert+VE Supt. | 27 | 2025-08-06 | 2025-08-27 | 22 | S-FT | S-OUT | S-IN | V-GX-SKL:08/05 > G10:08/06 | V-UV-G11:08/28 > SKL:08/29
81 | JAS | 25-0081 |  | ALL PF | AIM | WPC: LARS Sea-fastening installation [TNS + AI Sup] | Pradit | TNS / AI Sup | 9 | 2025-07-18 | 2025-08-10 | 24 | N-FT | N-OUT | N-IN | V-AT-STH:07/17 > JAS:07/18 | V-GY-JAS:08/11 > STH:08/12
82 | JAS | 25-0093 |  | FSO | FSO | Boiler No. 1 Tubing Replacement - Mob 2 | Petrofac | Altamar | 14 | 2025-07-27 | 2025-08-17 | 22 | N-FT | N-OUT | N-IN | V-G5-STH:07/26 > JAS:07/27 | V-NT-JAS:08/18 > G1:08/18 > JAS:08/21 | next demob MNA-STH on 18 Aug
83 | JAS | 25-0109 |  | FSO | FSO | Overhaul No.1 & No. 2 Stripping Pump | Petrofac | Altamar | 4 | 2025-07-21 | 2025-08-17 | 28 | N-FT | N-OUT | N-IN | C-HN-UTP:07/21 > JAS:07/21 | V-NT-JAS:08/18 > G1:08/18 > JAS:08/21 | change mob from 23 jul to 26 jul
84 | G11 | 25-0260 |  | NYC | BFT | [BFT] NY171 NYC additional wells - MV Termination DH | Wason | Baker H | 2 | 2025-07-26 | 2025-07-28 | 3 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > G11:07/26 | V-SM-G11:07/29 > G10:07/29 > SKL:07/30
85 | G11 | 25-0015 |  | NYC | BFT | [BFT] NY171 NYC additional wells-Hookup | Somkiat | TNS+VE Supt. | 15 | 2025-07-26 | 2025-08-11 | 17 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > G11:07/26 | V-UV-G11:08/12 > SKL:08/13
86 | G11 | 25-0158 | 1105 | NY | MNT | WPP-B Crane luffing cylinder replacement | Ekawit | TOS | 6 | 2025-07-26 | 2025-08-05 | 11 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > G11:07/26 | V-SM-G10:08/06 > G11:08/06 > SKL:08/07 | TBC
87 | JAS | 25-0078 | 396 |  | WSV | BV test and valve greasing : WPC/WPA/WPB/BYA | Asadawut | Well Service | 5 | 2025-08-14 | 2025-10-07 | 55 | N-FT | N-OUT | N-IN
88 | JAS | 25-0129 |  | FSO | OFF | Offtake JC-686 | Benjachai |  | 3 | 2025-07-29 | 2025-08-02 | 5 | N-FT | N-OUT | N-IN
89 | G11 | 25-0243 |  | NYC | BFT | [BFT] NY171 NYC additional wells mob 3-2 insulation | Somkiat | TNS | 4 | 2025-07-29 | 2025-08-11 | 14 | S-FT | S-OUT | S-IN | V-UV-SKL:07/28 > G11:07/29 | V-UV-G11:08/12 > SKL:08/13
90 | JAS | 25-0082 |  | WPC | AIM | WPC: Air Surface Diving [OC-21 + 1VE] | Pradit | Ocean-21 / VE | 14 | 2025-07-30 | 2025-08-10 | 12 | N-FT | N-OUT | N-IN | V-GY-STH:07/29 > JAS:07/30 | V-GY-JAS:08/11 > STH:08/12
91 | JAS | 25-0097 |  | FSO | FSO | Erect Scaffolding for Boiler No. 1 Tubing Replacement - Mob 2 | Petrofac | EMC | 4 | 2025-07-30 | 2025-08-04 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/29 > JAS:07/30 | V-NT-JAS:08/05 > STH:08/06 | plan in aug
92 | JAS | 25-0160 |  | WPD | BFT | [BFT] JM336 VSD Replacement | Somkiat | Experteam | 12 | 2025-08-08 | 2025-08-29 | 22 | N-FT | N-OUT | N-IN | V-NT-STH:08/07 > JAS:08/08 | V-GY-JAS:08/30 > STH:08/31
93 | JAS | 25-0162 |  | WPC | BFT | [BFT] JM351 Deck drain, JM356 seperate diesel line Gen B5 B6, JM359 boatlanding fence | Somkiat | Experteam+VE Supv | 17 | 2025-08-08 | 2025-09-01 | 25 | N-FT | N-OUT | N-IN | V-NT-STH:08/07 > JAS:08/08 | V-NT-JAS:09/02 > STH:09/03
94 | G11 | 25-0189 |  | ALL PF | ITM | NON - 2nd DT PM and Replacement Battery UPS at Tanker | Pichit | LBS | 1 | 2025-07-30 | 2025-08-15 | 17 | S-FT | S-OUT | S-IN | C-HS-SKL:07/30 > G11:07/30 | C-HS-G11:08/16 > SKL:08/16
95 | JAS | 25-0167 |  |  | WSV | CTU : JSD#42 & BYA#30 zone change | Asadawut | Well Service | 15 | 2025-08-11 | 2025-09-04 | 25 | N-FT | N-OUT | N-IN
96 | G1 | 25-0261 |  |  | FSO | Annual elevator servicing/replacement of elevator wire | OMNI |  | 1 | 2025-08-02 | 2025-08-04 | 3 | N-FT | N-OUT | N-IN
97 | G11 | 25-0190 |  | ALL PF | ITM | NON-2nd VSAT PM, Radio PM and Replacement new equipment | Pichit | Infonet+UMT | 4 | 2025-08-03 | 2025-08-05 | 3 | S-FT | S-OUT | S-IN | V-SM-SKL:08/02 > G11:08/03 > G10:08/03 | V-SM-G10:08/06 > G11:08/06 > SKL:08/07
98 | JAS | 25-0095 |  | FSO | FSO | Dexon NDT : Boiler No. 1 Tubing Replacement -Mob 2 | Petrofac | Dexon | 2 | 2025-08-04 | 2025-08-10 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:08/04 > JAS:08/04 | C-HN-JAS:08/11 > UTP:08/11 | Demob Jas by chopper on 04 Aug
99 | G11 | 25-0262 |  | ALL PF | ITM | NON-Server LCM at WPPA | Pichit | VE | 1 | 2025-08-06 | 2025-08-15 | 10 | S-FT | S-OUT | S-IN | C-HS-SKL:08/06 > G11:08/06 | C-HS-G11:08/16 > SKL:08/16
100 | JAS | 25-0201 |  | FSO | FSO | Boiler No. 1 Tubing Replacement -Operation & Integrity Enginee Visit | Petrofac | Petrofac | 1 | 2025-08-09 | 2025-08-10 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/09 > JAS:08/09 | C-HN-JAS:08/11 > UTP:08/11
101 | G11 | 25-0046 |  | FSO | HSSE | 2025 Workplace monitoring-G11 | Narumol | SGS | 2 | 2025-08-13 | 2025-08-20 | 8 | S-FT | S-OUT | S-IN |  |  | mob from G11 to G11 NYC by vessel
102 | JAS | 25-0110 |  | FSO | FSO | Boiler No. 1 Tubing Replacement - Chemical Cleaning Boiler after re-tube. | Petrofac | TBC | 4 | 2025-08-14 | 2025-08-22 | 9 | N-FT | N-OUT | N-IN | V-GY-STH:08/13 > JAS:08/14 | V-NT-JAS:08/23 > STH:08/24 | Mob/Demob on Aug-25
103 | JAS | 25-0191 |  | FSO | OFF | Offtake JC-687 | Benjachai |  | 3 | 2025-08-14 | 2025-08-18 | 5 | N-FT | N-OUT | N-IN
104 | JAS | 25-0200 |  | FSO | FSO | ABS Class Boiler No. 1 Tubing Replacement -Mob 3. (Commissioning) | Petrofac | ABS | 1 | 2025-08-14 | 2025-08-17 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:08/14 > JAS:08/14 | C-HN-JAS:08/18 > UTP:08/18
105 | JAS | 25-0202 |  | FSO | FSO | Dismantle Scaffolding for Boiler No. 1 Tubing Replacement. | Petrofac | EMC | 4 | 2025-08-14 | 2025-08-22 | 9 | N-FT | N-OUT | N-IN | V-GY-STH:08/13 > JAS:08/14 | V-NT-JAS:08/23 > STH:08/24
106 | JAS | 25-0204 |  | FSO | FSO | Conntrak Management Visit – (Q3 2025) | Petrofac | Contrak | 1 | 2025-08-14 | 2025-08-15 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/14 > JAS:08/14 | C-HN-JAS:08/16 > UTP:08/16
107 | G11 | 25-0193 |  | FSO | OFF | Offtake NC-129 | Benjachai |  | 3 | 2025-08-15 | 2025-08-19 | 5 | S-FT | S-OUT | S-IN
108 | G11 | 25-0047 |  | NYC | HSSE | [HSSE] 2025 Workplace monitoring-G11 NYC | Narumol | SGS | 2 | 2025-08-21 | 2025-08-26 | 6 | S-FT | S-OUT | S-IN
109 | JAS | 25-0168 |  |  | WSV | CTU : BYA#18 Scale clean out & JSA#37ST Sand clean out | Asadawut | Well Service | 18 | 2025-09-04 | 2025-09-16 | 13 | N-FT | N-OUT | N-IN
110 | G10 | 25-0187 |  | MOPU | ITM | WAS - 2nd DT PM | Pichit | LBS | 1 | 2025-08-22 | 2025-08-28 | 7 | S-FT | S-OUT | S-IN | C-HS-SKL:08/22 > G10:08/22 | C-HS-G10:08/29 > SKL:08/29
111 | G10 | 25-0195 |  | MOPU | ITM | WAS - 2nd Radio PM and Replacement new equipment | Pichit | UMT | 2 | 2025-08-22 | 2025-08-26 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:08/22 > G10:08/22 | C-HS-G10:08/27 > SKL:08/27
112 | JAS | 25-0192 |  | FSO | OFF | Offtake JC-688 | Benjachai |  | 3 | 2025-08-26 | 2025-08-30 | 5 | N-FT | N-OUT | N-IN
113 | G10 | 25-0194 |  | FSO | OFF | Offtake WC-048 | Benjachai |  | 3 | 2025-08-26 | 2025-09-01 | 7 | S-FT | S-OUT | S-IN
114 | G10 | 25-0045 |  | MOPU | HSSE | 2025 Workplace monitoring-G10 | Narumol | SGS | 2 | 2025-08-27 | 2025-09-02 | 7 | S-FT | S-OUT | S-IN
115 | G10 | 25-0188 |  | MOPU | ITM | WAS - 2nd VSAT PM | Pichit | Infonet | 2 | 2025-08-27 | 2025-08-28 | 2 | S-FT | S-OUT | S-IN | C-HS-SKL:08/27 > G10:08/27 | C-HS-G10:08/29 > SKL:08/29
116 | G11 | 25-0181 |  | ALL PF | AIM | ILI - Inline Inspection NYB to NYA pipeline [ROSEN/AI Sup] | Mittrapa | ROSEN / AI Sup | 2 | 2025-12-27 | 2026-01-03 | 8 | S-FT | S-OUT | S-IN |  | V-SM-G11:08/31 > G10:08/31 > SKL:09/01 | Project defered
117 | G11 | 25-0182 |  | ALL PF | AIM | ILI - Inline Inspection team support [TNS] | Mittrapa | TNS | 8 | 2025-12-27 | 2026-01-03 | 8 | S-FT | S-OUT | S-IN |  |  | Project defered
118 | JAS | 25-0205 |  | FSO | FSO | Petrofac OM visit (Q3 2025) | Petrofac | Petrofac | 1 | 2025-08-28 | 2025-08-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/28 > JAS:08/28 | C-HN-JAS:08/30 > UTP:08/30
119 | JAS | 25-0206 |  | FSO | FSO | Petrofac HSEQ Advisor visit (Q3 2025) | Petrofac | Petrofac | 1 | 2025-08-28 | 2025-08-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/28 > JAS:08/28 | C-HN-JAS:08/30 > UTP:08/30
120 | G11 | 25-0263 |  | NYB | BFT | [BFT] NY171 NYB Rig Protection & flowline removal / Modification | Somkiat | Experteam | 7 | 2025-08-03 | 2025-08-11 | 9 | S-FT | S-OUT | S-IN | V-SM-SKL:08/02 > G11:08/03 > G10:08/03 | V-UV-G11:08/12 > SKL:08/13
121 | G11 | 25-0264 |  | NYB | BFT | [BFT] NY171 NYB Wells Hookup & Downhole Sensor Installation mob 1 | Somkiat | Experteam | 15 | 2025-08-31 | 2025-09-17 | 18 | S-FT | S-OUT | S-IN | V-UV-SKL:08/30 > G11:08/31 | V-SM-G11:09/18 > G10:09/18 > SKL:09/19
122 | G11 | 25-0265 |  | NYB | BFT | [BFT] NY171 NYB Wells Hookup & Downhole Sensor Installation mob 2 | Somkiat | Experteam | 15 | 2025-09-25 | 2025-10-15 | 21 | S-FT | S-OUT | S-IN | V-GX-SKL:09/24 > G10:09/25
123 | G11 | 25-0219 |  | NYC | BFT | [BFT] NYC MOC + Punch list + NY175 VSD room piping | Somkiat | Tantawan+VE | 25 | 2025-09-05 | 2025-09-24 | 20 | S-FT | S-OUT | S-IN | V-SM-SKL:09/04 > G11:09/05 > G10:09/05 | V-SM-G10:09/25 > G11:09/25 > SKL:09/26
124 | G11 | 25-0071 |  | NYC | AIM | [AIM] TSI: Topside Inspection [Dexon] | Atthapong | DEXON | 4 | 2025-09-07 | 2025-09-28 | 22 | S-FT | S-OUT | S-IN
125 | G1 | 25-0266 |  | FSO | ITM | MAN - RigNet VSAT decommisionning | Pichit | RigNet | 2 | 2025-09-08 | 2025-09-12 | 5 | N-FT | N-OUT | N-IN
126 | G1 | 25-0169 |  |  | WSV | BV test and valve greasing : MNA | Asadawut | Well Service | 5 | 2025-09-30 | 2025-10-14 | 15 | N-FT | N-OUT | N-IN
127 | JAS | 25-0267 |  | ALL PF | ITM | JAS - Server LCM at PPB2 | Pichit | VE+LBS | 2 | 2025-09-25 | 2025-10-01 | 7 | N-FT | N-OUT | N-IN
128 | G11 | 25-0135 |  |  | WSV | NYA-34H: Well Integrity, Investigation for ESP packer / GVV leak | Asadawut | Well Service | 5 | 2025-10-15 | 2025-10-17 | 3 | S-FT | S-OUT | S-IN
129 | JAS | 25-0268 |  | ALL PF | AIM | TSI: Topside Inspection [Dexon] | Pradit | DEXON | 2 | 2025-09-18 | 2025-10-15 | 28 | N-FT | N-OUT | N-IN | V-GY-STH:09/17 > JAS:09/18
130 | JAS | 25-0040 |  | FSO | FSO | Replace Provsion Crane Boom Tip- TOS and 6M Crane proof load test - Thai law | Petrofac | TOS | 4 | 2025-07-10 | 2025-07-25 | 16 | N-FT | N-OUT | N-IN | V-AT-STH:07/09 > JAS:07/10 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
131 | JAS | 25-0087 | 880, 986 | FSO | FSO | Boiler No. 1 Tubing Replacement - Mob 1/RO Unit Installation/COP Spool Replace | Petrofac | Altamar | 16 | 2025-06-14 | 2025-07-09 | 26 | N-FT | N-OUT | N-IN | V-AT-STH:06/13 > G1:06/13 > JAS:06/14 | V-GY-JAS:07/10 > STH:07/11
132 | JAS | 25-0245 | 1178 | WPB | BFT | [BFT] Repair HPWD flowline WPB | Somkiat | Experteam | 11 | 2025-06-25 | 2025-07-01 | 7 | N-FT | N-OUT | N-IN | V-AT-STH:06/24 > JAS:06/25 | V-GY-JAS:07/02 > STH:07/03
133 | JAS | 25-0229 |  | PPB2 | BFT | [BFT] JM319 Wobbe index + GTG + Repair HPWD (VE Sup Anan) | Somkiat | VE | 1 | 2025-06-11 | 2025-07-01 | 21 | N-FT | N-OUT | N-IN | V-G5-STH:06/11 > JAS:06/11 | V-GY-JAS:07/02 > STH:07/03
134 | JAS | 25-0147 | 890 | FSO | FSO | Erect Scaffolding for Boiler No. 1 Tubing Replacement - Mob 1/Group2. | Petrofac | EMC | 2 | 2025-06-14 | 2025-07-09 | 26 | N-FT | N-OUT | N-IN | V-AT-STH:06/13 > G1:06/13 > JAS:06/14 | V-GY-JAS:07/10 > STH:07/11
135 | G10 | 25-0269 | 1083 |  | MNT | VSD tech to go to WAS to support BF installation of newly rental VSD | Suwitcha | BHGE | 1 | 2025-06-27 | 2025-07-01 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:06/27 > G10:06/27 | C-HS-G10:07/02 > SKL:07/02
136 | G10 | 25-0270 | 1148 |  | MNT | Support ICSS programming for WAS051 -VSD-17 Interface at Wassana MOPU | Woraphon | IO | 1 | 2025-06-27 | 2025-07-01 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:06/27 > G10:06/27 | C-HS-G10:07/02 > SKL:07/02
137 | G10 | 25-0247 | 1122 | MOPU | AIM | Wassana Hydro-cyclone cleaning | Atthapong | CR | 4 | 2025-07-04 | 2025-07-13 | 10 | S-FT | S-OUT | S-IN | V-SM-SKL:07/03 > G10:07/04 | V-GX-G10:07/14 > SKL:07/15
138 | JAS | 25-0271 |  | FSO | FSO | Cargo Oil Tank 1C, 1P, and 1S - Intermediate ABS Survey (Tank Cleaning) -Mob1 | Petrofac | TINDY | 11 | 2025-08-21 | 2025-09-14 | 25 | N-FT | N-OUT | N-IN | V-NT-JAS:08/18 > G1:08/18 > JAS:08/21 | V-GY-JAS:09/15 > STH:09/16
139 | JAS | 25-0272 |  | FSO | FSO | Replace Provision Crane Boom Tip -Dexon NDT | Petrofac | DEXON | 1 | 2025-07-14 | 2025-07-16 | 3 | N-FT | N-OUT | N-IN | C-HN-UTP:07/14 > JAS:07/14 | C-HN-JAS:07/17 > UTP:07/17
140 | JAS | 25-0273 |  |  | WSV | JAS C-39/B-16/B-05/B-42/BYA-35ST1/A-15 Slickline | Asadawut | Well Service | 8 | 2025-07-30 | 2025-08-10 | 12 | N-FT | N-OUT | N-IN |  | V-GY-JAS:08/11 > STH:08/12
141 | G1 | 25-0274 |  |  | WSV | MNA-21i wireline | Asadawut | Well Service | 10 | 2025-09-23 | 2025-09-30 | 8 | N-FT | N-OUT | N-IN
142 | JAS | 25-0275 |  | FSO | FSO | Overhaul No.1 & No. 2 Stripping Pump ( and Boiler No. 1 Tubing Replacement - Mob 2.) | Petrofac | Altamar | 1 | 2025-07-19 | 2025-08-13 | 26 | N-FT | N-OUT | N-IN | C-HN-UTP:07/19 > JAS:07/19 | C-HN-JAS:08/14 > UTP:08/14
143 | JAS | 25-0276 |  | FSO | FSO | Intermediate ABS Survey Mob 2. | Petrofac | ABS | 1 | 2025-09-25 | 2025-09-28 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:09/25 > JAS:09/25 | C-HN-JAS:09/29 > UTP:09/29
144 | JAS | 25-0277 |  | FSO | FSO | Intermediate Class Survey Mob 1. / Annual Survey | Petrofac | ABS | 1 | 2025-09-08 | 2025-09-10 | 3 | N-FT | N-OUT | N-IN | C-HN-UTP:09/08 > JAS:09/08 | C-HN-JAS:09/11 > UTP:09/11
145 | JAS | 25-0278 |  | FSO | FSO | Annual Critical Area Inspection for Topside & Flare Tower Interface - outstanding from Baseline | Petrofac | DEXON | 1 | 2025-09-08 | 2025-09-10 | 3 | N-FT | N-OUT | N-IN | C-HN-UTP:09/08 > JAS:09/08 | C-HN-JAS:09/11 > UTP:09/11
146 | JAS | 25-0279 |  |  | FSO | Cargo Oil Tank 1C, 1P, and 1S and 4P- Intermediate ABS Survey (Tank Cleaning) -Mob2 | Petrofac | TINDY | 18 | 2025-09-18 | 2025-09-30 | 13 | N-FT | N-OUT | N-IN | V-GY-STH:09/17 > JAS:09/18
147 | JAS | 25-0280 |  | FSO | OFF | Offtake JC-689 | Benjachai |  | 3 | 2025-09-08 | 2025-09-12 | 5 | N-FT | N-OUT | N-IN
148 | JAS | 25-0281 |  | FSO | OFF | Offtake JC-690 | Benjachai |  | 3 | 2025-09-21 | 2025-09-25 | 5 | N-FT | N-OUT | N-IN
149 | G1 | 25-0282 |  | FSO | OFF | Offtake MC-134 | Benjachai |  | 3 | 2025-09-26 | 2025-09-30 | 5 | N-FT | N-OUT | N-IN
150 | G11 | 25-0283 |  | FSO | OFF | Offtake NC-130 | Benjachai |  | 3 | 2025-09-11 | 2025-09-15 | 5 | S-FT | S-OUT | S-IN
151 | G1 | 25-0284 |  |  | BFT | [BFT] SD MN131 Manora debottleneck ABB #2 | Wason | ABB | 2 | 2025-07-14 | 2025-07-25 | 12 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > G1:07/14 | V-G5-JAS:07/26 > G1:07/26 > STH:07/26
152 | G1 | 25-0285 |  |  | BFT | [BFT] SD MN131 Manora debottleneck Sulzer #1 | Wason | Sulzer | 2 | 2025-07-20 | 2025-07-29 | 10 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > G1:07/20 | V-GY-JAS:07/27 > G1:07/27 > STH:07/28
153 | G1 | 25-0286 |  | WPP | MNT | MANORA Debottleneck DMC Load shedding configuration | Warakorn | Infinite | 2 | 2025-07-26 | 2025-08-01 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:07/26 > G1:07/26 | C-HN-G1:08/02 > UTP:08/02
154 | JAS | 25-0287 |  | FSO | FSO | Cargo Oil Tank 1C, 1P, and 1S - Intermediate ABS Survey (Tank Cleaning) -Mob1 | Petrofac | TINDY | 7 | 2025-08-26 | 2025-09-14 | 20 | N-FT | N-OUT | N-IN | V-NT-STH:08/25 > JAS:08/26 | V-GY-JAS:09/15 > STH:09/16
155 | G11 | 25-0288 |  | NYC | AIM | [AIM] NYC: Maintenance Painting [TCS + AI Sup] | Mittrapa | TCS / AI Sup | 19 | 2025-08-12 | 2025-08-30 | 19 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > G11:08/12 | V-SM-G11:08/31 > G10:08/31 > SKL:09/01
156 | JAS | 25-0289 |  | PPB2 | BFT | [BFT] JM319 GTG Commissioning | Wason | Pico , VE Eng , PCC , Solar , TNS , Expert , Enerproject | 13 | 2025-07-07 | 2025-07-17 | 11 | N-FT | N-OUT | N-IN | V-G5-STH:07/07 > JAS:07/07 | V-GY-JAS:07/18 > STH:07/19
157 | G10 | 25-0290 |  |  | FSO | Management visit | Kritsana | Three60 | 2 | 2025-06-27 | 2025-07-01 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:06/27 > G10:06/27 | C-HS-G10:07/02 > SKL:07/02
158 | G10 | 25-0291 |  |  | FSO | SEACOM audit | Kritsana | SEACOM | 1 | 2025-07-30 | 2025-07-31 | 2 | S-FT | S-OUT | S-IN | C-HS-SKL:07/30 > G10:07/30 | C-HS-G10:08/01 > SKL:08/01
159 | G10 | 25-0293 |  | MOPU | AIM | MOPU UWILD + Inspection for Life Extension [Dexon] | Mittrapa | DEXON | 3 | 2025-08-23 | 2025-08-30 | 8 | S-FT | S-OUT | S-IN | V-GX-SKL:08/22 > G10:08/23 | V-SM-G11:08/31 > G10:08/31 > SKL:09/01
160 | G10 | 25-0294 |  | MOPU | AIM | MOPU UWILD + Life Extension [BV+Egg] | Mittrapa | BV / VE | 2 | 2025-08-23 | 2025-08-30 | 8 | S-FT | S-OUT | S-IN | V-GX-SKL:08/22 > G10:08/23 | V-SM-G11:08/31 > G10:08/31 > SKL:09/01
161 | G10 | 25-0295 |  | MOPU | MNT | WSA-20 startup | Suwitcha | BHGE | 1 | 2025-07-23 | 2025-07-29 | 7 | S-FT | S-OUT | S-IN
162 | G11 | 25-0296 |  | NYC | HSSE | [HSSE] Lifeboat repair & wire rope replacement, and inspection CO2 system | Thanagon | MSC | 3 | 2025-08-03 | 2025-08-18 | 16 | S-FT | S-OUT | S-IN | V-SM-SKL:08/02 > G11:08/03 > G10:08/03 | V-SM-G11:08/19 > G10:08/19 | back to SKL by GX mob on 20 Aug
163 | G10 | 25-0248 | 1227 | WSA | MNT | Chloride UPS Apodys 1 - Alarm time out checking | Ohmmanas | WEA-ASIA | 1 | 2025-07-02 | 2025-07-03 | 2 | S-FT | S-OUT | S-IN | C-HS-SKL:07/02 > G10:07/02 | C-HS-G10:07/04 > SKL:07/04
164 | G1 | 25-0297 |  | FSO | OFF | Offtake MC-133#2 (DMF) | Benjachai | DMF | 1 | 2025-07-15 | 2025-07-15 | 1
165 | G10 | 25-0298 |  | MOPU | OPS | Management visit | Tanarat | VE | 11 | 2025-08-13 | 2025-08-13 | 1 | S-FT | S-OUT | S-IN |  |  | Special flight
166 | G11 | 25-0299 |  |  | OPS | Management visit | Chutarat | VE | 11 | 2025-08-14 | 2025-08-14 | 1 | S-FT | S-OUT | S-IN

## Boat_Plan
Id | Type | Boat_Name | Direction | Origin | Destination | Dep_Date | Dep_Time | Arr_Date | Arr_Time | Code | Trip_Id
1 | VESSEL | SUMMER | IN | G10 | SKL | 2025-07-01 | 7 | 2025-07-01 | 12 | S-IN | V-SM-G10:07/01 > SKL:07/01
2 | VESSEL | SUMMER | FT | G11 | SKL | 2025-07-01 | 17 | 2025-07-02 | 7 | S-FT | V-SM-G11:07/01 > SKL:07/02
3 | VESSEL | GLORY5 | IN | JAS | STH | 2025-07-01 | 21 | 2025-07-02 | 5 | N-IN | V-G5-JAS:07/01 > STH:07/02
4 | VESSEL | GLORY5 | OUT | STH | G1 | 2025-07-02 | 7 | 2025-07-02 | 11 | N-OUT | V-G5-STH:07/02 > G1:07/02
5 | VESSEL | GLORY5 | FT | G1 | JAS | 2025-07-02 | 12 | 2025-07-02 | 16 | N-FT | V-G5-G1:07/02 > JAS:07/02
6 | VESSEL | GANYA | IN | JAS | STH | 2025-07-02 | 18 | 2025-07-03 | 6 | N-IN | V-GY-JAS:07/02 > STH:07/03
7 | VESSEL | GANYA | OUT | STH | JAS | 2025-07-04 | 18 | 2025-07-05 | 6 | N-OUT | V-GY-STH:07/04 > JAS:07/05
8 | VESSEL | GLORY5 | IN | JAS | STH | 2025-07-05 | 8 | 2025-07-05 | 16 | N-IN | V-G5-JAS:07/05 > STH:07/05
9 | VESSEL | SUMMER | OUT | SKL | G10 | 2025-07-03 | 18 | 2025-07-04 | 7 | S-OUT | V-SM-SKL:07/03 > G10:07/04
10 | VESSEL | UNIVERSE | IN | G11 | G10 | 2025-07-06 | 13 | 2025-07-06 | 17 | S-IN | V-UV-G11:07/06 > G10:07/06
11 | VESSEL | UNIVERSE | IN | G10 | SKL | 2025-07-06 | 18 | 2025-07-07 | 7 | S-IN | V-UV-G10:07/06 > SKL:07/07
12 | VESSEL | GLORY5 | OUT | STH | JAS | 2025-07-07 | 8 | 2025-07-07 | 16 | N-OUT | V-G5-STH:07/07 > JAS:07/07
13 | VESSEL | ATHENA | IN | JAS | STH | 2025-07-07 | 18 | 2025-07-08 | 6 | N-IN | V-AT-JAS:07/07 > STH:07/08
14 | VESSEL | UNIVERSE | OUT | SKL | G11 | 2025-07-08 | 17 | 2025-07-09 | 7 | S-OUT | V-UV-SKL:07/08 > G11:07/09
15 | VESSEL | GALAXY | FT | G10 | G11 | 2025-07-06 | 12 | 2025-07-06 | 17 | S-FT | V-GX-G10:07/06 > G11:07/06
16 | VESSEL | GALAXY | FT | G11 | G10 | 2025-07-09 | 7 | 2025-07-09 | 12 | S-FT | V-GX-G11:07/09 > G10:07/09
17 | VESSEL | ATHENA | OUT | STH | JAS | 2025-07-09 | 18 | 2025-07-10 | 6 | N-OUT | V-AT-STH:07/09 > JAS:07/10
18 | VESSEL | GANYA | IN | JAS | STH | 2025-07-10 | 18 | 2025-07-11 | 6 | N-IN | V-GY-JAS:07/10 > STH:07/11
19 | VESSEL | GANYA | OUT | STH | G1 | 2025-07-11 | 20 | 2025-07-12 | 4 | N-OUT | V-GY-STH:07/11 > G1:07/12
20 | VESSEL | GANYA | FT | G1 | JAS | 2025-07-12 | 7 | 2025-07-12 | 15 | N-FT | V-GY-G1:07/12 > JAS:07/12
21 | VESSEL | ATHENA | FT | JAS | G1 | 2025-07-12 | 18 | 2025-07-13 | 2 | N-FT | V-AT-JAS:07/12 > G1:07/13
22 | VESSEL | NEPTUNE | IN | G1 | STH | 2025-07-13 | 2 | 2025-07-13 | 10 | N-IN | V-TC-G1:07/13 > STH:07/13
23 | VESSEL | SUMMER | IN | G10 | SKL | 2025-07-11 | 18 | 2025-07-12 | 6 | S-IN | V-SM-G10:07/11 > SKL:07/12
24 | VESSEL | NEPTUNE | OUT | STH | G1 | 2025-07-14 | 9 | 2025-07-14 | 17 | N-OUT | V-TC-STH:07/14 > G1:07/14
25 | VESSEL | SUMMER | OUT | SKL | G10 | 2025-07-12 | 18 | 2025-07-13 | 6 | S-OUT | V-SM-SKL:07/12 > G10:07/13
26 | VESSEL | GANYA | IN | JAS | STH | 2025-07-18 | 18 | 2025-07-19 | 6 | N-IN | V-GY-JAS:07/18 > STH:07/19
27 | VESSEL | GANYA | OUT | STH | G1 | 2025-07-19 | 21 | 2025-07-20 | 6 | N-OUT | V-GY-STH:07/19 > G1:07/20
28 | VESSEL | GALAXY | IN | G10 | SKL | 2025-07-14 | 18 | 2025-07-15 | 6 | S-IN | V-GX-G10:07/14 > SKL:07/15
29 | VESSEL | GALAXY | OUT | SKL | G11 | 2025-07-15 | 18 | 2025-07-16 | 7 | S-OUT | V-GX-SKL:07/15 > G11:07/16
30 | VESSEL | GALAXY | IN | G11 | G10 | 2025-07-20 | 7 | 2025-07-20 | 11 | S-IN | V-GX-G11:07/20 > G10:07/20
31 | VESSEL | GALAXY |  | G10 | SKL | 2025-07-20 | 17 | 2025-07-21 | 6 | FALSE | V-GX-G10:07/20 > SKL:07/21
32 | VESSEL | GALAXY | OUT | SKL | G10 | 2025-07-22 | 17 | 2025-07-23 | 6 | S-OUT | V-GX-SKL:07/22 > G10:07/23
33 | VESSEL | SUMMER | IN | G10 | G11 | 2025-07-23 | 8 | 2025-07-23 | 13 | S-IN | V-SM-G10:07/23 > G11:07/23
34 | VESSEL | SUMMER |  | G11 | SKL | 2025-07-23 | 17 | 2025-07-24 | 7 | FALSE | V-SM-G11:07/23 > SKL:07/24
35 | VESSEL | NATA | IN | G1 | STH | 2025-06-30 | 1 | 2025-06-30 | 10 | N-IN | V-NT-G1:06/30 > STH:06/30
36 | VESSEL | NATA | OUT | STH | G10 | 2025-06-30 | 23 | 2025-07-02 | 19 | S-OUT | V-NT-STH:06/30 > G10:07/02
37 | VESSEL | NATA | OUT | STH | JAS | 2025-07-30 | 18 | 2025-07-31 | 6 | N-OUT | V-NT-STH:07/30 > JAS:07/31
38 | VESSEL | ATHENA | IN | G1 | STH | 2025-07-16 | 20 | 2025-07-17 | 6 | N-IN | V-AT-G1:07/16 > STH:07/17
39 | VESSEL | ATHENA | OUT | STH | JAS | 2025-07-17 | 17 | 2025-07-18 | 6 | N-OUT | V-AT-STH:07/17 > JAS:07/18
40 | VESSEL | ATHENA | IN | JAS | SKL | 2025-07-31 | 10 | 2025-08-02 | 6 | N-IN | V-AT-JAS:07/31 > SKL:08/02
41 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-07-25 | 17 | 2025-07-26 | 8 | S-OUT | V-SM-SKL:07/25 > G11:07/26
42 | VESSEL | GLORY5 | IN | JAS | G1 | 2025-07-26 | 8 | 2025-07-26 | 12 | N-IN | V-G5-JAS:07/26 > G1:07/26
43 | VESSEL | GLORY5 |  | G1 | STH | 2025-07-26 | 13 | 2025-07-26 | 17 | FALSE | V-G5-G1:07/26 > STH:07/26
44 | VESSEL | GLORY5 | OUT | STH | JAS | 2025-07-26 | 20 | 2025-07-27 | 5 | N-OUT | V-G5-STH:07/26 > JAS:07/27
45 | VESSEL | UNIVERSE | IN | G11 | SKL | 2025-07-26 | 17 | 2025-07-27 | 7 | S-IN | V-UV-G11:07/26 > SKL:07/27
46 | VESSEL | GANYA | FT | G1 | JAS | 2025-07-26 | 8 | 2025-07-26 | 16 | N-FT | V-GY-G1:07/26 > JAS:07/26
47 | VESSEL | GANYA | IN | JAS | G1 | 2025-07-27 | 10 | 2025-07-27 | 17 | N-IN | V-GY-JAS:07/27 > G1:07/27
48 | VESSEL | GANYA |  | G1 | STH | 2025-07-27 | 21 | 2025-07-28 | 6 | FALSE | V-GY-G1:07/27 > STH:07/28
49 | VESSEL | UNIVERSE | OUT | SKL | G11 | 2025-07-28 | 17 | 2025-07-29 | 7 | S-OUT | V-UV-SKL:07/28 > G11:07/29
50 | VESSEL | GANYA | OUT | STH | JAS | 2025-07-29 | 18 | 2025-07-30 | 6 | N-OUT | V-GY-STH:07/29 > JAS:07/30
51 | VESSEL | SUMMER | IN | G11 | G10 | 2025-07-29 | 7 | 2025-07-29 | 12 | S-IN | V-SM-G11:07/29 > G10:07/29
52 | VESSEL | SUMMER |  | G10 | SKL | 2025-07-29 | 17 | 2025-07-30 | 6 | FALSE | V-SM-G10:07/29 > SKL:07/30
53 | VESSEL | NEPTUNE | IN | G1 | STH | 2025-08-02 | 20 | 2025-08-03 | 6 | N-IN | V-TC-G1:08/02 > STH:08/03
54 | VESSEL | NATA | FT | JAS | G1 | 2025-08-02 | 12 | 2025-08-02 | 20 | N-FT | V-NT-JAS:08/02 > G1:08/02
55 | VESSEL | NATA | FT | G1 | JAS | 2025-08-04 | 19 | 2025-08-05 | 3 | N-FT | V-NT-G1:08/04 > JAS:08/05
56 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-08-02 | 16 | 2025-08-03 | 6 | S-OUT | V-SM-SKL:08/02 > G11:08/03
57 | VESSEL | SUMMER | FT | G11 | G10 | 2025-08-03 | 10 | 2025-08-03 | 15 | S-FT | V-SM-G11:08/03 > G10:08/03
58 | VESSEL | GALAXY | IN | G10 | SKL | 2025-08-03 | 18 | 2025-08-04 | 7 | S-IN | V-GX-G10:08/03 > SKL:08/04
59 | VESSEL | NEPTUNE | OUT | STH | STH | 2025-08-04 | 9 | 2025-08-04 | 17 | FALSE | V-TC-STH:08/04 > STH:08/04
60 | VESSEL | GALAXY | OUT | SKL | G10 | 2025-08-05 | 18 | 2025-08-06 | 6 | S-OUT | V-GX-SKL:08/05 > G10:08/06
61 | VESSEL | NATA | IN | JAS | STH | 2025-08-05 | 18 | 2025-08-06 | 6 | N-IN | V-NT-JAS:08/05 > STH:08/06
62 | VESSEL | SUMMER | IN | G10 | G11 | 2025-08-06 | 7 | 2025-08-06 | 12 | S-IN | V-SM-G10:08/06 > G11:08/06
63 | VESSEL | SUMMER |  | G11 | SKL | 2025-08-06 | 17 | 2025-08-07 | 7 | FALSE | V-SM-G11:08/06 > SKL:08/07
64 | VESSEL | NATA | OUT | STH | JAS | 2025-08-07 | 18 | 2025-08-08 | 6 | N-OUT | V-NT-STH:08/07 > JAS:08/08
65 | VESSEL | GLORY5 | IN | JAS | STH | 2025-08-08 | 8 | 2025-08-08 | 16 | N-IN | V-G5-JAS:08/08 > STH:08/08
66 | VESSEL | GLORY5 | OUT | STH | JAS | 2025-08-10 | 8 | 2025-08-10 | 16 | N-OUT | V-G5-STH:08/10 > JAS:08/10
67 | VESSEL | GANYA | IN | JAS | STH | 2025-08-11 | 18 | 2025-08-12 | 6 | N-IN | V-GY-JAS:08/11 > STH:08/12
68 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-08-11 | 17 | 2025-08-12 | 7 | S-OUT | V-SM-SKL:08/11 > G11:08/12
69 | VESSEL | UNIVERSE | IN | G11 | SKL | 2025-08-12 | 17 | 2025-08-13 | 7 | S-IN | V-UV-G11:08/12 > SKL:08/13
70 | VESSEL | GANYA | OUT | STH | JAS | 2025-08-13 | 18 | 2025-08-14 | 6 | N-OUT | V-GY-STH:08/13 > JAS:08/14
71 | VESSEL | UNIVERSE | OUT | SKL | G11 | 2025-08-14 | 17 | 2025-08-15 | 7 | S-OUT | V-UV-SKL:08/14 > G11:08/15
72 | VESSEL | NEPTUNE | IN | G1 | STH | 2025-08-18 | 20 | 2025-08-19 | 6 | N-IN | V-TC-G1:08/18 > STH:08/19
73 | VESSEL | NATA | FT | JAS | G1 | 2025-08-18 | 12 | 2025-08-18 | 20 | N-FT | V-NT-JAS:08/18 > G1:08/18
74 | VESSEL | NATA | FT | G1 | JAS | 2025-08-21 | 7 | 2025-08-21 | 15 | N-FT | V-NT-G1:08/21 > JAS:08/21
75 | VESSEL | SUMMER | FT | G11 | G10 | 2025-08-19 | 18 | 2025-08-19 | 23 | S-FT | V-SM-G11:08/19 > G10:08/19
76 | VESSEL | GALAXY | IN | G10 | SKL | 2025-08-20 | 8 | 2025-08-20 | 20 | S-IN | V-GX-G10:08/20 > SKL:08/20
77 | VESSEL | NEPTUNE | OUT | STH | STH | 2025-08-20 | 20 | 2025-08-21 | 5 | FALSE | V-TC-STH:08/20 > STH:08/21
78 | VESSEL | GALAXY | OUT | SKL | G10 | 2025-08-22 | 17 | 2025-08-23 | 6 | S-OUT | V-GX-SKL:08/22 > G10:08/23
79 | VESSEL | NATA | IN | JAS | STH | 2025-08-23 | 18 | 2025-08-24 | 6 | N-IN | V-NT-JAS:08/23 > STH:08/24
80 | VESSEL | SUMMER | IN | G10 | G11 | 2025-08-23 | 7 | 2025-08-23 | 12 | S-IN | V-SM-G10:08/23 > G11:08/23
81 | VESSEL | SUMMER |  | G11 | SKL | 2025-08-23 | 17 | 2025-08-24 | 7 | FALSE | V-SM-G11:08/23 > SKL:08/24
82 | VESSEL | NATA | OUT | STH | JAS | 2025-08-25 | 18 | 2025-08-26 | 6 | N-OUT | V-NT-STH:08/25 > JAS:08/26
83 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-08-27 | 17 | 2025-08-28 | 7 | S-OUT | V-SM-SKL:08/27 > G11:08/28
84 | VESSEL | UNIVERSE | IN | G11 | SKL | 2025-08-28 | 17 | 2025-08-29 | 7 | S-IN | V-UV-G11:08/28 > SKL:08/29
85 | VESSEL | GANYA | IN | JAS | STH | 2025-08-30 | 18 | 2025-08-31 | 6 | N-IN | V-GY-JAS:08/30 > STH:08/31
86 | VESSEL | UNIVERSE | OUT | SKL | G11 | 2025-08-30 | 17 | 2025-08-31 | 7 | S-OUT | V-UV-SKL:08/30 > G11:08/31
87 | VESSEL | SUMMER | IN | G11 | G10 | 2025-08-31 | 8 | 2025-08-31 | 13 | S-IN | V-SM-G11:08/31 > G10:08/31
88 | VESSEL | SUMMER |  | G10 | SKL | 2025-08-31 | 17 | 2025-09-01 | 6 | FALSE | V-SM-G10:08/31 > SKL:09/01
89 | VESSEL | GANYA | OUT | STH | G1 | 2025-09-01 | 18 | 2025-09-02 | 4 | N-OUT | V-GY-STH:09/01 > G1:09/02
90 | VESSEL | GANYA |  | G1 | JAS | 2025-09-02 | 6 | 2025-09-02 | 14 | FALSE | V-GY-G1:09/02 > JAS:09/02
91 | VESSEL | NATA | IN | JAS | STH | 2025-09-02 | 18 | 2025-09-03 | 7 | N-IN | V-NT-JAS:09/02 > STH:09/03
92 | VESSEL | NATA | OUT | STH | JAS | 2025-09-04 | 18 | 2025-09-05 | 7 | N-OUT | V-NT-STH:09/04 > JAS:09/05
93 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-09-04 | 16 | 2025-09-05 | 7 | S-OUT | V-SM-SKL:09/04 > G11:09/05
94 | VESSEL | SUMMER | FT | G11 | G10 | 2025-09-05 | 10 | 2025-09-05 | 15 | S-FT | V-SM-G11:09/05 > G10:09/05
95 | VESSEL | GANYA | FT | JAS | G1 | 2025-09-05 | 12 | 2025-09-05 | 20 | N-FT | V-GY-JAS:09/05 > G1:09/05
96 | VESSEL | GANYA |  | G1 | JAS | 2025-09-08 | 7 | 2025-09-08 | 15 | FALSE | V-GY-G1:09/08 > JAS:09/08
97 | VESSEL | NEPTUNE | IN | G1 | STH | 2025-09-05 | 20 | 2025-09-06 | 6 | N-IN | V-TC-G1:09/05 > STH:09/06
98 | VESSEL | GALAXY | IN | G10 | SKL | 2025-09-05 | 18 | 2025-09-06 | 6 | S-IN | V-GX-G10:09/05 > SKL:09/06
99 | VESSEL | NEPTUNE | OUT | STH | G1 | 2025-09-07 | 20 | 2025-09-08 | 6 | N-OUT | V-TC-STH:09/07 > G1:09/08
100 | VESSEL | GALAXY | OUT | SKL | G10 | 2025-09-07 | 17 | 2025-09-08 | 6 | S-OUT | V-GX-SKL:09/07 > G10:09/08
101 | VESSEL | SUMMER | IN | G10 | G11 | 2025-09-08 | 7 | 2025-09-08 | 12 | S-IN | V-SM-G10:09/08 > G11:09/08
102 | VESSEL | SUMMER |  | G11 | SKL | 2025-09-08 | 16 | 2025-09-09 | 7 | FALSE | V-SM-G11:09/08 > SKL:09/09
103 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-09-10 | 16 | 2025-09-11 | 7 | S-OUT | V-SM-SKL:09/10 > G11:09/11
104 | VESSEL | GLORY5 | IN | JAS | STH | 2025-09-12 | 8 | 2025-09-12 | 16 | N-IN | V-G5-JAS:09/12 > STH:09/12
105 | VESSEL | GLORY5 | OUT | STH | JAS | 2025-09-14 | 8 | 2025-09-14 | 16 | N-OUT | V-G5-STH:09/14 > JAS:09/14
106 | VESSEL | GANYA | IN | JAS | STH | 2025-09-15 | 18 | 2025-09-16 | 7 | N-IN | V-GY-JAS:09/15 > STH:09/16
107 | VESSEL | UNIVERSE | IN | G11 | SKL | 2025-09-15 | 17 | 2025-09-16 | 7 | S-IN | V-UV-G11:09/15 > SKL:09/16
108 | VESSEL | GANYA | OUT | STH | JAS | 2025-09-17 | 18 | 2025-09-18 | 7 | N-OUT | V-GY-STH:09/17 > JAS:09/18
109 | VESSEL | UNIVERSE | OUT | SKL | G11 | 2025-09-17 | 16 | 2025-09-18 | 7 | S-OUT | V-UV-SKL:09/17 > G11:09/18
110 | VESSEL | NATA | IN | JAS | STH | 2025-09-18 | 18 | 2025-09-19 | 7 | N-IN | V-NT-JAS:09/18 > STH:09/19
111 | VESSEL | SUMMER | IN | G11 | G10 | 2025-09-18 | 9 | 2025-09-18 | 14 | S-IN | V-SM-G11:09/18 > G10:09/18
112 | VESSEL | SUMMER |  | G10 | SKL | 2025-09-18 | 18 | 2025-09-19 | 7 | FALSE | V-SM-G10:09/18 > SKL:09/19
113 | VESSEL | NATA | OUT | STH | JAS | 2025-09-20 | 18 | 2025-09-21 | 7 | N-OUT | V-NT-STH:09/20 > JAS:09/21
114 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-09-21 | 16 | 2025-09-22 | 7 | S-OUT | V-SM-SKL:09/21 > G11:09/22
115 | VESSEL | SUMMER | FT | G11 | G10 | 2025-09-22 | 10 | 2025-09-22 | 15 | S-FT | V-SM-G11:09/22 > G10:09/22
116 | VESSEL | GALAXY | IN | G10 | SKL | 2025-09-22 | 18 | 2025-09-23 | 6 | S-IN | V-GX-G10:09/22 > SKL:09/23
117 | VESSEL | GALAXY | OUT | SKL | G10 | 2025-09-24 | 17 | 2025-09-25 | 6 | S-OUT | V-GX-SKL:09/24 > G10:09/25
118 | VESSEL | NEPTUNE | IN | G1 | STH | 2025-09-25 | 20 | 2025-09-26 | 6 | N-IN | V-TC-G1:09/25 > STH:09/26
119 | VESSEL | GANYA | FT | JAS | G1 | 2025-09-25 | 12 | 2025-09-25 | 20 | N-FT | V-GY-JAS:09/25 > G1:09/25
120 | VESSEL | GANYA | FT | G1 | JAS | 2025-10-01 | 12 | 2025-10-01 | 20 | N-FT | V-GY-G1:10/01 > JAS:10/01
121 | VESSEL | SUMMER | IN | G10 | G11 | 2025-09-25 | 8 | 2025-09-25 | 13 | S-IN | V-SM-G10:09/25 > G11:09/25
122 | VESSEL | SUMMER |  | G11 | SKL | 2025-09-25 | 17 | 2025-09-26 | 8 | FALSE | V-SM-G11:09/25 > SKL:09/26
123 | VESSEL | NEPTUNE | OUT | STH | G1 | 2025-09-27 | 8 | 2025-09-27 | 17 | N-OUT | V-TC-STH:09/27 > G1:09/27
124 | VESSEL | SUMMER | OUT | SKL | G11 | 2025-09-30 | 16 | 2025-10-01 | 7 | S-OUT | V-SM-SKL:09/30 > G11:10/01

## Chopper_Plan
Id | Type | Vessel | Dir | Origin | Destination | Dep_Date | Arr_Date | Code | Trip_Id
1 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-01 | 2025-02-01 | N-OUT | C-HN-UTP:02/01 > JAS:02/01
2 | CHOPPER | HN | IN | JAS | UTP | 2025-02-01 | 2025-02-01 | N-IN | C-HN-JAS:02/01 > UTP:02/01
3 | CHOPPER | HN | OUT | UTP | G1 | 2025-02-01 | 2025-02-01 | N-OUT | C-HN-UTP:02/01 > G1:02/01
4 | CHOPPER | HN | IN | G1 | UTP | 2025-02-01 | 2025-02-01 | N-IN | C-HN-G1:02/01 > UTP:02/01
5 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-03 | 2025-02-03 | N-OUT | C-HN-UTP:02/03 > JAS:02/03
6 | CHOPPER | HN | IN | JAS | UTP | 2025-02-03 | 2025-02-03 | N-IN | C-HN-JAS:02/03 > UTP:02/03
7 | CHOPPER | HN | OUT | UTP | G1 | 2025-02-03 | 2025-02-03 | N-OUT | C-HN-UTP:02/03 > G1:02/03
8 | CHOPPER | HN | IN | G1 | UTP | 2025-02-03 | 2025-02-03 | N-IN | C-HN-G1:02/03 > UTP:02/03
9 | CHOPPER | HS | OUT | SKL | G11 | 2025-02-05 | 2025-02-05 | S-OUT | C-HS-SKL:02/05 > G11:02/05
10 | CHOPPER | HS | IN | G11 | SKL | 2025-02-05 | 2025-02-05 | S-IN | C-HS-G11:02/05 > SKL:02/05
11 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-05 | 2025-02-05 | S-OUT | C-HS-SKL:02/05 > G10:02/05
12 | CHOPPER | HS | IN | G10 | SKL | 2025-02-05 | 2025-02-05 | S-IN | C-HS-G10:02/05 > SKL:02/05
13 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-07 | 2025-02-07 | S-OUT | C-HS-SKL:02/07 > G10:02/07
14 | CHOPPER | HS | IN | G10 | SKL | 2025-02-07 | 2025-02-07 | S-IN | C-HS-G10:02/07 > SKL:02/07
15 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-08 | 2025-02-08 | N-OUT | C-HN-UTP:02/08 > JAS:02/08
16 | CHOPPER | HN | IN | JAS | UTP | 2025-02-08 | 2025-02-08 | N-IN | C-HN-JAS:02/08 > UTP:02/08
17 | CHOPPER | HN | OUT | UTP | G1 | 2025-02-08 | 2025-02-08 | N-OUT | C-HN-UTP:02/08 > G1:02/08
18 | CHOPPER | HN | IN | G1 | UTP | 2025-02-08 | 2025-02-08 | N-IN | C-HN-G1:02/08 > UTP:02/08
19 | CHOPPER | HS | OUT | SKL | G11 | 2025-02-08 | 2025-02-08 | S-OUT | C-HS-SKL:02/08 > G11:02/08
20 | CHOPPER | HS | IN | G11 | SKL | 2025-02-08 | 2025-02-08 | S-IN | C-HS-G11:02/08 > SKL:02/08
21 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-10 | 2025-02-10 | N-OUT | C-HN-UTP:02/10 > JAS:02/10
22 | CHOPPER | HN | IN | JAS | UTP | 2025-02-10 | 2025-02-10 | N-IN | C-HN-JAS:02/10 > UTP:02/10
23 | CHOPPER | HS | OUT | SKL | G11 | 2025-02-12 | 2025-02-12 | S-OUT | C-HS-SKL:02/12 > G11:02/12
24 | CHOPPER | HS | IN | G11 | SKL | 2025-02-12 | 2025-02-12 | S-IN | C-HS-G11:02/12 > SKL:02/12
25 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-12 | 2025-02-12 | S-OUT | C-HS-SKL:02/12 > G10:02/12
26 | CHOPPER | HS | IN | G10 | SKL | 2025-02-12 | 2025-02-12 | S-IN | C-HS-G10:02/12 > SKL:02/12
27 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-13 | 2025-02-13 | N-OUT | C-HN-UTP:02/13 > JAS:02/13
28 | CHOPPER | HN | IN | JAS | UTP | 2025-02-13 | 2025-02-13 | N-IN | C-HN-JAS:02/13 > UTP:02/13
29 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-14 | 2025-02-14 | S-OUT | C-HS-SKL:02/14 > G10:02/14
30 | CHOPPER | HS | IN | G10 | SKL | 2025-02-14 | 2025-02-14 | S-IN | C-HS-G10:02/14 > SKL:02/14
31 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-15 | 2025-02-15 | N-OUT | C-HN-UTP:02/15 > JAS:02/15
32 | CHOPPER | HN | IN | JAS | UTP | 2025-02-15 | 2025-02-15 | N-IN | C-HN-JAS:02/15 > UTP:02/15
33 | CHOPPER | HN | OUT | UTP | G1 | 2025-02-15 | 2025-02-15 | N-OUT | C-HN-UTP:02/15 > G1:02/15
34 | CHOPPER | HN | FT | G1 | JAS | 2025-02-15 | 2025-02-15 | N-FT | C-HN-G1:02/15 > JAS:02/15
35 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-17 | 2025-02-17 | N-OUT | C-HN-UTP:02/17 > JAS:02/17
36 | CHOPPER | HN | IN | JAS | UTP | 2025-02-17 | 2025-02-17 | N-IN | C-HN-JAS:02/17 > UTP:02/17
37 | CHOPPER | HN | OUT | UTP | G1 | 2025-02-17 | 2025-02-17 | N-OUT | C-HN-UTP:02/17 > G1:02/17
38 | CHOPPER | HN | IN | G1 | UTP | 2025-02-17 | 2025-02-17 | N-IN | C-HN-G1:02/17 > UTP:02/17
39 | CHOPPER | HS | OUT | SKL | G11 | 2025-02-19 | 2025-02-19 | S-OUT | C-HS-SKL:02/19 > G11:02/19
40 | CHOPPER | HS | IN | G11 | SKL | 2025-02-19 | 2025-02-19 | S-IN | C-HS-G11:02/19 > SKL:02/19
41 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-19 | 2025-02-19 | S-OUT | C-HS-SKL:02/19 > G10:02/19
42 | CHOPPER | HS | IN | G10 | SKL | 2025-02-19 | 2025-02-19 | S-IN | C-HS-G10:02/19 > SKL:02/19
43 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-22 | 2025-02-22 | N-OUT | C-HN-UTP:02/22 > JAS:02/22
44 | CHOPPER | HN | IN | JAS | UTP | 2025-02-22 | 2025-02-22 | N-IN | C-HN-JAS:02/22 > UTP:02/22
45 | CHOPPER | HN | OUT | UTP | G1 | 2025-02-22 | 2025-02-22 | N-OUT | C-HN-UTP:02/22 > G1:02/22
46 | CHOPPER | HN | IN | G1 | UTP | 2025-02-22 | 2025-02-22 | N-IN | C-HN-G1:02/22 > UTP:02/22
47 | CHOPPER | HS | OUT | SKL | G11 | 2025-02-22 | 2025-02-22 | S-OUT | C-HS-SKL:02/22 > G11:02/22
48 | CHOPPER | HS | IN | G11 | SKL | 2025-02-22 | 2025-02-22 | S-IN | C-HS-G11:02/22 > SKL:02/22
49 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-24 | 2025-02-24 | N-OUT | C-HN-UTP:02/24 > JAS:02/24
50 | CHOPPER | HN | IN | JAS | UTP | 2025-02-24 | 2025-02-24 | N-IN | C-HN-JAS:02/24 > UTP:02/24
51 | CHOPPER | HS | OUT | SKL | G11 | 2025-02-26 | 2025-02-26 | S-OUT | C-HS-SKL:02/26 > G11:02/26
52 | CHOPPER | HS | IN | G11 | SKL | 2025-02-26 | 2025-02-26 | S-IN | C-HS-G11:02/26 > SKL:02/26
53 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-26 | 2025-02-26 | S-OUT | C-HS-SKL:02/26 > G10:02/26
54 | CHOPPER | HS | IN | G10 | SKL | 2025-02-26 | 2025-02-26 | S-IN | C-HS-G10:02/26 > SKL:02/26
55 | CHOPPER | HN | OUT | UTP | JAS | 2025-02-27 | 2025-02-27 | N-OUT | C-HN-UTP:02/27 > JAS:02/27
56 | CHOPPER | HN | IN | JAS | UTP | 2025-02-27 | 2025-02-27 | N-IN | C-HN-JAS:02/27 > UTP:02/27
57 | CHOPPER | HS | OUT | SKL | G10 | 2025-02-28 | 2025-02-28 | S-OUT | C-HS-SKL:02/28 > G10:02/28
58 | CHOPPER | HS | IN | G10 | SKL | 2025-02-28 | 2025-02-28 | S-IN | C-HS-G10:02/28 > SKL:02/28
59 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-01 | 2025-03-01 | N-OUT | C-HN-UTP:03/01 > JAS:03/01
60 | CHOPPER | HN | IN | JAS | UTP | 2025-03-01 | 2025-03-01 | N-IN | C-HN-JAS:03/01 > UTP:03/01
61 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-01 | 2025-03-01 | N-OUT | C-HN-UTP:03/01 > G1:03/01
62 | CHOPPER | HN | IN | G1 | UTP | 2025-03-01 | 2025-03-01 | N-IN | C-HN-G1:03/01 > UTP:03/01
63 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-01 | 2025-03-01 | S-OUT | C-HS-SKL:03/01 > G11:03/01
64 | CHOPPER | HS | IN | G11 | SKL | 2025-03-01 | 2025-03-01 | S-IN | C-HS-G11:03/01 > SKL:03/01
65 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-05 | 2025-03-05 | S-OUT | C-HS-SKL:03/05 > G11:03/05
66 | CHOPPER | HS | IN | G11 | SKL | 2025-03-05 | 2025-03-05 | S-IN | C-HS-G11:03/05 > SKL:03/05
67 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-05 | 2025-03-05 | S-OUT | C-HS-SKL:03/05 > G10:03/05
68 | CHOPPER | HS | IN | G10 | SKL | 2025-03-05 | 2025-03-05 | S-IN | C-HS-G10:03/05 > SKL:03/05
69 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-06 | 2025-03-06 | N-OUT | C-HN-UTP:03/06 > JAS:03/06
70 | CHOPPER | HN | IN | JAS | UTP | 2025-03-06 | 2025-03-06 | N-IN | C-HN-JAS:03/06 > UTP:03/06
71 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-07 | 2025-03-07 | S-OUT | C-HS-SKL:03/07 > G10:03/07
72 | CHOPPER | HS | IN | G10 | SKL | 2025-03-07 | 2025-03-07 | S-IN | C-HS-G10:03/07 > SKL:03/07
73 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-08 | 2025-03-08 | N-OUT | C-HN-UTP:03/08 > JAS:03/08
74 | CHOPPER | HN | IN | JAS | UTP | 2025-03-08 | 2025-03-08 | N-IN | C-HN-JAS:03/08 > UTP:03/08
75 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-08 | 2025-03-08 | N-OUT | C-HN-UTP:03/08 > G1:03/08
76 | CHOPPER | HN | IN | G1 | UTP | 2025-03-08 | 2025-03-08 | N-IN | C-HN-G1:03/08 > UTP:03/08
77 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-08 | 2025-03-08 | S-OUT | C-HS-SKL:03/08 > G11:03/08
78 | CHOPPER | HS | IN | G11 | SKL | 2025-03-08 | 2025-03-08 | S-IN | C-HS-G11:03/08 > SKL:03/08
79 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-10 | 2025-03-10 | N-OUT | C-HN-UTP:03/10 > JAS:03/10
80 | CHOPPER | HN | IN | JAS | UTP | 2025-03-10 | 2025-03-10 | N-IN | C-HN-JAS:03/10 > UTP:03/10
81 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-12 | 2025-03-12 | S-OUT | C-HS-SKL:03/12 > G11:03/12
82 | CHOPPER | HS | IN | G11 | SKL | 2025-03-12 | 2025-03-12 | S-IN | C-HS-G11:03/12 > SKL:03/12
83 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-12 | 2025-03-12 | S-OUT | C-HS-SKL:03/12 > G10:03/12
84 | CHOPPER | HS | IN | G10 | SKL | 2025-03-12 | 2025-03-12 | S-IN | C-HS-G10:03/12 > SKL:03/12
85 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-13 | 2025-03-13 | N-OUT | C-HN-UTP:03/13 > JAS:03/13
86 | CHOPPER | HN | IN | JAS | UTP | 2025-03-13 | 2025-03-13 | N-IN | C-HN-JAS:03/13 > UTP:03/13
87 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-14 | 2025-03-14 | S-OUT | C-HS-SKL:03/14 > G10:03/14
88 | CHOPPER | HS | IN | G10 | SKL | 2025-03-14 | 2025-03-14 | S-IN | C-HS-G10:03/14 > SKL:03/14
89 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-15 | 2025-03-15 | N-OUT | C-HN-UTP:03/15 > JAS:03/15
90 | CHOPPER | HN | IN | JAS | UTP | 2025-03-15 | 2025-03-15 | N-IN | C-HN-JAS:03/15 > UTP:03/15
91 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-15 | 2025-03-15 | N-OUT | C-HN-UTP:03/15 > G1:03/15
92 | CHOPPER | HN | IN | G1 | UTP | 2025-03-15 | 2025-03-15 | N-IN | C-HN-G1:03/15 > UTP:03/15
93 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-17 | 2025-03-17 | N-OUT | C-HN-UTP:03/17 > JAS:03/17
94 | CHOPPER | HN | IN | JAS | UTP | 2025-03-17 | 2025-03-17 | N-IN | C-HN-JAS:03/17 > UTP:03/17
95 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-17 | 2025-03-17 | N-OUT | C-HN-UTP:03/17 > G1:03/17
96 | CHOPPER | HN | IN | G1 | UTP | 2025-03-17 | 2025-03-17 | N-IN | C-HN-G1:03/17 > UTP:03/17
97 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-19 | 2025-03-19 | S-OUT | C-HS-SKL:03/19 > G11:03/19
98 | CHOPPER | HS | IN | G11 | SKL | 2025-03-19 | 2025-03-19 | S-IN | C-HS-G11:03/19 > SKL:03/19
99 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-19 | 2025-03-19 | S-OUT | C-HS-SKL:03/19 > G10:03/19
100 | CHOPPER | HS | IN | G10 | SKL | 2025-03-19 | 2025-03-19 | S-IN | C-HS-G10:03/19 > SKL:03/19
101 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-22 | 2025-03-22 | N-OUT | C-HN-UTP:03/22 > JAS:03/22
102 | CHOPPER | HN | IN | JAS | UTP | 2025-03-22 | 2025-03-22 | N-IN | C-HN-JAS:03/22 > UTP:03/22
103 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-22 | 2025-03-22 | N-OUT | C-HN-UTP:03/22 > G1:03/22
104 | CHOPPER | HN | IN | G1 | UTP | 2025-03-22 | 2025-03-22 | N-IN | C-HN-G1:03/22 > UTP:03/22
105 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-22 | 2025-03-22 | S-OUT | C-HS-SKL:03/22 > G11:03/22
106 | CHOPPER | HS | IN | G11 | SKL | 2025-03-22 | 2025-03-22 | S-IN | C-HS-G11:03/22 > SKL:03/22
107 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-24 | 2025-03-24 | N-OUT | C-HN-UTP:03/24 > JAS:03/24
108 | CHOPPER | HN | IN | JAS | UTP | 2025-03-24 | 2025-03-24 | N-IN | C-HN-JAS:03/24 > UTP:03/24
109 | CHOPPER | HS | OUT | SKL | G11 | 2025-03-26 | 2025-03-26 | S-OUT | C-HS-SKL:03/26 > G11:03/26
110 | CHOPPER | HS | IN | G11 | SKL | 2025-03-26 | 2025-03-26 | S-IN | C-HS-G11:03/26 > SKL:03/26
111 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-26 | 2025-03-26 | S-OUT | C-HS-SKL:03/26 > G10:03/26
112 | CHOPPER | HS | IN | G10 | SKL | 2025-03-26 | 2025-03-26 | S-IN | C-HS-G10:03/26 > SKL:03/26
113 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-27 | 2025-03-27 | N-OUT | C-HN-UTP:03/27 > JAS:03/27
114 | CHOPPER | HN | IN | JAS | UTP | 2025-03-27 | 2025-03-27 | N-IN | C-HN-JAS:03/27 > UTP:03/27
115 | CHOPPER | HS | OUT | SKL | G10 | 2025-03-28 | 2025-03-28 | S-OUT | C-HS-SKL:03/28 > G10:03/28
116 | CHOPPER | HS | IN | G10 | SKL | 2025-03-28 | 2025-03-28 | S-IN | C-HS-G10:03/28 > SKL:03/28
117 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-29 | 2025-03-29 | N-OUT | C-HN-UTP:03/29 > JAS:03/29
118 | CHOPPER | HN | IN | JAS | UTP | 2025-03-29 | 2025-03-29 | N-IN | C-HN-JAS:03/29 > UTP:03/29
119 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-29 | 2025-03-29 | N-OUT | C-HN-UTP:03/29 > G1:03/29
120 | CHOPPER | HN | IN | G1 | UTP | 2025-03-29 | 2025-03-29 | N-IN | C-HN-G1:03/29 > UTP:03/29
121 | CHOPPER | HN | OUT | UTP | JAS | 2025-03-31 | 2025-03-31 | N-OUT | C-HN-UTP:03/31 > JAS:03/31
122 | CHOPPER | HN | IN | JAS | UTP | 2025-03-31 | 2025-03-31 | N-IN | C-HN-JAS:03/31 > UTP:03/31
123 | CHOPPER | HN | OUT | UTP | G1 | 2025-03-31 | 2025-03-31 | N-OUT | C-HN-UTP:03/31 > G1:03/31
124 | CHOPPER | HN | IN | G1 | UTP | 2025-03-31 | 2025-03-31 | N-IN | C-HN-G1:03/31 > UTP:03/31
125 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-01 | 2025-04-01 | S-OUT | C-HS-SKL:04/01 > G11:04/01
126 | CHOPPER | HS | IN | G11 | SKL | 2025-04-01 | 2025-04-01 | S-IN | C-HS-G11:04/01 > SKL:04/01
127 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-02 | 2025-04-02 | S-OUT | C-HS-SKL:04/02 > G11:04/02
128 | CHOPPER | HS | IN | G11 | SKL | 2025-04-02 | 2025-04-02 | S-IN | C-HS-G11:04/02 > SKL:04/02
129 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-02 | 2025-04-02 | S-OUT | C-HS-SKL:04/02 > G10:04/02
130 | CHOPPER | HS | IN | G10 | SKL | 2025-04-02 | 2025-04-02 | S-IN | C-HS-G10:04/02 > SKL:04/02
131 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-04 | 2025-04-04 | S-OUT | C-HS-SKL:04/04 > G10:04/04
132 | CHOPPER | HS | IN | G10 | SKL | 2025-04-04 | 2025-04-04 | S-IN | C-HS-G10:04/04 > SKL:04/04
133 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-05 | 2025-04-05 | N-OUT | C-HN-UTP:04/05 > JAS:04/05
134 | CHOPPER | HN | IN | JAS | UTP | 2025-04-05 | 2025-04-05 | N-IN | C-HN-JAS:04/05 > UTP:04/05
135 | CHOPPER | HN | OUT | UTP | G1 | 2025-04-05 | 2025-04-05 | N-OUT | C-HN-UTP:04/05 > G1:04/05
136 | CHOPPER | HN | IN | G1 | UTP | 2025-04-05 | 2025-04-05 | N-IN | C-HN-G1:04/05 > UTP:04/05
137 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-05 | 2025-04-05 | S-OUT | C-HS-SKL:04/05 > G11:04/05
138 | CHOPPER | HS | IN | G11 | SKL | 2025-04-05 | 2025-04-05 | S-IN | C-HS-G11:04/05 > SKL:04/05
139 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-07 | 2025-04-07 | N-OUT | C-HN-UTP:04/07 > JAS:04/07
140 | CHOPPER | HN | IN | JAS | UTP | 2025-04-07 | 2025-04-07 | N-IN | C-HN-JAS:04/07 > UTP:04/07
141 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-09 | 2025-04-09 | S-OUT | C-HS-SKL:04/09 > G11:04/09
142 | CHOPPER | HS | IN | G11 | SKL | 2025-04-09 | 2025-04-09 | S-IN | C-HS-G11:04/09 > SKL:04/09
143 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-09 | 2025-04-09 | S-OUT | C-HS-SKL:04/09 > G10:04/09
144 | CHOPPER | HS | IN | G10 | SKL | 2025-04-09 | 2025-04-09 | S-IN | C-HS-G10:04/09 > SKL:04/09
145 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-10 | 2025-04-10 | N-OUT | C-HN-UTP:04/10 > JAS:04/10
146 | CHOPPER | HN | IN | JAS | UTP | 2025-04-10 | 2025-04-10 | N-IN | C-HN-JAS:04/10 > UTP:04/10
147 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-11 | 2025-04-11 | S-OUT | C-HS-SKL:04/11 > G10:04/11
148 | CHOPPER | HS | IN | G10 | SKL | 2025-04-11 | 2025-04-11 | S-IN | C-HS-G10:04/11 > SKL:04/11
149 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-12 | 2025-04-12 | N-OUT | C-HN-UTP:04/12 > JAS:04/12
150 | CHOPPER | HN | IN | JAS | UTP | 2025-04-12 | 2025-04-12 | N-IN | C-HN-JAS:04/12 > UTP:04/12
151 | CHOPPER | HN | OUT | UTP | G1 | 2025-04-12 | 2025-04-12 | N-OUT | C-HN-UTP:04/12 > G1:04/12
152 | CHOPPER | HN | IN | G1 | UTP | 2025-04-12 | 2025-04-12 | N-IN | C-HN-G1:04/12 > UTP:04/12
153 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-12 | 2025-04-12 | S-OUT | C-HS-SKL:04/12 > G11:04/12
154 | CHOPPER | HS | IN | G11 | SKL | 2025-04-12 | 2025-04-12 | S-IN | C-HS-G11:04/12 > SKL:04/12
155 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-14 | 2025-04-14 | N-OUT | C-HN-UTP:04/14 > JAS:04/14
156 | CHOPPER | HN | IN | JAS | UTP | 2025-04-14 | 2025-04-14 | N-IN | C-HN-JAS:04/14 > UTP:04/14
157 | CHOPPER | HN | OUT | UTP | G1 | 2025-04-14 | 2025-04-14 | N-OUT | C-HN-UTP:04/14 > G1:04/14
158 | CHOPPER | HN | IN | G1 | UTP | 2025-04-14 | 2025-04-14 | N-IN | C-HN-G1:04/14 > UTP:04/14
159 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-16 | 2025-04-16 | S-OUT | C-HS-SKL:04/16 > G11:04/16
160 | CHOPPER | HS | IN | G11 | SKL | 2025-04-16 | 2025-04-16 | S-IN | C-HS-G11:04/16 > SKL:04/16
161 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-16 | 2025-04-16 | S-OUT | C-HS-SKL:04/16 > G10:04/16
162 | CHOPPER | HS | IN | G10 | SKL | 2025-04-16 | 2025-04-16 | S-IN | C-HS-G10:04/16 > SKL:04/16
163 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-17 | 2025-04-17 | N-OUT | C-HN-UTP:04/17 > JAS:04/17
164 | CHOPPER | HN | IN | JAS | UTP | 2025-04-17 | 2025-04-17 | N-IN | C-HN-JAS:04/17 > UTP:04/17
165 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-19 | 2025-04-19 | N-OUT | C-HN-UTP:04/19 > JAS:04/19
166 | CHOPPER | HN | IN | JAS | UTP | 2025-04-19 | 2025-04-19 | N-IN | C-HN-JAS:04/19 > UTP:04/19
167 | CHOPPER | HN | OUT | UTP | G1 | 2025-04-19 | 2025-04-19 | N-OUT | C-HN-UTP:04/19 > G1:04/19
168 | CHOPPER | HN | IN | G1 | UTP | 2025-04-19 | 2025-04-19 | N-IN | C-HN-G1:04/19 > UTP:04/19
169 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-19 | 2025-04-19 | S-OUT | C-HS-SKL:04/19 > G11:04/19
170 | CHOPPER | HS | IN | G11 | SKL | 2025-04-19 | 2025-04-19 | S-IN | C-HS-G11:04/19 > SKL:04/19
171 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-21 | 2025-04-21 | N-OUT | C-HN-UTP:04/21 > JAS:04/21
172 | CHOPPER | HN | IN | JAS | UTP | 2025-04-21 | 2025-04-21 | N-IN | C-HN-JAS:04/21 > UTP:04/21
173 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-23 | 2025-04-23 | S-OUT | C-HS-SKL:04/23 > G11:04/23
174 | CHOPPER | HS | IN | G11 | SKL | 2025-04-23 | 2025-04-23 | S-IN | C-HS-G11:04/23 > SKL:04/23
175 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-23 | 2025-04-23 | S-OUT | C-HS-SKL:04/23 > G10:04/23
176 | CHOPPER | HS | IN | G10 | SKL | 2025-04-23 | 2025-04-23 | S-IN | C-HS-G10:04/23 > SKL:04/23
177 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-24 | 2025-04-24 | N-OUT | C-HN-UTP:04/24 > JAS:04/24
178 | CHOPPER | HN | IN | JAS | UTP | 2025-04-24 | 2025-04-24 | N-IN | C-HN-JAS:04/24 > UTP:04/24
179 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-25 | 2025-04-25 | S-OUT | C-HS-SKL:04/25 > G10:04/25
180 | CHOPPER | HS | IN | G10 | SKL | 2025-04-25 | 2025-04-25 | S-IN | C-HS-G10:04/25 > SKL:04/25
181 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-26 | 2025-04-26 | N-OUT | C-HN-UTP:04/26 > JAS:04/26
182 | CHOPPER | HN | IN | JAS | UTP | 2025-04-26 | 2025-04-26 | N-IN | C-HN-JAS:04/26 > UTP:04/26
183 | CHOPPER | HN | OUT | UTP | G1 | 2025-04-26 | 2025-04-26 | N-OUT | C-HN-UTP:04/26 > G1:04/26
184 | CHOPPER | HN | IN | G1 | UTP | 2025-04-26 | 2025-04-26 | N-IN | C-HN-G1:04/26 > UTP:04/26
185 | CHOPPER | HN | OUT | UTP | JAS | 2025-04-28 | 2025-04-28 | N-OUT | C-HN-UTP:04/28 > JAS:04/28
186 | CHOPPER | HN | IN | JAS | UTP | 2025-04-28 | 2025-04-28 | N-IN | C-HN-JAS:04/28 > UTP:04/28
187 | CHOPPER | HN | OUT | UTP | G1 | 2025-04-28 | 2025-04-28 | N-OUT | C-HN-UTP:04/28 > G1:04/28
188 | CHOPPER | HN | IN | G1 | UTP | 2025-04-28 | 2025-04-28 | N-IN | C-HN-G1:04/28 > UTP:04/28
189 | CHOPPER | HS | OUT | SKL | G11 | 2025-04-30 | 2025-04-30 | S-OUT | C-HS-SKL:04/30 > G11:04/30
190 | CHOPPER | HS | IN | G11 | SKL | 2025-04-30 | 2025-04-30 | S-IN | C-HS-G11:04/30 > SKL:04/30
191 | CHOPPER | HS | OUT | SKL | G10 | 2025-04-30 | 2025-04-30 | S-OUT | C-HS-SKL:04/30 > G10:04/30
192 | CHOPPER | HS | IN | G10 | SKL | 2025-04-30 | 2025-04-30 | S-IN | C-HS-G10:04/30 > SKL:04/30
193 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-02 | 2025-05-02 | S-OUT | C-HS-SKL:05/02 > G10:05/02
194 | CHOPPER | HS | IN | G10 | SKL | 2025-05-02 | 2025-05-02 | S-IN | C-HS-G10:05/02 > SKL:05/02
195 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-03 | 2025-05-03 | N-OUT | C-HN-UTP:05/03 > JAS:05/03
196 | CHOPPER | HN | IN | JAS | UTP | 2025-05-03 | 2025-05-03 | N-IN | C-HN-JAS:05/03 > UTP:05/03
197 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-03 | 2025-05-03 | N-OUT | C-HN-UTP:05/03 > G1:05/03
198 | CHOPPER | HN | IN | G1 | UTP | 2025-05-03 | 2025-05-03 | N-IN | C-HN-G1:05/03 > UTP:05/03
199 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-03 | 2025-05-03 | S-OUT | C-HS-SKL:05/03 > G11:05/03
200 | CHOPPER | HS | IN | G11 | SKL | 2025-05-03 | 2025-05-03 | S-IN | C-HS-G11:05/03 > SKL:05/03
201 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-05 | 2025-05-05 | N-OUT | C-HN-UTP:05/05 > JAS:05/05
202 | CHOPPER | HN | IN | JAS | UTP | 2025-05-05 | 2025-05-05 | N-IN | C-HN-JAS:05/05 > UTP:05/05
203 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-07 | 2025-05-07 | S-OUT | C-HS-SKL:05/07 > G11:05/07
204 | CHOPPER | HS | IN | G11 | SKL | 2025-05-07 | 2025-05-07 | S-IN | C-HS-G11:05/07 > SKL:05/07
205 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-07 | 2025-05-07 | S-OUT | C-HS-SKL:05/07 > G10:05/07
206 | CHOPPER | HS | IN | G10 | SKL | 2025-05-07 | 2025-05-07 | S-IN | C-HS-G10:05/07 > SKL:05/07
207 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-08 | 2025-05-08 | N-OUT | C-HN-UTP:05/08 > JAS:05/08
208 | CHOPPER | HN | IN | JAS | UTP | 2025-05-08 | 2025-05-08 | N-IN | C-HN-JAS:05/08 > UTP:05/08
209 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-09 | 2025-05-09 | S-OUT | C-HS-SKL:05/09 > G10:05/09
210 | CHOPPER | HS | IN | G10 | SKL | 2025-05-09 | 2025-05-09 | S-IN | C-HS-G10:05/09 > SKL:05/09
211 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-10 | 2025-05-10 | N-OUT | C-HN-UTP:05/10 > JAS:05/10
212 | CHOPPER | HN | IN | JAS | UTP | 2025-05-10 | 2025-05-10 | N-IN | C-HN-JAS:05/10 > UTP:05/10
213 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-10 | 2025-05-10 | N-OUT | C-HN-UTP:05/10 > G1:05/10
214 | CHOPPER | HN | IN | G1 | UTP | 2025-05-10 | 2025-05-10 | N-IN | C-HN-G1:05/10 > UTP:05/10
215 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-12 | 2025-05-12 | N-OUT | C-HN-UTP:05/12 > JAS:05/12
216 | CHOPPER | HN | IN | JAS | UTP | 2025-05-12 | 2025-05-12 | N-IN | C-HN-JAS:05/12 > UTP:05/12
217 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-12 | 2025-05-12 | N-OUT | C-HN-UTP:05/12 > G1:05/12
218 | CHOPPER | HN | IN | G1 | UTP | 2025-05-12 | 2025-05-12 | N-IN | C-HN-G1:05/12 > UTP:05/12
219 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-14 | 2025-05-14 | S-OUT | C-HS-SKL:05/14 > G11:05/14
220 | CHOPPER | HS | IN | G11 | SKL | 2025-05-14 | 2025-05-14 | S-IN | C-HS-G11:05/14 > SKL:05/14
221 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-14 | 2025-05-14 | S-OUT | C-HS-SKL:05/14 > G10:05/14
222 | CHOPPER | HS | IN | G10 | SKL | 2025-05-14 | 2025-05-14 | S-IN | C-HS-G10:05/14 > SKL:05/14
223 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-17 | 2025-05-17 | N-OUT | C-HN-UTP:05/17 > JAS:05/17
224 | CHOPPER | HN | IN | JAS | UTP | 2025-05-17 | 2025-05-17 | N-IN | C-HN-JAS:05/17 > UTP:05/17
225 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-17 | 2025-05-17 | N-OUT | C-HN-UTP:05/17 > G1:05/17
226 | CHOPPER | HN | IN | G1 | UTP | 2025-05-17 | 2025-05-17 | N-IN | C-HN-G1:05/17 > UTP:05/17
227 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-17 | 2025-05-17 | S-OUT | C-HS-SKL:05/17 > G11:05/17
228 | CHOPPER | HS | IN | G11 | SKL | 2025-05-17 | 2025-05-17 | S-IN | C-HS-G11:05/17 > SKL:05/17
229 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-19 | 2025-05-19 | N-OUT | C-HN-UTP:05/19 > JAS:05/19
230 | CHOPPER | HN | IN | JAS | UTP | 2025-05-19 | 2025-05-19 | N-IN | C-HN-JAS:05/19 > UTP:05/19
231 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-21 | 2025-05-21 | S-OUT | C-HS-SKL:05/21 > G11:05/21
232 | CHOPPER | HS | IN | G11 | SKL | 2025-05-21 | 2025-05-21 | S-IN | C-HS-G11:05/21 > SKL:05/21
233 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-21 | 2025-05-21 | S-OUT | C-HS-SKL:05/21 > G10:05/21
234 | CHOPPER | HS | IN | G10 | SKL | 2025-05-21 | 2025-05-21 | S-IN | C-HS-G10:05/21 > SKL:05/21
235 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-22 | 2025-05-22 | N-OUT | C-HN-UTP:05/22 > JAS:05/22
236 | CHOPPER | HN | IN | JAS | UTP | 2025-05-22 | 2025-05-22 | N-IN | C-HN-JAS:05/22 > UTP:05/22
237 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-23 | 2025-05-23 | S-OUT | C-HS-SKL:05/23 > G10:05/23
238 | CHOPPER | HS | IN | G10 | SKL | 2025-05-23 | 2025-05-23 | S-IN | C-HS-G10:05/23 > SKL:05/23
239 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-24 | 2025-05-24 | N-OUT | C-HN-UTP:05/24 > JAS:05/24
240 | CHOPPER | HN | IN | JAS | UTP | 2025-05-24 | 2025-05-24 | N-IN | C-HN-JAS:05/24 > UTP:05/24
241 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-24 | 2025-05-24 | N-OUT | C-HN-UTP:05/24 > G1:05/24
242 | CHOPPER | HN | IN | G1 | UTP | 2025-05-24 | 2025-05-24 | N-IN | C-HN-G1:05/24 > UTP:05/24
243 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-24 | 2025-05-24 | S-OUT | C-HS-SKL:05/24 > G11:05/24
244 | CHOPPER | HS | IN | G11 | SKL | 2025-05-24 | 2025-05-24 | S-IN | C-HS-G11:05/24 > SKL:05/24
245 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-26 | 2025-05-26 | N-OUT | C-HN-UTP:05/26 > JAS:05/26
246 | CHOPPER | HN | IN | JAS | UTP | 2025-05-26 | 2025-05-26 | N-IN | C-HN-JAS:05/26 > UTP:05/26
247 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-26 | 2025-05-26 | N-OUT | C-HN-UTP:05/26 > G1:05/26
248 | CHOPPER | HN | IN | G1 | UTP | 2025-05-26 | 2025-05-26 | N-IN | C-HN-G1:05/26 > UTP:05/26
249 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-28 | 2025-05-28 | S-OUT | C-HS-SKL:05/28 > G11:05/28
250 | CHOPPER | HS | IN | G11 | SKL | 2025-05-28 | 2025-05-28 | S-IN | C-HS-G11:05/28 > SKL:05/28
251 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-28 | 2025-05-28 | S-OUT | C-HS-SKL:05/28 > G10:05/28
252 | CHOPPER | HS | IN | G10 | SKL | 2025-05-28 | 2025-05-28 | S-IN | C-HS-G10:05/28 > SKL:05/28
253 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-29 | 2025-05-29 | N-OUT | C-HN-UTP:05/29 > JAS:05/29
254 | CHOPPER | HN | IN | JAS | UTP | 2025-05-29 | 2025-05-29 | N-IN | C-HN-JAS:05/29 > UTP:05/29
255 | CHOPPER | HS | OUT | SKL | G10 | 2025-05-30 | 2025-05-30 | S-OUT | C-HS-SKL:05/30 > G10:05/30
256 | CHOPPER | HS | IN | G10 | SKL | 2025-05-30 | 2025-05-30 | S-IN | C-HS-G10:05/30 > SKL:05/30
257 | CHOPPER | HN | OUT | UTP | JAS | 2025-05-31 | 2025-05-31 | N-OUT | C-HN-UTP:05/31 > JAS:05/31
258 | CHOPPER | HN | IN | JAS | UTP | 2025-05-31 | 2025-05-31 | N-IN | C-HN-JAS:05/31 > UTP:05/31
259 | CHOPPER | HN | OUT | UTP | G1 | 2025-05-31 | 2025-05-31 | N-OUT | C-HN-UTP:05/31 > G1:05/31
260 | CHOPPER | HN | IN | G1 | UTP | 2025-05-31 | 2025-05-31 | N-IN | C-HN-G1:05/31 > UTP:05/31
261 | CHOPPER | HS | OUT | SKL | G11 | 2025-05-31 | 2025-05-31 | S-OUT | C-HS-SKL:05/31 > G11:05/31
262 | CHOPPER | HS | IN | G11 | SKL | 2025-05-31 | 2025-05-31 | S-IN | C-HS-G11:05/31 > SKL:05/31
263 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-02 | 2025-06-02 | N-OUT | C-HN-UTP:06/02 > JAS:06/02
264 | CHOPPER | HN | IN | JAS | UTP | 2025-06-02 | 2025-06-02 | N-IN | C-HN-JAS:06/02 > UTP:06/02
265 | CHOPPER | HS | OUT | SKL | G11 | 2025-06-04 | 2025-06-04 | S-OUT | C-HS-SKL:06/04 > G11:06/04
266 | CHOPPER | HS | IN | G11 | SKL | 2025-06-04 | 2025-06-04 | S-IN | C-HS-G11:06/04 > SKL:06/04
267 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-04 | 2025-06-04 | S-OUT | C-HS-SKL:06/04 > G10:06/04
268 | CHOPPER | HS | IN | G10 | SKL | 2025-06-04 | 2025-06-04 | S-IN | C-HS-G10:06/04 > SKL:06/04
269 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-05 | 2025-06-05 | N-OUT | C-HN-UTP:06/05 > JAS:06/05
270 | CHOPPER | HN | IN | JAS | UTP | 2025-06-05 | 2025-06-05 | N-IN | C-HN-JAS:06/05 > UTP:06/05
271 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-06 | 2025-06-06 | N-OUT | C-HN-UTP:06/06 > JAS:06/06
272 | CHOPPER | HN | IN | JAS | UTP | 2025-06-06 | 2025-06-06 | N-IN | C-HN-JAS:06/06 > UTP:06/06
273 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-06 | 2025-06-06 | S-OUT | C-HS-SKL:06/06 > G10:06/06
274 | CHOPPER | HS | IN | G10 | SKL | 2025-06-06 | 2025-06-06 | S-IN | C-HS-G10:06/06 > SKL:06/06
275 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-07 | 2025-06-07 | N-OUT | C-HN-UTP:06/07 > JAS:06/07
276 | CHOPPER | HN | IN | JAS | UTP | 2025-06-07 | 2025-06-07 | N-IN | C-HN-JAS:06/07 > UTP:06/07
277 | CHOPPER | HN | OUT | UTP | G1 | 2025-06-07 | 2025-06-07 | N-OUT | C-HN-UTP:06/07 > G1:06/07
278 | CHOPPER | HN | IN | G1 | UTP | 2025-06-07 | 2025-06-07 | N-IN | C-HN-G1:06/07 > UTP:06/07
279 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-09 | 2025-06-09 | N-OUT | C-HN-UTP:06/09 > JAS:06/09
280 | CHOPPER | HN | IN | JAS | UTP | 2025-06-09 | 2025-06-09 | N-IN | C-HN-JAS:06/09 > UTP:06/09
281 | CHOPPER | HN | OUT | UTP | G1 | 2025-06-09 | 2025-06-09 | N-OUT | C-HN-UTP:06/09 > G1:06/09
282 | CHOPPER | HN | IN | G1 | UTP | 2025-06-09 | 2025-06-09 | N-IN | C-HN-G1:06/09 > UTP:06/09
283 | CHOPPER | HS | OUT | SKL | G11 | 2025-06-11 | 2025-06-11 | S-OUT | C-HS-SKL:06/11 > G11:06/11
284 | CHOPPER | HS | IN | G11 | SKL | 2025-06-11 | 2025-06-11 | S-IN | C-HS-G11:06/11 > SKL:06/11
285 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-11 | 2025-06-11 | S-OUT | C-HS-SKL:06/11 > G10:06/11
286 | CHOPPER | HS | IN | G10 | SKL | 2025-06-11 | 2025-06-11 | S-IN | C-HS-G10:06/11 > SKL:06/11
287 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-14 | 2025-06-14 | N-OUT | C-HN-UTP:06/14 > JAS:06/14
288 | CHOPPER | HN | IN | JAS | UTP | 2025-06-14 | 2025-06-14 | N-IN | C-HN-JAS:06/14 > UTP:06/14
289 | CHOPPER | HN | OUT | UTP | G1 | 2025-06-14 | 2025-06-14 | N-OUT | C-HN-UTP:06/14 > G1:06/14
290 | CHOPPER | HN | IN | G1 | UTP | 2025-06-14 | 2025-06-14 | N-IN | C-HN-G1:06/14 > UTP:06/14
291 | CHOPPER | HS | OUT | SKL | G11 | 2025-06-14 | 2025-06-14 | S-OUT | C-HS-SKL:06/14 > G11:06/14
292 | CHOPPER | HS | IN | G11 | SKL | 2025-06-14 | 2025-06-14 | S-IN | C-HS-G11:06/14 > SKL:06/14
293 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-16 | 2025-06-16 | N-OUT | C-HN-UTP:06/16 > JAS:06/16
294 | CHOPPER | HN | IN | JAS | UTP | 2025-06-16 | 2025-06-16 | N-IN | C-HN-JAS:06/16 > UTP:06/16
295 | CHOPPER | HS | OUT | SKL | G11 | 2025-06-18 | 2025-06-18 | S-OUT | C-HS-SKL:06/18 > G11:06/18
296 | CHOPPER | HS | IN | G11 | SKL | 2025-06-18 | 2025-06-18 | S-IN | C-HS-G11:06/18 > SKL:06/18
297 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-18 | 2025-06-18 | S-OUT | C-HS-SKL:06/18 > G10:06/18
298 | CHOPPER | HS | IN | G10 | SKL | 2025-06-18 | 2025-06-18 | S-IN | C-HS-G10:06/18 > SKL:06/18
299 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-19 | 2025-06-19 | N-OUT | C-HN-UTP:06/19 > JAS:06/19
300 | CHOPPER | HN | IN | JAS | UTP | 2025-06-19 | 2025-06-19 | N-IN | C-HN-JAS:06/19 > UTP:06/19
301 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-20 | 2025-06-20 | S-OUT | C-HS-SKL:06/20 > G10:06/20
302 | CHOPPER | HS | IN | G10 | SKL | 2025-06-20 | 2025-06-20 | S-IN | C-HS-G10:06/20 > SKL:06/20
303 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-21 | 2025-06-21 | N-OUT | C-HN-UTP:06/21 > JAS:06/21
304 | CHOPPER | HN | IN | JAS | UTP | 2025-06-21 | 2025-06-21 | N-IN | C-HN-JAS:06/21 > UTP:06/21
305 | CHOPPER | HN | OUT | UTP | G1 | 2025-06-21 | 2025-06-21 | N-OUT | C-HN-UTP:06/21 > G1:06/21
306 | CHOPPER | HN | IN | G1 | UTP | 2025-06-21 | 2025-06-21 | N-IN | C-HN-G1:06/21 > UTP:06/21
307 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-23 | 2025-06-23 | N-OUT | C-HN-UTP:06/23 > JAS:06/23
308 | CHOPPER | HN | IN | JAS | UTP | 2025-06-23 | 2025-06-23 | N-IN | C-HN-JAS:06/23 > UTP:06/23
309 | CHOPPER | HN | OUT | UTP | G1 | 2025-06-23 | 2025-06-23 | N-OUT | C-HN-UTP:06/23 > G1:06/23
310 | CHOPPER | HN | IN | G1 | UTP | 2025-06-23 | 2025-06-23 | N-IN | C-HN-G1:06/23 > UTP:06/23
311 | CHOPPER | HS | OUT | SKL | G11 | 2025-06-25 | 2025-06-25 | S-OUT | C-HS-SKL:06/25 > G11:06/25
312 | CHOPPER | HS | IN | G11 | SKL | 2025-06-25 | 2025-06-25 | S-IN | C-HS-G11:06/25 > SKL:06/25
313 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-25 | 2025-06-25 | S-OUT | C-HS-SKL:06/25 > G10:06/25
314 | CHOPPER | HS | IN | G10 | SKL | 2025-06-25 | 2025-06-25 | S-IN | C-HS-G10:06/25 > SKL:06/25
315 | CHOPPER | HS | OUT | SKL | G10 | 2025-06-27 | 2025-06-27 | S-OUT | C-HS-SKL:06/27 > G10:06/27
316 | CHOPPER | HS | IN | G10 | SKL | 2025-06-27 | 2025-06-27 | S-IN | C-HS-G10:06/27 > SKL:06/27
317 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-28 | 2025-06-28 | N-OUT | C-HN-UTP:06/28 > JAS:06/28
318 | CHOPPER | HN | IN | JAS | UTP | 2025-06-28 | 2025-06-28 | N-IN | C-HN-JAS:06/28 > UTP:06/28
319 | CHOPPER | HN | OUT | UTP | G1 | 2025-06-28 | 2025-06-28 | N-OUT | C-HN-UTP:06/28 > G1:06/28
320 | CHOPPER | HN | IN | G1 | UTP | 2025-06-28 | 2025-06-28 | N-IN | C-HN-G1:06/28 > UTP:06/28
321 | CHOPPER | HS | OUT | SKL | G11 | 2025-06-28 | 2025-06-28 | S-OUT | C-HS-SKL:06/28 > G11:06/28
322 | CHOPPER | HS | IN | G11 | SKL | 2025-06-28 | 2025-06-28 | S-IN | C-HS-G11:06/28 > SKL:06/28
323 | CHOPPER | HN | OUT | UTP | JAS | 2025-06-30 | 2025-06-30 | N-OUT | C-HN-UTP:06/30 > JAS:06/30
324 | CHOPPER | HN | IN | JAS | UTP | 2025-06-30 | 2025-06-30 | N-IN | C-HN-JAS:06/30 > UTP:06/30
325 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-02 | 2025-07-02 | S-OUT | C-HS-SKL:07/02 > G11:07/02
326 | CHOPPER | HS | IN | G11 | SKL | 2025-07-02 | 2025-07-02 | S-IN | C-HS-G11:07/02 > SKL:07/02
327 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-02 | 2025-07-02 | S-OUT | C-HS-SKL:07/02 > G10:07/02
328 | CHOPPER | HS | IN | G10 | SKL | 2025-07-02 | 2025-07-02 | S-IN | C-HS-G10:07/02 > SKL:07/02
329 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-03 | 2025-07-03 | N-OUT | C-HN-UTP:07/03 > JAS:07/03
330 | CHOPPER | HN | IN | JAS | UTP | 2025-07-03 | 2025-07-03 | N-IN | C-HN-JAS:07/03 > UTP:07/03
331 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-04 | 2025-07-04 | S-OUT | C-HS-SKL:07/04 > G10:07/04
332 | CHOPPER | HS | IN | G10 | SKL | 2025-07-04 | 2025-07-04 | S-IN | C-HS-G10:07/04 > SKL:07/04
333 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-05 | 2025-07-05 | N-OUT | C-HN-UTP:07/05 > JAS:07/05
334 | CHOPPER | HN | IN | JAS | UTP | 2025-07-05 | 2025-07-05 | N-IN | C-HN-JAS:07/05 > UTP:07/05
335 | CHOPPER | HN | OUT | UTP | G1 | 2025-07-05 | 2025-07-05 | N-OUT | C-HN-UTP:07/05 > G1:07/05
336 | CHOPPER | HN | IN | G1 | UTP | 2025-07-05 | 2025-07-05 | N-IN | C-HN-G1:07/05 > UTP:07/05
337 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-05 | 2025-07-05 | S-OUT | C-HS-SKL:07/05 > G11:07/05
338 | CHOPPER | HS | IN | G11 | SKL | 2025-07-05 | 2025-07-05 | S-IN | C-HS-G11:07/05 > SKL:07/05
339 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-07 | 2025-07-07 | N-OUT | C-HN-UTP:07/07 > JAS:07/07
340 | CHOPPER | HN | IN | JAS | UTP | 2025-07-07 | 2025-07-07 | N-IN | C-HN-JAS:07/07 > UTP:07/07
341 | CHOPPER | HN | OUT | UTP | G1 | 2025-07-07 | 2025-07-07 | N-OUT | C-HN-UTP:07/07 > G1:07/07
342 | CHOPPER | HN | IN | G1 | UTP | 2025-07-07 | 2025-07-07 | N-IN | C-HN-G1:07/07 > UTP:07/07
343 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-09 | 2025-07-09 | S-OUT | C-HS-SKL:07/09 > G11:07/09
344 | CHOPPER | HS | IN | G11 | SKL | 2025-07-09 | 2025-07-09 | S-IN | C-HS-G11:07/09 > SKL:07/09
345 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-09 | 2025-07-09 | S-OUT | C-HS-SKL:07/09 > G10:07/09
346 | CHOPPER | HS | IN | G10 | SKL | 2025-07-09 | 2025-07-09 | S-IN | C-HS-G10:07/09 > SKL:07/09
347 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-10 | 2025-07-10 | N-OUT | C-HN-UTP:07/10 > JAS:07/10
348 | CHOPPER | HN | IN | JAS | UTP | 2025-07-10 | 2025-07-10 | N-IN | C-HN-JAS:07/10 > UTP:07/10
349 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-12 | 2025-07-12 | N-OUT | C-HN-UTP:07/12 > JAS:07/12
350 | CHOPPER | HN | IN | JAS | UTP | 2025-07-12 | 2025-07-12 | N-IN | C-HN-JAS:07/12 > UTP:07/12
351 | CHOPPER | HN | OUT | UTP | G1 | 2025-07-12 | 2025-07-12 | N-OUT | C-HN-UTP:07/12 > G1:07/12
352 | CHOPPER | HN | IN | G1 | UTP | 2025-07-12 | 2025-07-12 | N-IN | C-HN-G1:07/12 > UTP:07/12
353 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-14 | 2025-07-14 | N-OUT | C-HN-UTP:07/14 > JAS:07/14
354 | CHOPPER | HN | IN | JAS | UTP | 2025-07-14 | 2025-07-14 | N-IN | C-HN-JAS:07/14 > UTP:07/14
355 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-16 | 2025-07-16 | S-OUT | C-HS-SKL:07/16 > G11:07/16
356 | CHOPPER | HS | IN | G11 | SKL | 2025-07-16 | 2025-07-16 | S-IN | C-HS-G11:07/16 > SKL:07/16
357 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-16 | 2025-07-16 | S-OUT | C-HS-SKL:07/16 > G10:07/16
358 | CHOPPER | HS | IN | G10 | SKL | 2025-07-16 | 2025-07-16 | S-IN | C-HS-G10:07/16 > SKL:07/16
359 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-17 | 2025-07-17 | N-OUT | C-HN-UTP:07/17 > JAS:07/17
360 | CHOPPER | HN | IN | JAS | UTP | 2025-07-17 | 2025-07-17 | N-IN | C-HN-JAS:07/17 > UTP:07/17
361 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-18 | 2025-07-18 | S-OUT | C-HS-SKL:07/18 > G10:07/18
362 | CHOPPER | HS | IN | G10 | SKL | 2025-07-18 | 2025-07-18 | S-IN | C-HS-G10:07/18 > SKL:07/18
363 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-19 | 2025-07-19 | N-OUT | C-HN-UTP:07/19 > JAS:07/19
364 | CHOPPER | HN | IN | JAS | UTP | 2025-07-19 | 2025-07-19 | N-IN | C-HN-JAS:07/19 > UTP:07/19
365 | CHOPPER | HN | OUT | UTP | G1 | 2025-07-19 | 2025-07-19 | N-OUT | C-HN-UTP:07/19 > G1:07/19
366 | CHOPPER | HN | IN | G1 | UTP | 2025-07-19 | 2025-07-19 | N-IN | C-HN-G1:07/19 > UTP:07/19
367 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-21 | 2025-07-21 | N-OUT | C-HN-UTP:07/21 > JAS:07/21
368 | CHOPPER | HN | IN | JAS | UTP | 2025-07-21 | 2025-07-21 | N-IN | C-HN-JAS:07/21 > UTP:07/21
369 | CHOPPER | HN | OUT | UTP | G1 | 2025-07-21 | 2025-07-21 | N-OUT | C-HN-UTP:07/21 > G1:07/21
370 | CHOPPER | HN | IN | G1 | UTP | 2025-07-21 | 2025-07-21 | N-IN | C-HN-G1:07/21 > UTP:07/21
371 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-23 | 2025-07-23 | S-OUT | C-HS-SKL:07/23 > G11:07/23
372 | CHOPPER | HS | IN | G11 | SKL | 2025-07-23 | 2025-07-23 | S-IN | C-HS-G11:07/23 > SKL:07/23
373 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-23 | 2025-07-23 | S-OUT | C-HS-SKL:07/23 > G10:07/23
374 | CHOPPER | HS | IN | G10 | SKL | 2025-07-23 | 2025-07-23 | S-IN | C-HS-G10:07/23 > SKL:07/23
375 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-25 | 2025-07-25 | S-OUT | C-HS-SKL:07/25 > G10:07/25
376 | CHOPPER | HS | IN | G10 | SKL | 2025-07-25 | 2025-07-25 | S-IN | C-HS-G10:07/25 > SKL:07/25
377 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-26 | 2025-07-26 | N-OUT | C-HN-UTP:07/26 > JAS:07/26
378 | CHOPPER | HN | IN | JAS | UTP | 2025-07-26 | 2025-07-26 | N-IN | C-HN-JAS:07/26 > UTP:07/26
379 | CHOPPER | HN | OUT | UTP | G1 | 2025-07-26 | 2025-07-26 | N-OUT | C-HN-UTP:07/26 > G1:07/26
380 | CHOPPER | HN | IN | G1 | UTP | 2025-07-26 | 2025-07-26 | N-IN | C-HN-G1:07/26 > UTP:07/26
381 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-26 | 2025-07-26 | S-OUT | C-HS-SKL:07/26 > G11:07/26
382 | CHOPPER | HS | IN | G11 | SKL | 2025-07-26 | 2025-07-26 | S-IN | C-HS-G11:07/26 > SKL:07/26
383 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-28 | 2025-07-28 | N-OUT | C-HN-UTP:07/28 > JAS:07/28
384 | CHOPPER | HN | IN | JAS | UTP | 2025-07-28 | 2025-07-28 | N-IN | C-HN-JAS:07/28 > UTP:07/28
385 | CHOPPER | HS | OUT | SKL | G11 | 2025-07-30 | 2025-07-30 | S-OUT | C-HS-SKL:07/30 > G11:07/30
386 | CHOPPER | HS | IN | G11 | SKL | 2025-07-30 | 2025-07-30 | S-IN | C-HS-G11:07/30 > SKL:07/30
387 | CHOPPER | HS | OUT | SKL | G10 | 2025-07-30 | 2025-07-30 | S-OUT | C-HS-SKL:07/30 > G10:07/30
388 | CHOPPER | HS | IN | G10 | SKL | 2025-07-30 | 2025-07-30 | S-IN | C-HS-G10:07/30 > SKL:07/30
389 | CHOPPER | HN | OUT | UTP | JAS | 2025-07-31 | 2025-07-31 | N-OUT | C-HN-UTP:07/31 > JAS:07/31
390 | CHOPPER | HN | IN | JAS | UTP | 2025-07-31 | 2025-07-31 | N-IN | C-HN-JAS:07/31 > UTP:07/31
391 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-01 | 2025-08-01 | S-OUT | C-HS-SKL:08/01 > G10:08/01
392 | CHOPPER | HS | IN | G10 | SKL | 2025-08-01 | 2025-08-01 | S-IN | C-HS-G10:08/01 > SKL:08/01
393 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-02 | 2025-08-02 | N-OUT | C-HN-UTP:08/02 > JAS:08/02
394 | CHOPPER | HN | IN | JAS | UTP | 2025-08-02 | 2025-08-02 | N-IN | C-HN-JAS:08/02 > UTP:08/02
395 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-02 | 2025-08-02 | N-OUT | C-HN-UTP:08/02 > G1:08/02
396 | CHOPPER | HN | IN | G1 | UTP | 2025-08-02 | 2025-08-02 | N-IN | C-HN-G1:08/02 > UTP:08/02
397 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-04 | 2025-08-04 | N-OUT | C-HN-UTP:08/04 > JAS:08/04
398 | CHOPPER | HN | IN | JAS | UTP | 2025-08-04 | 2025-08-04 | N-IN | C-HN-JAS:08/04 > UTP:08/04
399 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-04 | 2025-08-04 | N-OUT | C-HN-UTP:08/04 > G1:08/04
400 | CHOPPER | HN | IN | G1 | UTP | 2025-08-04 | 2025-08-04 | N-IN | C-HN-G1:08/04 > UTP:08/04
401 | CHOPPER | HS | OUT | SKL | G11 | 2025-08-06 | 2025-08-06 | S-OUT | C-HS-SKL:08/06 > G11:08/06
402 | CHOPPER | HS | IN | G11 | SKL | 2025-08-06 | 2025-08-06 | S-IN | C-HS-G11:08/06 > SKL:08/06
403 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-06 | 2025-08-06 | S-OUT | C-HS-SKL:08/06 > G10:08/06
404 | CHOPPER | HS | IN | G10 | SKL | 2025-08-06 | 2025-08-06 | S-IN | C-HS-G10:08/06 > SKL:08/06
405 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-09 | 2025-08-09 | N-OUT | C-HN-UTP:08/09 > JAS:08/09
406 | CHOPPER | HN | IN | JAS | UTP | 2025-08-09 | 2025-08-09 | N-IN | C-HN-JAS:08/09 > UTP:08/09
407 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-09 | 2025-08-09 | N-OUT | C-HN-UTP:08/09 > G1:08/09
408 | CHOPPER | HN | IN | G1 | UTP | 2025-08-09 | 2025-08-09 | N-IN | C-HN-G1:08/09 > UTP:08/09
409 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-11 | 2025-08-11 | N-OUT | C-HN-UTP:08/11 > JAS:08/11
410 | CHOPPER | HN | IN | JAS | UTP | 2025-08-11 | 2025-08-11 | N-IN | C-HN-JAS:08/11 > UTP:08/11
411 | CHOPPER | HS | OUT | SKL | G11 | 2025-08-13 | 2025-08-13 | S-OUT | C-HS-SKL:08/13 > G11:08/13
412 | CHOPPER | HS | IN | G11 | SKL | 2025-08-13 | 2025-08-13 | S-IN | C-HS-G11:08/13 > SKL:08/13
413 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-13 | 2025-08-13 | S-OUT | C-HS-SKL:08/13 > G10:08/13
414 | CHOPPER | HS | IN | G10 | SKL | 2025-08-13 | 2025-08-13 | S-IN | C-HS-G10:08/13 > SKL:08/13
415 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-14 | 2025-08-14 | N-OUT | C-HN-UTP:08/14 > JAS:08/14
416 | CHOPPER | HN | IN | JAS | UTP | 2025-08-14 | 2025-08-14 | N-IN | C-HN-JAS:08/14 > UTP:08/14
417 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-15 | 2025-08-15 | S-OUT | C-HS-SKL:08/15 > G10:08/15
418 | CHOPPER | HS | IN | G10 | SKL | 2025-08-15 | 2025-08-15 | S-IN | C-HS-G10:08/15 > SKL:08/15
419 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-16 | 2025-08-16 | N-OUT | C-HN-UTP:08/16 > JAS:08/16
420 | CHOPPER | HN | IN | JAS | UTP | 2025-08-16 | 2025-08-16 | N-IN | C-HN-JAS:08/16 > UTP:08/16
421 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-16 | 2025-08-16 | N-OUT | C-HN-UTP:08/16 > G1:08/16
422 | CHOPPER | HN | IN | G1 | UTP | 2025-08-16 | 2025-08-16 | N-IN | C-HN-G1:08/16 > UTP:08/16
423 | CHOPPER | HS | OUT | SKL | G11 | 2025-08-16 | 2025-08-16 | S-OUT | C-HS-SKL:08/16 > G11:08/16
424 | CHOPPER | HS | IN | G11 | SKL | 2025-08-16 | 2025-08-16 | S-IN | C-HS-G11:08/16 > SKL:08/16
425 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-18 | 2025-08-18 | N-OUT | C-HN-UTP:08/18 > JAS:08/18
426 | CHOPPER | HN | IN | JAS | UTP | 2025-08-18 | 2025-08-18 | N-IN | C-HN-JAS:08/18 > UTP:08/18
427 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-18 | 2025-08-18 | N-OUT | C-HN-UTP:08/18 > G1:08/18
428 | CHOPPER | HN | IN | G1 | UTP | 2025-08-18 | 2025-08-18 | N-IN | C-HN-G1:08/18 > UTP:08/18
429 | CHOPPER | HS | OUT | SKL | G11 | 2025-08-20 | 2025-08-20 | S-OUT | C-HS-SKL:08/20 > G11:08/20
430 | CHOPPER | HS | IN | G11 | SKL | 2025-08-20 | 2025-08-20 | S-IN | C-HS-G11:08/20 > SKL:08/20
431 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-20 | 2025-08-20 | S-OUT | C-HS-SKL:08/20 > G10:08/20
432 | CHOPPER | HS | IN | G10 | SKL | 2025-08-20 | 2025-08-20 | S-IN | C-HS-G10:08/20 > SKL:08/20
433 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-21 | 2025-08-21 | N-OUT | C-HN-UTP:08/21 > JAS:08/21
434 | CHOPPER | HN | IN | JAS | UTP | 2025-08-21 | 2025-08-21 | N-IN | C-HN-JAS:08/21 > UTP:08/21
435 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-22 | 2025-08-22 | S-OUT | C-HS-SKL:08/22 > G10:08/22
436 | CHOPPER | HS | IN | G10 | SKL | 2025-08-22 | 2025-08-22 | S-IN | C-HS-G10:08/22 > SKL:08/22
437 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-23 | 2025-08-23 | N-OUT | C-HN-UTP:08/23 > JAS:08/23
438 | CHOPPER | HN | IN | JAS | UTP | 2025-08-23 | 2025-08-23 | N-IN | C-HN-JAS:08/23 > UTP:08/23
439 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-23 | 2025-08-23 | N-OUT | C-HN-UTP:08/23 > G1:08/23
440 | CHOPPER | HN | IN | G1 | UTP | 2025-08-23 | 2025-08-23 | N-IN | C-HN-G1:08/23 > UTP:08/23
441 | CHOPPER | HS | OUT | SKL | G11 | 2025-08-23 | 2025-08-23 | S-OUT | C-HS-SKL:08/23 > G11:08/23
442 | CHOPPER | HS | IN | G11 | SKL | 2025-08-23 | 2025-08-23 | S-IN | C-HS-G11:08/23 > SKL:08/23
443 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-25 | 2025-08-25 | N-OUT | C-HN-UTP:08/25 > JAS:08/25
444 | CHOPPER | HN | IN | JAS | UTP | 2025-08-25 | 2025-08-25 | N-IN | C-HN-JAS:08/25 > UTP:08/25
445 | CHOPPER | HS | OUT | SKL | G11 | 2025-08-27 | 2025-08-27 | S-OUT | C-HS-SKL:08/27 > G11:08/27
446 | CHOPPER | HS | IN | G11 | SKL | 2025-08-27 | 2025-08-27 | S-IN | C-HS-G11:08/27 > SKL:08/27
447 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-27 | 2025-08-27 | S-OUT | C-HS-SKL:08/27 > G10:08/27
448 | CHOPPER | HS | IN | G10 | SKL | 2025-08-27 | 2025-08-27 | S-IN | C-HS-G10:08/27 > SKL:08/27
449 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-28 | 2025-08-28 | N-OUT | C-HN-UTP:08/28 > JAS:08/28
450 | CHOPPER | HN | IN | JAS | UTP | 2025-08-28 | 2025-08-28 | N-IN | C-HN-JAS:08/28 > UTP:08/28
451 | CHOPPER | HS | OUT | SKL | G10 | 2025-08-29 | 2025-08-29 | S-OUT | C-HS-SKL:08/29 > G10:08/29
452 | CHOPPER | HS | IN | G10 | SKL | 2025-08-29 | 2025-08-29 | S-IN | C-HS-G10:08/29 > SKL:08/29
453 | CHOPPER | HN | OUT | UTP | JAS | 2025-08-30 | 2025-08-30 | N-OUT | C-HN-UTP:08/30 > JAS:08/30
454 | CHOPPER | HN | IN | JAS | UTP | 2025-08-30 | 2025-08-30 | N-IN | C-HN-JAS:08/30 > UTP:08/30
455 | CHOPPER | HN | OUT | UTP | G1 | 2025-08-30 | 2025-08-30 | N-OUT | C-HN-UTP:08/30 > G1:08/30
456 | CHOPPER | HN | IN | G1 | UTP | 2025-08-30 | 2025-08-30 | N-IN | C-HN-G1:08/30 > UTP:08/30
457 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-01 | 2025-09-01 | N-OUT | C-HN-UTP:09/01 > JAS:09/01
458 | CHOPPER | HN | IN | JAS | UTP | 2025-09-01 | 2025-09-01 | N-IN | C-HN-JAS:09/01 > UTP:09/01
459 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-01 | 2025-09-01 | N-OUT | C-HN-UTP:09/01 > G1:09/01
460 | CHOPPER | HN | IN | G1 | UTP | 2025-09-01 | 2025-09-01 | N-IN | C-HN-G1:09/01 > UTP:09/01
461 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-03 | 2025-09-03 | S-OUT | C-HS-SKL:09/03 > G11:09/03
462 | CHOPPER | HS | IN | G11 | SKL | 2025-09-03 | 2025-09-03 | S-IN | C-HS-G11:09/03 > SKL:09/03
463 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-03 | 2025-09-03 | S-OUT | C-HS-SKL:09/03 > G10:09/03
464 | CHOPPER | HS | IN | G10 | SKL | 2025-09-03 | 2025-09-03 | S-IN | C-HS-G10:09/03 > SKL:09/03
465 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-06 | 2025-09-06 | N-OUT | C-HN-UTP:09/06 > JAS:09/06
466 | CHOPPER | HN | IN | JAS | UTP | 2025-09-06 | 2025-09-06 | N-IN | C-HN-JAS:09/06 > UTP:09/06
467 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-06 | 2025-09-06 | N-OUT | C-HN-UTP:09/06 > G1:09/06
468 | CHOPPER | HN | IN | G1 | UTP | 2025-09-06 | 2025-09-06 | N-IN | C-HN-G1:09/06 > UTP:09/06
469 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-06 | 2025-09-06 | S-OUT | C-HS-SKL:09/06 > G11:09/06
470 | CHOPPER | HS | IN | G11 | SKL | 2025-09-06 | 2025-09-06 | S-IN | C-HS-G11:09/06 > SKL:09/06
471 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-08 | 2025-09-08 | N-OUT | C-HN-UTP:09/08 > JAS:09/08
472 | CHOPPER | HN | IN | JAS | UTP | 2025-09-08 | 2025-09-08 | N-IN | C-HN-JAS:09/08 > UTP:09/08
473 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-10 | 2025-09-10 | S-OUT | C-HS-SKL:09/10 > G11:09/10
474 | CHOPPER | HS | IN | G11 | SKL | 2025-09-10 | 2025-09-10 | S-IN | C-HS-G11:09/10 > SKL:09/10
475 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-10 | 2025-09-10 | S-OUT | C-HS-SKL:09/10 > G10:09/10
476 | CHOPPER | HS | IN | G10 | SKL | 2025-09-10 | 2025-09-10 | S-IN | C-HS-G10:09/10 > SKL:09/10
477 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-11 | 2025-09-11 | N-OUT | C-HN-UTP:09/11 > JAS:09/11
478 | CHOPPER | HN | IN | JAS | UTP | 2025-09-11 | 2025-09-11 | N-IN | C-HN-JAS:09/11 > UTP:09/11
479 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-12 | 2025-09-12 | S-OUT | C-HS-SKL:09/12 > G10:09/12
480 | CHOPPER | HS | IN | G10 | SKL | 2025-09-12 | 2025-09-12 | S-IN | C-HS-G10:09/12 > SKL:09/12
481 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-13 | 2025-09-13 | N-OUT | C-HN-UTP:09/13 > JAS:09/13
482 | CHOPPER | HN | IN | JAS | UTP | 2025-09-13 | 2025-09-13 | N-IN | C-HN-JAS:09/13 > UTP:09/13
483 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-13 | 2025-09-13 | N-OUT | C-HN-UTP:09/13 > G1:09/13
484 | CHOPPER | HN | IN | G1 | UTP | 2025-09-13 | 2025-09-13 | N-IN | C-HN-G1:09/13 > UTP:09/13
485 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-15 | 2025-09-15 | N-OUT | C-HN-UTP:09/15 > JAS:09/15
486 | CHOPPER | HN | IN | JAS | UTP | 2025-09-15 | 2025-09-15 | N-IN | C-HN-JAS:09/15 > UTP:09/15
487 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-15 | 2025-09-15 | N-OUT | C-HN-UTP:09/15 > G1:09/15
488 | CHOPPER | HN | IN | G1 | UTP | 2025-09-15 | 2025-09-15 | N-IN | C-HN-G1:09/15 > UTP:09/15
489 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-17 | 2025-09-17 | S-OUT | C-HS-SKL:09/17 > G11:09/17
490 | CHOPPER | HS | IN | G11 | SKL | 2025-09-17 | 2025-09-17 | S-IN | C-HS-G11:09/17 > SKL:09/17
491 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-17 | 2025-09-17 | S-OUT | C-HS-SKL:09/17 > G10:09/17
492 | CHOPPER | HS | IN | G10 | SKL | 2025-09-17 | 2025-09-17 | S-IN | C-HS-G10:09/17 > SKL:09/17
493 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-19 | 2025-09-19 | S-OUT | C-HS-SKL:09/19 > G10:09/19
494 | CHOPPER | HS | IN | G10 | SKL | 2025-09-19 | 2025-09-19 | S-IN | C-HS-G10:09/19 > SKL:09/19
495 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-20 | 2025-09-20 | N-OUT | C-HN-UTP:09/20 > JAS:09/20
496 | CHOPPER | HN | IN | JAS | UTP | 2025-09-20 | 2025-09-20 | N-IN | C-HN-JAS:09/20 > UTP:09/20
497 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-20 | 2025-09-20 | N-OUT | C-HN-UTP:09/20 > G1:09/20
498 | CHOPPER | HN | IN | G1 | UTP | 2025-09-20 | 2025-09-20 | N-IN | C-HN-G1:09/20 > UTP:09/20
499 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-20 | 2025-09-20 | S-OUT | C-HS-SKL:09/20 > G11:09/20
500 | CHOPPER | HS | IN | G11 | SKL | 2025-09-20 | 2025-09-20 | S-IN | C-HS-G11:09/20 > SKL:09/20
501 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-22 | 2025-09-22 | N-OUT | C-HN-UTP:09/22 > JAS:09/22
502 | CHOPPER | HN | IN | JAS | UTP | 2025-09-22 | 2025-09-22 | N-IN | C-HN-JAS:09/22 > UTP:09/22
503 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-24 | 2025-09-24 | S-OUT | C-HS-SKL:09/24 > G11:09/24
504 | CHOPPER | HS | IN | G11 | SKL | 2025-09-24 | 2025-09-24 | S-IN | C-HS-G11:09/24 > SKL:09/24
505 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-24 | 2025-09-24 | S-OUT | C-HS-SKL:09/24 > G10:09/24
506 | CHOPPER | HS | IN | G10 | SKL | 2025-09-24 | 2025-09-24 | S-IN | C-HS-G10:09/24 > SKL:09/24
507 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-25 | 2025-09-25 | N-OUT | C-HN-UTP:09/25 > JAS:09/25
508 | CHOPPER | HN | IN | JAS | UTP | 2025-09-25 | 2025-09-25 | N-IN | C-HN-JAS:09/25 > UTP:09/25
509 | CHOPPER | HS | OUT | SKL | G10 | 2025-09-26 | 2025-09-26 | S-OUT | C-HS-SKL:09/26 > G10:09/26
510 | CHOPPER | HS | IN | G10 | SKL | 2025-09-26 | 2025-09-26 | S-IN | C-HS-G10:09/26 > SKL:09/26
511 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-27 | 2025-09-27 | N-OUT | C-HN-UTP:09/27 > JAS:09/27
512 | CHOPPER | HN | IN | JAS | UTP | 2025-09-27 | 2025-09-27 | N-IN | C-HN-JAS:09/27 > UTP:09/27
513 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-27 | 2025-09-27 | N-OUT | C-HN-UTP:09/27 > G1:09/27
514 | CHOPPER | HN | IN | G1 | UTP | 2025-09-27 | 2025-09-27 | N-IN | C-HN-G1:09/27 > UTP:09/27
515 | CHOPPER | HS | OUT | SKL | G11 | 2025-09-27 | 2025-09-27 | S-OUT | C-HS-SKL:09/27 > G11:09/27
516 | CHOPPER | HS | IN | G11 | SKL | 2025-09-27 | 2025-09-27 | S-IN | C-HS-G11:09/27 > SKL:09/27
517 | CHOPPER | HN | OUT | UTP | JAS | 2025-09-29 | 2025-09-29 | N-OUT | C-HN-UTP:09/29 > JAS:09/29
518 | CHOPPER | HN | IN | JAS | UTP | 2025-09-29 | 2025-09-29 | N-IN | C-HN-JAS:09/29 > UTP:09/29
519 | CHOPPER | HN | OUT | UTP | G1 | 2025-09-29 | 2025-09-29 | N-OUT | C-HN-UTP:09/29 > G1:09/29
520 | CHOPPER | HN | IN | G1 | UTP | 2025-09-29 | 2025-09-29 | N-IN | C-HN-G1:09/29 > UTP:09/29

## Field_Bed_Capacity
Id | Field | Bed_Capacity
1 | JAS | 101
2 | G1 | 80
3 | G11 | 80
4 | NYC | 50
5 | G10 | 46
6 | G10_FSO | 45

## Regular_Crew
Id | Field | Date_Start | Date_End | Person_On_Board
1 | JAS | 2025-07-01 | 2025-07-16 | 66
2 | JAS | 2025-07-17 | 2025-07-18 | 67
3 | JAS | 2025-07-19 | 2025-09-30 | 70
4 | G1 | 2025-07-01 | 2025-07-16 | 52
5 | G1 | 2025-07-17 | 2025-07-26 | 48
6 | G1 | 2025-07-27 | 2025-09-30 | 52
7 | G11 | 2025-07-01 | 2025-09-30 | 49
8 | NYC | 2025-07-01 | 2025-07-04 | 15
10 | NYC | 2025-07-07 | 2025-07-11 | 15
12 | NYC | 2025-07-14 | 2025-07-18 | 15
14 | NYC | 2025-07-21 | 2025-07-25 | 15
16 | NYC | 2025-07-28 | 2025-08-01 | 15
18 | NYC | 2025-08-04 | 2025-08-08 | 15
20 | NYC | 2025-08-11 | 2025-08-15 | 15
22 | NYC | 2025-08-18 | 2025-08-22 | 15
24 | NYC | 2025-08-25 | 2025-08-29 | 15
26 | NYC | 2025-09-01 | 2025-09-05 | 15
28 | NYC | 2025-09-08 | 2025-09-12 | 15
30 | NYC | 2025-09-15 | 2025-09-19 | 15
32 | NYC | 2025-09-22 | 2025-09-26 | 15
34 | NYC | 2025-09-29 | 2025-10-03 | 15
36 | NYC | 2025-10-06 | 2025-10-10 | 15
38 | NYC | 2025-07-05 | 2025-07-06 | 17
40 | NYC | 2025-07-12 | 2025-07-13 | 17
42 | NYC | 2025-07-19 | 2025-07-20 | 17
44 | NYC | 2025-07-26 | 2025-07-27 | 17
46 | NYC | 2025-08-02 | 2025-08-03 | 17
48 | NYC | 2025-08-09 | 2025-08-10 | 17
50 | NYC | 2025-08-16 | 2025-08-17 | 17
52 | NYC | 2025-08-23 | 2025-08-24 | 17
54 | NYC | 2025-08-30 | 2025-08-31 | 17
56 | NYC | 2025-09-06 | 2025-09-07 | 17
58 | NYC | 2025-09-13 | 2025-09-14 | 17
60 | NYC | 2025-09-20 | 2025-09-21 | 17
62 | NYC | 2025-09-27 | 2025-09-28 | 17
64 | G10 | 2025-07-01 | 2025-09-30 | 26
66 | G10_FSO | 2025-07-01 | 2025-09-30 | 26

## Boat_Chopper_Capacity
Id | Vessel_Name | Bed_Capacity | Seat_Capacity
1 | SUMMER | 27 | 27
2 | GLORY5 | 0 | 90
3 | GANYA | 43 | 43
4 | UNIVERSE | 27 | 27
5 | ATHENA | 24 | 24
6 | GALAXY | 33 | 33
7 | NEPTUNE | 27 | 27
8 | NATA | 43 | 43
9 | CHOPPER | 0 | 12

## Date_Calendar
Id | Date
1 | 2025-07-01
2 | 2025-07-02
3 | 2025-07-03
4 | 2025-07-04
5 | 2025-07-05
6 | 2025-07-06
7 | 2025-07-07
8 | 2025-07-08
9 | 2025-07-09
10 | 2025-07-10
11 | 2025-07-11
12 | 2025-07-12
13 | 2025-07-13
14 | 2025-07-14
15 | 2025-07-15
16 | 2025-07-16
17 | 2025-07-17
18 | 2025-07-18
19 | 2025-07-19
20 | 2025-07-20
21 | 2025-07-21
22 | 2025-07-22
23 | 2025-07-23
24 | 2025-07-24
25 | 2025-07-25
26 | 2025-07-26
27 | 2025-07-27
28 | 2025-07-28
29 | 2025-07-29
30 | 2025-07-30
31 | 2025-07-31
32 | 2025-08-01
33 | 2025-08-02
34 | 2025-08-03
35 | 2025-08-04
36 | 2025-08-05
37 | 2025-08-06
38 | 2025-08-07
39 | 2025-08-08
40 | 2025-08-09
41 | 2025-08-10
42 | 2025-08-11
43 | 2025-08-12
44 | 2025-08-13
45 | 2025-08-14
46 | 2025-08-15
47 | 2025-08-16
48 | 2025-08-17
49 | 2025-08-18
50 | 2025-08-19
51 | 2025-08-20
52 | 2025-08-21
53 | 2025-08-22
54 | 2025-08-23
55 | 2025-08-24
56 | 2025-08-25
57 | 2025-08-26
58 | 2025-08-27
59 | 2025-08-28
60 | 2025-08-29
61 | 2025-08-30
62 | 2025-08-31
63 | 2025-09-01
64 | 2025-09-02
65 | 2025-09-03
66 | 2025-09-04
67 | 2025-09-05
68 | 2025-09-06
69 | 2025-09-07
70 | 2025-09-08
71 | 2025-09-09
72 | 2025-09-10
73 | 2025-09-11
74 | 2025-09-12
75 | 2025-09-13
76 | 2025-09-14
77 | 2025-09-15
78 | 2025-09-16
79 | 2025-09-17
80 | 2025-09-18
81 | 2025-09-19
82 | 2025-09-20
83 | 2025-09-21
84 | 2025-09-22
85 | 2025-09-23
86 | 2025-09-24
87 | 2025-09-25
88 | 2025-09-26
89 | 2025-09-27
90 | 2025-09-28
91 | 2025-09-29
92 | 2025-09-30