## Booking
Field | IAP_ID | SML_ID | Platform | Department | Project_Description | Project_Owner | Vendor | POB | PlanStart | PlanFinish | Duration | InterField | MobCode | DeMobCode | Mob_By_Code | De-mob_By_Code | L_Remarks
G11 | 25-0023 |  |  | DRI | NYA (3D+1A) | Drilling |  |  | 2025-05-23 | 2025-07-08 | 47 | S-FT | S-OUT | S-IN
JAS | 25-0244 |  | PPB2 | OPS | TNS/Expert suport GTG operation (Jun 25 - Jan 26) | Somsak | TNS/Expert | 1 | 2025-06-01 | 2026-01-01 | 215 | N-FT | N-OUT | N-IN
JAS | 25-0005 | 934, 958, 980 | ALL PF | AIM | Maintenance Painting #1 [Experteam+AI Sup ] | Mittrapa | EXPT / AI Sup | 9 | 2025-06-08 | 2025-07-01 | 24 | N-FT | N-OUT | N-IN | V-MC-STH:06/07 > JAS:06/08 | V-GY-JAS:07/02 > STH:07/03
JAS | 25-0006 |  | ALL PF | AIM | TSI: Topside Inspection [Dexon-RA] | Pradit | DEXON | 4 | 2025-06-08 | 2025-07-01 | 24 | N-FT | N-OUT | N-IN | V-MC-STH:06/07 > JAS:06/08 | V-GY-JAS:07/02 > STH:07/03
G1 | 25-0075 | 843, 845 |  | WSV | Work Over : MNA-16&27 | Asadawut | Work Over | 4 | 2025-06-12 | 2025-06-29 | 18 | N-FT | N-OUT | N-IN |  |  | reroute demob MN on 22 Jun
G10 | 25-0017 | 998, 997 | MOPU | BFT | [BFT] WAS051 Additional VSD 18, WAS083 Gen 5, SCADA Upgrade | Wason | Experteam+VE Supt. | 10 | 2025-06-15 | 2025-06-30 | 16 | S-FT | S-OUT | S-IN | V-SM-SKL:06/14 > WN:06/15 | V-SM-WN:07/01 > NY:07/01 > SKL:07/02 | demob to skl by galaxy on 20 Jul
G10 | 25-0048 | 996 | MOPU | MNT | ABB pump Air-Cooling Fan Cover VFD & MG#7 & #8 Insulation exhaust | Ohmmanas | Expert | 12 | 2025-06-15 | 2025-07-05 | 21 | S-FT | S-OUT | S-IN | V-SM-SKL:06/14 > WN:06/15 | V-UV-NY:07/06 > WN:07/06 > SKL:07/07 | Reqeust Reroute to WAS
JAS | 25-0233 | 982 | ALL PF | AIM | Maintenance Painting #3 [Experteam] | Mittrapa | EXPT | 8 | 2025-06-17 | 2025-07-01 | 15 | N-FT | N-OUT | N-IN | V-TC-STH:06/16 > MNA:06/17 | V-GY-JAS:07/02 > STH:07/03
G11 | 25-0013 | 402, 882, 903, 963, 977 | NYA | BFT | [BFT] NYA Well Hookup | Somkiat | Tantawan , BAKER , VE Supt | 9 | 2025-06-19 | 2025-07-05 | 17 | S-FT | S-OUT | S-IN | V-GX-SKL:06/18 > NY:06/19 | V-UV-NY:07/06 > WN:07/06 > SKL:07/07
G11 | 25-0231 | 979 | NYC | OPS | [OPS] Extra cattering support activity#1 | Pitsanu |  | 1 | 2025-06-19 | 2025-07-22 | 34 | S-FT | S-OUT | S-IN | V-GX-SKL:06/18 > NY:06/19 | V-SM-WN:07/23 > NY:07/23 > SKL:07/24
G11 | 25-0015 | 789 | NYC | BFT | [BFT] NY171 NYC additional wells mob 1 team 1 | Somkiat | TNS | 17 | 2025-06-23 | 2025-07-19 | 27 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > NY:06/23 | V-GX-NY:07/20 > WN:07/20 > SKL:07/21 | Reroute GX WN-SKL to WN-NY-SKL
G11 | 25-0234 | 1138, 1201 | NYC | BFT | [BFT] NY171 NYC additional well VE supt no. 1 | Somkiat | VE Supt | 1 | 2025-06-23 | 2025-07-19 | 27 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > NY:06/23 | V-GX-NY:07/20 > WN:07/20 > SKL:07/21
G11 | 25-0015 |  | NYC | BFT | [BFT] NY171 NYC additional wells mob 1 team 2 | Somkiat | TNS | 7 | 2025-06-23 | 2025-07-19 | 27 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > NY:06/23 | V-GX-NY:07/20 > WN:07/20 > SKL:07/21
G10 | 25-0076 |  |  | WSV | Work Over : WSA-01i | Asadawut | Work Over | 8 | 2025-07-03 | 2025-07-14 | 12 | S-FT | S-OUT | S-IN
G11 | 25-0116 |  | FSO | FSO | OMNI Suptds visit /OMNI HSE Audit / 10 Year Ceremony#3 | OMNI | OMNI | 1 | 2025-06-23 | 2025-07-04 | 12 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > NY:06/23 | C-HS-NY:07/05 > SKL:07/05
G11 | 25-0122 |  | FSO | FSO | Metering Skid 2 Yearly Prover Calibration with DMF verification (Tentative 23 Jun - 07 Jul) | OMNI | OMNI | 2 | 2025-06-23 | 2025-07-04 | 12 | S-FT | S-OUT | S-IN | V-UV-SKL:06/22 > NY:06/23 | V-UV-NY:07/06 > SKL:07/07
JAS | 25-0196 |  | FSO | FSO | Pre-Mooring Wire Replacement: 200T Turret hydraulic winch inspection | Petrofac | Sparrow | 1 | 2025-08-02 | 2025-08-08 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:08/02 > JAS:08/02 | C-HN-JAS:08/09 > UTP:08/09
G11 | 25-0212 | 785, 1141 | WPP | OPS | fiscal meter recalibration 2025 DMF (1), VE (1), Flowlabs (6) | Benjachai | DMF+VE+Flowlab | 8 | 2025-06-24 | 2025-07-04 | 11 | S-FT | S-OUT | S-IN |  |  | wait for special flight mob and demob
JAS | 25-0197 | 1162 | FSO | FSO | General Remedial Repairs and Fabric Maintenance & Chipping and Painting -Mob 6 | Petrofac | Tindy | 6 | 2025-06-25 | 2025-07-17 | 23 | N-FT | N-OUT | N-IN | V-AT-STH:06/24 > JAS:06/25 | V-GY-JAS:07/18 > STH:07/19
JAS | 25-0218 | 1211 | BYA | MNT | BYA Bi-Fuel survey | Pruang | Comap | 1 | 2025-07-03 | 2025-07-06 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:07/03 > JAS:07/03 | C-HN-JAS:07/07 > UTP:07/07
JAS | 25-0246 | 1199 | WPA, PPB2, WPD, BYA | MNT | Jasmine UPS, Charger and Battery 3 Year Service Maintenance. | Ohmmanas | SR | 2 | 2025-06-30 | 2025-07-09 | 10 | N-FT | N-OUT | N-IN | C-HN-UTP:06/30 > JAS:06/30 | C-HN-JAS:07/10 > UTP:07/10
JAS | 25-0042 | 1163 | FSO | FSO | Annual Main Turret Bearing Inspection -OEM | Petrofac | Thyssenkrupp | 1 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
JAS | 25-0128 | 973, 1001 | FSO | OFF | Offtake JC-685 | Benjachai |  | 3 | 2025-06-28 | 2025-07-02 | 5 | N-FT | N-OUT | N-IN
JAS | 25-0149 | 791 | FSO | FSO | Petrofac Managemnt visit (M Danish Merchant /Josie Philips ) | Petrofac | Petrofac | 2 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
JAS | 25-0150 | 628 | FSO | FSO | Annual Main Turret Bearing Inspection -OEM | Petrofac | ABS | 1 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
JAS | 25-0198 | 1121 | FSO | FSO | Annual Main Turret Bearing Inspection -Petrofac Operation & Integrity Engineer | Petrofac | Petrofac | 1 | 2025-06-28 | 2025-06-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:06/28 > JAS:06/28 | C-HN-JAS:06/30 > UTP:06/30
G10 | 25-0156 | 1048 | MOPU | MNT | Aggreko MG#7 and MG#8 service | Ekawit | Aggreko | 2 | 2025-07-01 | 2025-07-05 | 5 | S-FT | S-OUT | S-IN | V-GX-SKL:06/30 > WN:07/01 |  | Request reroute vessel SC UNIVERSE on 6 July from "NY - SKL" to "NY - WAS - SKL"
G11 | 25-0136 |  | NYC | AIM | [AIM] NYC MOPU annual classification survey #1 [Itt+ABS] | Atthapong | ABS/VE | 3 | 2025-08-12 | 2025-08-18 | 7 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > NY:08/12 | V-SM-NY:08/19 > WN:08/19 | Request Reroute to NY
G1 | 25-0171 |  | FSO | FSO | OMNI Suptds visit /ISM/HSE Audit Jun | OMNI | OMNI | 1 | 2025-07-05 | 2025-07-11 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:07/05 > MNA:07/05 | C-HN-MNA:07/12 > UTP:07/12
G11 | 25-0175 |  | NYC | AIM | [AIM] NYC MOPU annual classification survey #2 [SMC] | Atthapong | SMC | 2 | 2025-08-12 | 2025-08-18 | 7 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > NY:08/12 | V-SM-NY:08/19 > WN:08/19 | Request Reroute to NY
G11 | 25-0176 |  | NYC | AIM | [AIM] NYC MOPU annual classification survey #3 [Brilliant] | Atthapong | Brilliant | 1 | 2025-08-12 | 2025-08-18 | 7 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > NY:08/12 | V-SM-NY:08/19 > WN:08/19 | Request Reroute to NY
G10 | 25-0249 |  | MOPU | MNT | ABB pump VSD major 6Y PM#1 | Ohmmanas | VE | 1 | 2025-07-04 | 2025-07-13 | 10 | S-FT | S-OUT | S-IN | V-SM-SKL:07/03 > WN:07/04 | V-GX-WN:07/14 > SKL:07/15
JAS | 25-0183 |  | ALL PF | ITM | JAS-2nd DT PM | Pichit | LBS | 1 | 2025-07-03 | 2025-07-11 | 9 | N-FT | N-OUT | N-IN | C-HN-UTP:07/03 > JAS:07/03 | V-AT-JAS:07/12 > MNA:07/13 > JAS:07/18
G10 | 25-0049 |  | MOPU | MNT | ABB pump VSD major 6Y PM#2 | Ohmmanas | ABB | 2 | 2025-07-04 | 2025-07-13 | 10 | S-FT | S-OUT | S-IN | V-SM-SKL:07/03 > WN:07/04 | V-GX-WN:07/14 > SKL:07/15
JAS | 25-0039 |  | FSO | FSO | Replace Provsion Crane Boom Tip - Scaffolding | Petrofac | EMC | 5 | 2025-07-05 | 2025-07-17 | 13 | N-FT | N-OUT | N-IN | V-GY-STH:07/04 > JAS:07/05 | V-GY-JAS:07/18 > STH:07/19 | postpone demob on 22 Jun to 26 due seat not enough
JAS | 25-0101 |  | WPB | MNT | WPB WPD BYA HVAC Replacement [Expert] | Pruang | Expert | 10 | 2025-07-05 | 2025-08-01 | 28 | N-FT | N-OUT | N-IN | V-GY-STH:07/04 > JAS:07/05 | V-NT-JAS:08/02 > MNA:08/02 > JAS:08/05 | back to STH by Neptune on 2 Aug
G1 | 25-0250 |  |  | FSO | ABS Class Survey / Flag Inspection | OMNI | ABS | 1 | 2025-07-05 | 2025-07-07 | 3 | N-FT | N-OUT | N-IN
JAS | 25-0184 |  | ALL PF | ITM | JAS-2nd VSAT PM, Radio PM and Replacement new equipment | Pichit | Infonet+UMT | 4 | 2025-07-07 | 2025-07-11 | 5 | N-FT | N-OUT | N-IN | V-G5-STH:07/07 > JAS:07/07 | V-AT-JAS:07/12 > MNA:07/13 > JAS:07/18
G10 | 25-0207 |  | MOPU | WSV | Work Over : WSA-20H | Asadawut | Work Over | 4 | 2025-07-14 | 2025-07-26 | 13 | S-FT | S-OUT | S-IN
G11 | 25-0074 |  |  | DRI | NYC (1D+1A/D+2WI) | Drilling |  |  | 2025-07-08 | 2025-08-15 |  | S-FT | S-OUT | S-IN
G10 | 25-0251 |  | MOPU | BFT | [BFT] Workover support (WSA-01i) | Somkiat | Experteam+VE Supt. | 8 | 2025-07-09 | 2025-07-25 | 17 | S-FT | S-OUT | S-IN | V-UV-SKL:07/08 > NY:07/09 | V-UV-NY:07/26 > SKL:07/27
G10 | 25-0132 |  | FSO | OFF | Offtake WC-047 | Benjachai |  | 3 | 2025-07-09 | 2025-07-15 | 7 | S-FT | S-OUT | S-IN
G1 | 25-0252 |  | WPP-A | AIM | Maintenance Painting [Experteam+AI Sup ] | Mittrapa | EXPT / AI Sup | 18 | 2025-09-02 | 2025-09-24 | 23 | N-FT | N-OUT | N-IN | V-GY-STH:09/01 > MNA:09/02 > JAS:09/02 | V-TC-MNA:09/25 > STH:09/26 | Request to reroute GY via MN.
G1 | 25-0011 | 950 | WPP-A | BFT | [BFT] MN131 Manora debottleneck mob + S/D, MN136 PWIP check valve, MN137 Annulus vent, MN138 Gen Bellow, change SDV manifold, repair pipe leak, Closed drain header scale cleaning | Somkiat | TNS+VE Sup | 31 | 2025-07-02 | 2025-07-26 | 25 | N-FT | N-OUT | N-IN |  | V-GY-JAS:07/27 > MNA:07/27 > STH:07/28 | Mob via G5
G1 | 25-0253 |  | WPP-A | BFT | [BFT] MN131 Manora debottleneck mob post S/D | Somkiat | TNS+VE Sup | 12 | 2025-07-27 | 2025-08-01 | 6 | N-FT | N-OUT | N-IN | V-G5-STH:07/26 > JAS:07/27 | V-TC-MNA:08/02 > STH:08/03
JAS | 25-0254 |  | ALL PF | AIM | Maintenance Painting #4 [Experteam+AI Sup ] | Mittrapa | EXPT / AI Sup | 18 | 2025-09-18 | 2025-10-15 | 28 | N-FT | N-OUT | N-IN | V-GY-STH:09/17 > JAS:09/18
G1 | 25-0185 |  | ALL PF | ITM | MAN - 2nd Radio PM | Pichit | UMT | 2 | 2025-07-13 | 2025-07-18 | 6 | N-FT | N-OUT | N-IN | V-AT-JAS:07/12 > MNA:07/13 > JAS:07/18 | C-HN-MNA:07/19 > UTP:07/19
G1 | 25-0186 |  | ALL PF | ITM | MAN-2nd DT and VSAT PM + ICS Power cord replacement during MAN S/D#1 | Pichit | LBS+Infonet | 2 | 2025-07-13 | 2025-07-26 | 14 | N-FT | N-OUT | N-IN | V-AT-JAS:07/12 > MNA:07/13 > JAS:07/18 | C-HN-MNA:07/26 > UTP:07/26
G1 | 25-0238 |  | ALL PF | ITM | MAN-2nd DT and VSAT PM + ICS Power cord replacement during MAN S/D#2 | Pichit | Infonet | 1 | 2025-07-13 | 2025-07-20 | 8 | N-FT | N-OUT | N-IN | V-AT-JAS:07/12 > MNA:07/13 > JAS:07/18 | C-HN-MNA:07/21 > UTP:07/21
G1 | 25-0001 |  | WPP-A | AIM | [SD] Flare & GEN Exhaust Line Inspection [Dexon] | Pradit | DEXON | 4 | 2025-07-14 | 2025-08-01 | 19 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > MNA:07/14 | V-TC-MNA:08/02 > STH:08/03
G1 | 25-0061 |  | WPP-A | AIM | AI Supervisor [AI Sup] | Mittrapa | VE | 1 | 2025-07-14 | 2025-08-01 | 19 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > MNA:07/14 | V-TC-MNA:08/02 > STH:08/03
G1 | 25-0063 |  | WPP-A | AIM | [SD] GEN Exhaust Insulation Repair [TNS] | Pradit | TNS | 4 | 2025-07-14 | 2025-08-01 | 19 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > MNA:07/14 | V-TC-MNA:08/02 > STH:08/03
G1 | 25-0214 |  |  | OPS | [SD] Operation extra manpower (Opt ) | Puwat | VE | 2 | 2025-07-14 | 2025-07-25 | 12 | N-FT | N-OUT | N-IN
G1 | 25-0255 |  | WPP | MNT | ICSS DCS MODIFICATION FOR MN DBN Phase 3 Project | Warakorn | Yokogawa | 1 | 2025-07-14 | 2025-08-02 | 20 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > MNA:07/14 | V-TC-MNA:08/02 > STH:08/03
G11 | 25-0236 |  | NYC | BFT | [BFT] NY171 NYC additional wells mob 3-1 (MV) | Somkiat | ABB MV Term | 2 | 2025-07-16 | 2025-07-19 | 4 | S-FT | S-OUT | S-IN | V-GX-SKL:07/15 > NY:07/16 | V-GX-NY:07/20 > WN:07/20 > SKL:07/21
G11 | 25-0159 | 1106 | NYC | MNT | [MNT] NYC CM works with lacing replacement | Ekawit | TOS | 6 | 2025-07-16 | 2025-07-25 | 10 | S-FT | S-OUT | S-IN | V-GX-SKL:07/15 > NY:07/16 | V-UV-NY:07/26 > SKL:07/27 | Use same TOS crews of row 84
G11 | 25-0160 | 1008/1009 | NY | MNT | NYB2 Crank seal replacement | Ekawit | METRO CAT + Tantawan | 7 | 2025-07-16 | 2025-07-28 | 13 | S-FT | S-OUT | S-IN | V-GX-SKL:07/15 > NY:07/16 | V-SM-NY:07/29 > WN:07/29 > SKL:07/30 | TBC
G1 | 25-0130 |  | FSO | OFF | Offtake MC-133#1 | Benjachai |  | 3 | 2025-07-15 | 2025-07-19 | 5 | N-FT | N-OUT | N-IN
G11 | 25-0131 |  | FSO | OFF | Offtake NC-128 | Benjachai |  | 3 | 2025-07-15 | 2025-07-19 | 5 | S-FT | S-OUT | S-IN
G11 | 25-0235 |  | NYC | BFT | [BFT] NY171 NYC additional well VE supt no. 2 | Somkiat | VE Supt | 1 | 2025-07-26 | 2025-08-11 | 17 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > NY:07/26 | V-UV-NY:08/12 > SKL:08/13
G11 | 25-0256 |  | NYC | MNT | [MNT] NYC ICSS ADDITIONAL WELL DCS PROGRAM MODIFICATION#1 | Warakorn | Infinite | 1 | 2025-07-16 | 2025-07-30 | 15 |  |  |  | C-HS-SKL:07/16 > NY:07/16 | C-HS-NY:07/30 > SKL:07/30
G11 | 25-0257 |  | NYC | MNT | [MNT] NYC ICSS ADDITIONAL WELL DCS PROGRAM MODIFICATION#2 | Warakorn | VE | 1 | 2025-07-16 | 2025-07-26 | 11 |  |  |  | C-HS-SKL:07/16 > NY:07/16 | C-HS-NY:07/26 > SKL:07/26
JAS | 25-0098 |  | FSO | FSO | Pest Control Year 2025 Mob 3 | Petrofac | Johnson | 1 | 2025-07-17 | 2025-07-18 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:07/17 > JAS:07/17 | C-HN-JAS:07/19 > UTP:07/19
JAS | 25-0151 |  | FSO | FSO | Replace Provsion Crane Boom Tip -ABS | Petrofac | ABS | 1 | 2025-07-17 | 2025-07-20 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:07/17 > JAS:07/17 | C-HN-JAS:07/21 > UTP:07/21
JAS | 25-0199 |  | FSO | FSO | Replace Provsion Crane Boom Tip -Operation & Integrity Enginee Visit | Petrofac | Petrofac | 1 | 2025-07-17 | 2025-07-20 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:07/17 > JAS:07/17 | C-HN-JAS:07/21 > UTP:07/21
G1 | 25-0216 |  |  | OPS | [SD] Operation extra manpower (EIO + MECH ) | Puwat | VE | 4 | 2025-07-19 | 2025-07-25 | 7 | N-FT | N-OUT | N-IN
G1 | 25-0258 |  | WPP-A | BFT | [BFT] SD MN131 Manora debottleneck ABB #1 | Wason | ABB | 2 | 2025-07-20 | 2025-07-26 | 7 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-GY-JAS:07/27 > MNA:07/27 > STH:07/28
G1 | 25-0007 |  | WPP-A | BFT | [BFT] POST SD MN131 Manora debottleneck GEBH & Schneider | Wason | Baker /Schneider | 4 | 2025-07-20 | 2025-07-29 | 10 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20
G1 | 25-0062 |  | WPP-A | AIM | [SD] PSV rectification (Night shift) / SDV passing rate testing and Valve Greasing | Atthapong | Systech | 8 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0173 |  | WPP | MNT | [SD] ICSS ANNUAL PM 2025#1 and DCS operator workstation upgrade | Warakorn | Yokogawa | 1 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0179 |  | WPP | MNT | [SD] LV-MV Switchgear PM (3 year PM) | Ohmmanas | VE+ABB+MARC | 7 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0180 |  | WPP | MNT | [SD] MV Transformer PM | Ohmmanas | MARC | 3 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0208 |  | WPP | MNT | [SD] VSD PM | Suwitcha | BHGE | 3 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0210 |  | WPP | WSV | Well Service (Valves Greasing and BV Test) | Atisuda | Well Service | 6 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0239 |  | WPP-A | AIM | [SD] Tantawan extra crews to support operations for hydrocyclone cleaning | Atthapong | TBC | 4 | 2025-07-20 | 2025-07-25 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0172 |  | FSO | FSO | Extra Manpower for shutdown works | OMNI | OMNI | 5 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0174 |  | WPP | MNT | [SD] ICSS ANNUAL PM 2025#2 (Warakorn+Ohmmanas) | Warakorn | VE | 2 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN | C-HN-UTP:07/21 > MNA:07/21 | C-HN-MNA:07/26 > UTP:07/26
G1 | 25-0209 |  | WPP | OPS | OM + Shutdown Co. | Puwat | VE | 2 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN |  | C-HN-MNA:07/26 > UTP:07/26 | mob special flight on 21 Jul 25
G1 | 25-0215 |  |  | OPS | [SD] Operation extra manpower Safety Eng | Puwat | VE | 1 | 2025-07-21 | 2025-07-25 | 5 | N-FT | N-OUT | N-IN
G10 | 25-0237 | 1039 | MOPU | BFT | [BFT] WAS083 Generator #5 Replacement + Test Separator upgrade | Somkiat | TNS+Expert+VE Supt. | 27 | 2025-08-06 | 2025-08-27 | 22 | S-FT | S-OUT | S-IN | V-GX-SKL:08/05 > WN:08/06 | V-UV-NY:08/28 > SKL:08/29
JAS | 25-0081 |  | ALL PF | AIM | WPC: LARS Sea-fastening installation [TNS + AI Sup] | Pradit | TNS / AI Sup | 9 | 2025-07-18 | 2025-08-10 | 24 | N-FT | N-OUT | N-IN | V-AT-STH:07/17 > JAS:07/18 | V-GY-JAS:08/11 > STH:08/12
JAS | 25-0093 |  | FSO | FSO | Boiler No. 1 Tubing Replacement - Mob 2 | Petrofac | Altamar | 14 | 2025-07-27 | 2025-08-17 | 22 | N-FT | N-OUT | N-IN | V-G5-STH:07/26 > JAS:07/27 | V-NT-JAS:08/18 > MNA:08/18 > JAS:08/21 | next demob MNA-STH on 18 Aug
JAS | 25-0109 |  | FSO | FSO | Overhaul No.1 & No. 2 Stripping Pump | Petrofac | Altamar | 4 | 2025-07-21 | 2025-08-17 | 28 | N-FT | N-OUT | N-IN | C-HN-UTP:07/21 > JAS:07/21 | V-NT-JAS:08/18 > MNA:08/18 > JAS:08/21 | change mob from 23 jul to 26 jul
G11 | 25-0260 |  | NYC | BFT | [BFT] NY171 NYC additional wells - MV Termination DH | Wason | Baker H | 2 | 2025-07-26 | 2025-07-28 | 3 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > NY:07/26 | V-SM-NY:07/29 > WN:07/29 > SKL:07/30
G11 | 25-0015 |  | NYC | BFT | [BFT] NY171 NYC additional wells-Hookup | Somkiat | TNS+VE Supt. | 15 | 2025-07-26 | 2025-08-11 | 17 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > NY:07/26 | V-UV-NY:08/12 > SKL:08/13
G11 | 25-0158 | 1105 | NY | MNT | WPP-B Crane luffing cylinder replacement | Ekawit | TOS | 6 | 2025-07-26 | 2025-08-05 | 11 | S-FT | S-OUT | S-IN | V-SM-SKL:07/25 > NY:07/26 | V-SM-WN:08/06 > NY:08/06 > SKL:08/07 | TBC
JAS | 25-0078 | 396 |  | WSV | BV test and valve greasing : WPC/WPA/WPB/BYA | Asadawut | Well Service | 5 | 2025-08-14 | 2025-10-07 | 55 | N-FT | N-OUT | N-IN
JAS | 25-0129 |  | FSO | OFF | Offtake JC-686 | Benjachai |  | 3 | 2025-07-29 | 2025-08-02 | 5 | N-FT | N-OUT | N-IN
G11 | 25-0243 |  | NYC | BFT | [BFT] NY171 NYC additional wells mob 3-2 insulation | Somkiat | TNS | 4 | 2025-07-29 | 2025-08-11 | 14 | S-FT | S-OUT | S-IN | V-UV-SKL:07/28 > NY:07/29 | V-UV-NY:08/12 > SKL:08/13
JAS | 25-0082 |  | WPC | AIM | WPC: Air Surface Diving [OC-21 + 1VE] | Pradit | Ocean-21 / VE | 14 | 2025-07-30 | 2025-08-10 | 12 | N-FT | N-OUT | N-IN | V-GY-STH:07/29 > JAS:07/30 | V-GY-JAS:08/11 > STH:08/12
JAS | 25-0097 |  | FSO | FSO | Erect Scaffolding for Boiler No. 1 Tubing Replacement - Mob 2 | Petrofac | EMC | 4 | 2025-07-30 | 2025-08-04 | 6 | N-FT | N-OUT | N-IN | V-GY-STH:07/29 > JAS:07/30 | V-NT-JAS:08/05 > STH:08/06 | plan in aug
JAS | 25-0160 |  | WPD | BFT | [BFT] JM336 VSD Replacement | Somkiat | Experteam | 12 | 2025-08-08 | 2025-08-29 | 22 | N-FT | N-OUT | N-IN | V-NT-STH:08/07 > JAS:08/08 | V-GY-JAS:08/30 > STH:08/31
JAS | 25-0162 |  | WPC | BFT | [BFT] JM351 Deck drain, JM356 seperate diesel line Gen B5 B6, JM359 boatlanding fence | Somkiat | Experteam+VE Supv | 17 | 2025-08-08 | 2025-09-01 | 25 | N-FT | N-OUT | N-IN | V-NT-STH:08/07 > JAS:08/08 | V-NT-JAS:09/02 > STH:09/03
G11 | 25-0189 |  | ALL PF | ITM | NON - 2nd DT PM and Replacement Battery UPS at Tanker | Pichit | LBS | 1 | 2025-07-30 | 2025-08-15 | 17 | S-FT | S-OUT | S-IN | C-HS-SKL:07/30 > NY:07/30 | C-HS-NY:08/16 > SKL:08/16
JAS | 25-0167 |  |  | WSV | CTU : JSD#42 & BYA#30 zone change | Asadawut | Well Service | 15 | 2025-08-11 | 2025-09-04 | 25 | N-FT | N-OUT | N-IN
G1 | 25-0261 |  |  | FSO | Annual elevator servicing/replacement of elevator wire | OMNI |  | 1 | 2025-08-02 | 2025-08-04 | 3 | N-FT | N-OUT | N-IN
G11 | 25-0190 |  | ALL PF | ITM | NON-2nd VSAT PM, Radio PM and Replacement new equipment | Pichit | Infonet+UMT | 4 | 2025-08-03 | 2025-08-05 | 3 | S-FT | S-OUT | S-IN | V-SM-SKL:08/02 > NY:08/03 > WN:08/03 | V-SM-WN:08/06 > NY:08/06 > SKL:08/07
JAS | 25-0095 |  | FSO | FSO | Dexon NDT : Boiler No. 1 Tubing Replacement -Mob 2 | Petrofac | Dexon | 2 | 2025-08-04 | 2025-08-10 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:08/04 > JAS:08/04 | C-HN-JAS:08/11 > UTP:08/11 | Demob Jas by chopper on 04 Aug
G11 | 25-0262 |  | ALL PF | ITM | NON-Server LCM at WPPA | Pichit | VE | 1 | 2025-08-06 | 2025-08-15 | 10 | S-FT | S-OUT | S-IN | C-HS-SKL:08/06 > NY:08/06 | C-HS-NY:08/16 > SKL:08/16
JAS | 25-0201 |  | FSO | FSO | Boiler No. 1 Tubing Replacement -Operation & Integrity Enginee Visit | Petrofac | Petrofac | 1 | 2025-08-09 | 2025-08-10 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/09 > JAS:08/09 | C-HN-JAS:08/11 > UTP:08/11
G11 | 25-0046 |  | FSO | HSSE | 2025 Workplace monitoring-G11 | Narumol | SGS | 2 | 2025-08-13 | 2025-08-20 | 8 | S-FT | S-OUT | S-IN |  |  | mob from G11 to G11 NYC by vessel
JAS | 25-0110 |  | FSO | FSO | Boiler No. 1 Tubing Replacement - Chemical Cleaning Boiler after re-tube. | Petrofac | TBC | 4 | 2025-08-14 | 2025-08-22 | 9 | N-FT | N-OUT | N-IN | V-GY-STH:08/13 > JAS:08/14 | V-NT-JAS:08/23 > STH:08/24 | Mob/Demob on Aug-25
JAS | 25-0191 |  | FSO | OFF | Offtake JC-687 | Benjachai |  | 3 | 2025-08-14 | 2025-08-18 | 5 | N-FT | N-OUT | N-IN
JAS | 25-0200 |  | FSO | FSO | ABS Class Boiler No. 1 Tubing Replacement -Mob 3. (Commissioning) | Petrofac | ABS | 1 | 2025-08-14 | 2025-08-17 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:08/14 > JAS:08/14 | C-HN-JAS:08/18 > UTP:08/18
JAS | 25-0202 |  | FSO | FSO | Dismantle Scaffolding for Boiler No. 1 Tubing Replacement. | Petrofac | EMC | 4 | 2025-08-14 | 2025-08-22 | 9 | N-FT | N-OUT | N-IN | V-GY-STH:08/13 > JAS:08/14 | V-NT-JAS:08/23 > STH:08/24
JAS | 25-0204 |  | FSO | FSO | Conntrak Management Visit – (Q3 2025) | Petrofac | Contrak | 1 | 2025-08-14 | 2025-08-15 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/14 > JAS:08/14 | C-HN-JAS:08/16 > UTP:08/16
G11 | 25-0193 |  | FSO | OFF | Offtake NC-129 | Benjachai |  | 3 | 2025-08-15 | 2025-08-19 | 5 | S-FT | S-OUT | S-IN
G11 | 25-0047 |  | NYC | HSSE | [HSSE] 2025 Workplace monitoring-G11 NYC | Narumol | SGS | 2 | 2025-08-21 | 2025-08-26 | 6 | S-FT | S-OUT | S-IN
JAS | 25-0168 |  |  | WSV | CTU : BYA#18 Scale clean out & JSA#37ST Sand clean out | Asadawut | Well Service | 18 | 2025-09-04 | 2025-09-16 | 13 | N-FT | N-OUT | N-IN
G10 | 25-0187 |  | MOPU | ITM | WAS - 2nd DT PM | Pichit | LBS | 1 | 2025-08-22 | 2025-08-28 | 7 | S-FT | S-OUT | S-IN | C-HS-SKL:08/22 > WN:08/22 | C-HS-WN:08/29 > SKL:08/29
G10 | 25-0195 |  | MOPU | ITM | WAS - 2nd Radio PM and Replacement new equipment | Pichit | UMT | 2 | 2025-08-22 | 2025-08-26 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:08/22 > WN:08/22 | C-HS-WN:08/27 > SKL:08/27
JAS | 25-0192 |  | FSO | OFF | Offtake JC-688 | Benjachai |  | 3 | 2025-08-26 | 2025-08-30 | 5 | N-FT | N-OUT | N-IN
G10 | 25-0194 |  | FSO | OFF | Offtake WC-048 | Benjachai |  | 3 | 2025-08-26 | 2025-09-01 | 7 | S-FT | S-OUT | S-IN
G10 | 25-0045 |  | MOPU | HSSE | 2025 Workplace monitoring-G10 | Narumol | SGS | 2 | 2025-08-27 | 2025-09-02 | 7 | S-FT | S-OUT | S-IN
G10 | 25-0188 |  | MOPU | ITM | WAS - 2nd VSAT PM | Pichit | Infonet | 2 | 2025-08-27 | 2025-08-28 | 2 | S-FT | S-OUT | S-IN | C-HS-SKL:08/27 > WN:08/27 | C-HS-WN:08/29 > SKL:08/29
G11 | 25-0181 |  | ALL PF | AIM | ILI - Inline Inspection NYB to NYA pipeline [ROSEN/AI Sup] | Mittrapa | ROSEN / AI Sup | 2 | 2025-12-27 | 2026-01-03 | 8 | S-FT | S-OUT | S-IN |  | V-SM-NY:08/31 > WN:08/31 > SKL:09/01 | Project defered
G11 | 25-0182 |  | ALL PF | AIM | ILI - Inline Inspection team support [TNS] | Mittrapa | TNS | 8 | 2025-12-27 | 2026-01-03 | 8 | S-FT | S-OUT | S-IN |  |  | Project defered
JAS | 25-0205 |  | FSO | FSO | Petrofac OM visit (Q3 2025) | Petrofac | Petrofac | 1 | 2025-08-28 | 2025-08-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/28 > JAS:08/28 | C-HN-JAS:08/30 > UTP:08/30
JAS | 25-0206 |  | FSO | FSO | Petrofac HSEQ Advisor visit (Q3 2025) | Petrofac | Petrofac | 1 | 2025-08-28 | 2025-08-29 | 2 | N-FT | N-OUT | N-IN | C-HN-UTP:08/28 > JAS:08/28 | C-HN-JAS:08/30 > UTP:08/30
G11 | 25-0263 |  | NYB | BFT | [BFT] NY171 NYB Rig Protection & flowline removal / Modification | Somkiat | Experteam | 7 | 2025-08-03 | 2025-08-11 | 9 | S-FT | S-OUT | S-IN | V-SM-SKL:08/02 > NY:08/03 > WN:08/03 | V-UV-NY:08/12 > SKL:08/13
G11 | 25-0264 |  | NYB | BFT | [BFT] NY171 NYB Wells Hookup & Downhole Sensor Installation mob 1 | Somkiat | Experteam | 15 | 2025-08-31 | 2025-09-17 | 18 | S-FT | S-OUT | S-IN | V-UV-SKL:08/30 > NY:08/31 | V-SM-NY:09/18 > WN:09/18 > SKL:09/19
G11 | 25-0265 |  | NYB | BFT | [BFT] NY171 NYB Wells Hookup & Downhole Sensor Installation mob 2 | Somkiat | Experteam | 15 | 2025-09-25 | 2025-10-15 | 21 | S-FT | S-OUT | S-IN | V-GX-SKL:09/24 > WN:09/25
G11 | 25-0219 |  | NYC | BFT | [BFT] NYC MOC + Punch list + NY175 VSD room piping | Somkiat | Tantawan+VE | 25 | 2025-09-05 | 2025-09-24 | 20 | S-FT | S-OUT | S-IN | V-SM-SKL:09/04 > NY:09/05 > WN:09/05 | V-SM-WN:09/25 > NY:09/25 > SKL:09/26
G11 | 25-0071 |  | NYC | AIM | [AIM] TSI: Topside Inspection [Dexon] | Atthapong | DEXON | 4 | 2025-09-07 | 2025-09-28 | 22 | S-FT | S-OUT | S-IN
G1 | 25-0266 |  | FSO | ITM | MAN - RigNet VSAT decommisionning | Pichit | RigNet | 2 | 2025-09-08 | 2025-09-12 | 5 | N-FT | N-OUT | N-IN
G1 | 25-0169 |  |  | WSV | BV test and valve greasing : MNA | Asadawut | Well Service | 5 | 2025-09-30 | 2025-10-14 | 15 | N-FT | N-OUT | N-IN
JAS | 25-0267 |  | ALL PF | ITM | JAS - Server LCM at PPB2 | Pichit | VE+LBS | 2 | 2025-09-25 | 2025-10-01 | 7 | N-FT | N-OUT | N-IN
G11 | 25-0135 |  |  | WSV | NYA-34H: Well Integrity, Investigation for ESP packer / GVV leak | Asadawut | Well Service | 5 | 2025-10-15 | 2025-10-17 | 3 | S-FT | S-OUT | S-IN
JAS | 25-0268 |  | ALL PF | AIM | TSI: Topside Inspection [Dexon] | Pradit | DEXON | 2 | 2025-09-18 | 2025-10-15 | 28 | N-FT | N-OUT | N-IN | V-GY-STH:09/17 > JAS:09/18
JAS | 25-0040 |  | FSO | FSO | Replace Provsion Crane Boom Tip- TOS and 6M Crane proof load test - Thai law | Petrofac | TOS | 4 | 2025-07-10 | 2025-07-25 | 16 | N-FT | N-OUT | N-IN | V-AT-STH:07/09 > JAS:07/10 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
JAS | 25-0087 | 880, 986 | FSO | FSO | Boiler No. 1 Tubing Replacement - Mob 1/RO Unit Installation/COP Spool Replace | Petrofac | Altamar | 16 | 2025-06-14 | 2025-07-09 | 26 | N-FT | N-OUT | N-IN | V-AT-STH:06/13 > MNA:06/13 > JAS:06/14 | V-GY-JAS:07/10 > STH:07/11
JAS | 25-0245 | 1178 | WPB | BFT | [BFT] Repair HPWD flowline WPB | Somkiat | Experteam | 11 | 2025-06-25 | 2025-07-01 | 7 | N-FT | N-OUT | N-IN | V-AT-STH:06/24 > JAS:06/25 | V-GY-JAS:07/02 > STH:07/03
JAS | 25-0229 |  | PPB2 | BFT | [BFT] JM319 Wobbe index + GTG + Repair HPWD (VE Sup Anan) | Somkiat | VE | 1 | 2025-06-11 | 2025-07-01 | 21 | N-FT | N-OUT | N-IN | V-G5-STH:06/11 > JAS:06/11 | V-GY-JAS:07/02 > STH:07/03
JAS | 25-0147 | 890 | FSO | FSO | Erect Scaffolding for Boiler No. 1 Tubing Replacement - Mob 1/Group2. | Petrofac | EMC | 2 | 2025-06-14 | 2025-07-09 | 26 | N-FT | N-OUT | N-IN | V-AT-STH:06/13 > MNA:06/13 > JAS:06/14 | V-GY-JAS:07/10 > STH:07/11
G10 | 25-0269 | 1083 |  | MNT | VSD tech to go to WAS to support BF installation of newly rental VSD | Suwitcha | BHGE | 1 | 2025-06-27 | 2025-07-01 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:06/27 > WN:06/27 | C-HS-WN:07/02 > SKL:07/02
G10 | 25-0270 | 1148 |  | MNT | Support ICSS programming for WAS051 -VSD-17 Interface at Wassana MOPU | Woraphon | IO | 1 | 2025-06-27 | 2025-07-01 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:06/27 > WN:06/27 | C-HS-WN:07/02 > SKL:07/02
G10 | 25-0247 | 1122 | MOPU | AIM | Wassana Hydro-cyclone cleaning | Atthapong | CR | 4 | 2025-07-04 | 2025-07-13 | 10 | S-FT | S-OUT | S-IN | V-SM-SKL:07/03 > WN:07/04 | V-GX-WN:07/14 > SKL:07/15
JAS | 25-0271 |  | FSO | FSO | Cargo Oil Tank 1C, 1P, and 1S - Intermediate ABS Survey (Tank Cleaning) -Mob1 | Petrofac | TINDY | 11 | 2025-08-21 | 2025-09-14 | 25 | N-FT | N-OUT | N-IN | V-NT-JAS:08/18 > MNA:08/18 > JAS:08/21 | V-GY-JAS:09/15 > STH:09/16
JAS | 25-0272 |  | FSO | FSO | Replace Provision Crane Boom Tip -Dexon NDT | Petrofac | DEXON | 1 | 2025-07-14 | 2025-07-16 | 3 | N-FT | N-OUT | N-IN | C-HN-UTP:07/14 > JAS:07/14 | C-HN-JAS:07/17 > UTP:07/17
JAS | 25-0273 |  |  | WSV | JAS C-39/B-16/B-05/B-42/BYA-35ST1/A-15 Slickline | Asadawut | Well Service | 8 | 2025-07-30 | 2025-08-10 | 12 | N-FT | N-OUT | N-IN |  | V-GY-JAS:08/11 > STH:08/12
G1 | 25-0274 |  |  | WSV | MNA-21i wireline | Asadawut | Well Service | 10 | 2025-09-23 | 2025-09-30 | 8 | N-FT | N-OUT | N-IN
JAS | 25-0275 |  | FSO | FSO | Overhaul No.1 & No. 2 Stripping Pump ( and Boiler No. 1 Tubing Replacement - Mob 2.) | Petrofac | Altamar | 1 | 2025-07-19 | 2025-08-13 | 26 | N-FT | N-OUT | N-IN | C-HN-UTP:07/19 > JAS:07/19 | C-HN-JAS:08/14 > UTP:08/14
JAS | 25-0276 |  | FSO | FSO | Intermediate ABS Survey Mob 2. | Petrofac | ABS | 1 | 2025-09-25 | 2025-09-28 | 4 | N-FT | N-OUT | N-IN | C-HN-UTP:09/25 > JAS:09/25 | C-HN-JAS:09/29 > UTP:09/29
JAS | 25-0277 |  | FSO | FSO | Intermediate Class Survey Mob 1. / Annual Survey | Petrofac | ABS | 1 | 2025-09-08 | 2025-09-10 | 3 | N-FT | N-OUT | N-IN | C-HN-UTP:09/08 > JAS:09/08 | C-HN-JAS:09/11 > UTP:09/11
JAS | 25-0278 |  | FSO | FSO | Annual Critical Area Inspection for Topside & Flare Tower Interface - outstanding from Baseline | Petrofac | DEXON | 1 | 2025-09-08 | 2025-09-10 | 3 | N-FT | N-OUT | N-IN | C-HN-UTP:09/08 > JAS:09/08 | C-HN-JAS:09/11 > UTP:09/11
JAS | 25-0279 |  |  | FSO | Cargo Oil Tank 1C, 1P, and 1S and 4P- Intermediate ABS Survey (Tank Cleaning) -Mob2 | Petrofac | TINDY | 18 | 2025-09-18 | 2025-09-30 | 13 | N-FT | N-OUT | N-IN | V-GY-STH:09/17 > JAS:09/18
JAS | 25-0280 |  | FSO | OFF | Offtake JC-689 | Benjachai |  | 3 | 2025-09-08 | 2025-09-12 | 5 | N-FT | N-OUT | N-IN
JAS | 25-0281 |  | FSO | OFF | Offtake JC-690 | Benjachai |  | 3 | 2025-09-21 | 2025-09-25 | 5 | N-FT | N-OUT | N-IN
G1 | 25-0282 |  | FSO | OFF | Offtake MC-134 | Benjachai |  | 3 | 2025-09-26 | 2025-09-30 | 5 | N-FT | N-OUT | N-IN
G11 | 25-0283 |  | FSO | OFF | Offtake NC-130 | Benjachai |  | 3 | 2025-09-11 | 2025-09-15 | 5 | S-FT | S-OUT | S-IN
G1 | 25-0284 |  |  | BFT | [BFT] SD MN131 Manora debottleneck ABB #2 | Wason | ABB | 2 | 2025-07-14 | 2025-07-25 | 12 | N-FT | N-OUT | N-IN | V-TC-STH:07/14 > MNA:07/14 | V-G5-JAS:07/26 > MNA:07/26 > STH:07/26
G1 | 25-0285 |  |  | BFT | [BFT] SD MN131 Manora debottleneck Sulzer #1 | Wason | Sulzer | 2 | 2025-07-20 | 2025-07-29 | 10 | N-FT | N-OUT | N-IN | V-GY-STH:07/19 > MNA:07/20 | V-GY-JAS:07/27 > MNA:07/27 > STH:07/28
G1 | 25-0286 |  | WPP | MNT | MANORA Debottleneck DMC Load shedding configuration | Warakorn | Infinite | 2 | 2025-07-26 | 2025-08-01 | 7 | N-FT | N-OUT | N-IN | C-HN-UTP:07/26 > MNA:07/26 | C-HN-MNA:08/02 > UTP:08/02
JAS | 25-0287 |  | FSO | FSO | Cargo Oil Tank 1C, 1P, and 1S - Intermediate ABS Survey (Tank Cleaning) -Mob1 | Petrofac | TINDY | 7 | 2025-08-26 | 2025-09-14 | 20 | N-FT | N-OUT | N-IN | V-NT-STH:08/25 > JAS:08/26 | V-GY-JAS:09/15 > STH:09/16
G11 | 25-0288 |  | NYC | AIM | [AIM] NYC: Maintenance Painting [TCS + AI Sup] | Mittrapa | TCS / AI Sup | 19 | 2025-08-12 | 2025-08-30 | 19 | S-FT | S-OUT | S-IN | V-SM-SKL:08/11 > NY:08/12 | V-SM-NY:08/31 > WN:08/31 > SKL:09/01
JAS | 25-0289 |  | PPB2 | BFT | [BFT] JM319 GTG Commissioning | Wason | Pico , VE Eng , PCC , Solar , TNS , Expert , Enerproject | 13 | 2025-07-07 | 2025-07-17 | 11 | N-FT | N-OUT | N-IN | V-G5-STH:07/07 > JAS:07/07 | V-GY-JAS:07/18 > STH:07/19
G10 | 25-0290 |  |  | FSO | Management visit | Kritsana | Three60 | 2 | 2025-06-27 | 2025-07-01 | 5 | S-FT | S-OUT | S-IN | C-HS-SKL:06/27 > WN:06/27 | C-HS-WN:07/02 > SKL:07/02
G10 | 25-0291 |  |  | FSO | SEACOM audit | Kritsana | SEACOM | 1 | 2025-07-30 | 2025-07-31 | 2 | S-FT | S-OUT | S-IN | C-HS-SKL:07/30 > WN:07/30 | C-HS-WN:08/01 > SKL:08/01
G10 | 25-0293 |  | MOPU | AIM | MOPU UWILD + Inspection for Life Extension [Dexon] | Mittrapa | DEXON | 3 | 2025-08-23 | 2025-08-30 | 8 | S-FT | S-OUT | S-IN | V-GX-SKL:08/22 > WN:08/23 | V-SM-NY:08/31 > WN:08/31 > SKL:09/01
G10 | 25-0294 |  | MOPU | AIM | MOPU UWILD + Life Extension [BV+Egg] | Mittrapa | BV / VE | 2 | 2025-08-23 | 2025-08-30 | 8 | S-FT | S-OUT | S-IN | V-GX-SKL:08/22 > WN:08/23 | V-SM-NY:08/31 > WN:08/31 > SKL:09/01
G10 | 25-0295 |  | MOPU | MNT | WSA-20 startup | Suwitcha | BHGE | 1 | 2025-07-23 | 2025-07-29 | 7 | S-FT | S-OUT | S-IN
G11 | 25-0296 |  | NYC | HSSE | [HSSE] Lifeboat repair & wire rope replacement, and inspection CO2 system | Thanagon | MSC | 3 | 2025-08-03 | 2025-08-18 | 16 | S-FT | S-OUT | S-IN | V-SM-SKL:08/02 > NY:08/03 > WN:08/03 | V-SM-NY:08/19 > WN:08/19 | back to SKL by GX mob on 20 Aug
G10 | 25-0248 | 1227 | WSA | MNT | Chloride UPS Apodys 1 - Alarm time out checking | Ohmmanas | WEA-ASIA | 1 | 2025-07-02 | 2025-07-03 | 2 | S-FT | S-OUT | S-IN | C-HS-SKL:07/02 > WN:07/02 | C-HS-WN:07/04 > SKL:07/04
G1 | 25-0297 |  | FSO | OFF | Offtake MC-133#2 (DMF) | Benjachai | DMF | 1 | 2025-07-15 | 2025-07-15 | 1
G10 | 25-0298 |  | MOPU | OPS | Management visit | Tanarat | VE | 11 | 2025-08-13 | 2025-08-13 | 1 | S-FT | S-OUT | S-IN |  |  | Special flight
G11 | 25-0299 |  |  | OPS | Management visit | Chutarat | VE | 11 | 2025-08-14 | 2025-08-14 | 1 | S-FT | S-OUT | S-IN

## Boat_Plan
Type | Boat_Name | Direction | Origin | Destination | DEP. Date | DEP. Time | ARR Date | ARR Time | MAX SEAT | Regular Crew | BOOK SEAT | AVAILABLE SEAT | Code | Trip ID
VESSEL | SUMMER | IN | WN | SKL | 2025-07-01 | 7 | 2025-07-01 | 12 | 27 |  | 0 | 27 | S-IN | V-SM-WN:07/01 > SKL:07/01
VESSEL | SUMMER | FT | NY | SKL | 2025-07-01 | 17 | 2025-07-02 | 7 | 27 |  | 0 | 27 | S-FT | V-SM-NY:07/01 > SKL:07/02
VESSEL | GLORY5 | IN | JAS | STH | 2025-07-01 | 21 | 2025-07-02 | 5 | 80 |  | 0 | 80 | N-IN | V-G5-JAS:07/01 > STH:07/02
VESSEL | GLORY5 | OUT | STH | MNA | 2025-07-02 | 7 | 2025-07-02 | 11 | 80 |  | 0 | 80 | N-OUT | V-G5-STH:07/02 > MNA:07/02
VESSEL | GLORY5 | FT | MNA | JAS | 2025-07-02 | 12 | 2025-07-02 | 16 | 80 |  | 0 | 80 | N-FT | V-G5-MNA:07/02 > JAS:07/02
VESSEL | GANYA | IN | JAS | STH | 2025-07-02 | 18 | 2025-07-03 | 6 | 43 |  | 33 | 10 | N-IN | V-GY-JAS:07/02 > STH:07/03
VESSEL | GANYA | OUT | STH | JAS | 2025-07-04 | 18 | 2025-07-05 | 6 | 43 |  | 15 | 28 | N-OUT | V-GY-STH:07/04 > JAS:07/05
VESSEL | GLORY5 | IN | JAS | STH | 2025-07-05 | 8 | 2025-07-05 | 16 | 90 |  | 0 | 90 | N-IN | V-G5-JAS:07/05 > STH:07/05
VESSEL | SUMMER | OUT | SKL | WN | 2025-07-03 | 18 | 2025-07-04 | 7 | 27 |  | 7 | 20 | S-OUT | V-SM-SKL:07/03 > WN:07/04
VESSEL | UNIVERSE | IN | NY | WN | 2025-07-06 | 13 | 2025-07-06 | 17 | 27 |  | 0 | 27 | S-IN | V-UV-NY:07/06 > WN:07/06
VESSEL | UNIVERSE | IN | WN | SKL | 2025-07-06 | 18 | 2025-07-07 | 7 | 27 |  | 0 | 27 | S-IN | V-UV-WN:07/06 > SKL:07/07
VESSEL | GLORY5 | OUT | STH | JAS | 2025-07-07 | 8 | 2025-07-07 | 16 | 90 |  | 17 | 73 | N-OUT | V-G5-STH:07/07 > JAS:07/07
VESSEL | ATHENA | IN | JAS | STH | 2025-07-07 | 18 | 2025-07-08 | 6 | 24 |  | 0 | 24 | N-IN | V-AT-JAS:07/07 > STH:07/08
VESSEL | UNIVERSE | OUT | SKL | NY | 2025-07-08 | 17 | 2025-07-09 | 7 | 27 |  | 8 | 19 | S-OUT | V-UV-SKL:07/08 > NY:07/09
VESSEL | GALAXY | FT | WN | NY | 2025-07-06 | 12 | 2025-07-06 | 17 | 33 |  | 0 | 33 | S-FT | V-GX-WN:07/06 > NY:07/06
VESSEL | GALAXY | FT | NY | WN | 2025-07-09 | 7 | 2025-07-09 | 12 | 33 |  | 0 | 33 | S-FT | V-GX-NY:07/09 > WN:07/09
VESSEL | ATHENA | OUT | STH | JAS | 2025-07-09 | 18 | 2025-07-10 | 6 | 24 |  | 4 | 20 | N-OUT | V-AT-STH:07/09 > JAS:07/10
VESSEL | GANYA | IN | JAS | STH | 2025-07-10 | 18 | 2025-07-11 | 6 | 43 |  | 18 | 25 | N-IN | V-GY-JAS:07/10 > STH:07/11
VESSEL | GANYA | OUT | STH | MNA | 2025-07-11 | 20 | 2025-07-12 | 4 | 43 |  | 0 | 43 | N-OUT | V-GY-STH:07/11 > MNA:07/12
VESSEL | GANYA | FT | MNA | JAS | 2025-07-12 | 7 | 2025-07-12 | 15 | 43 |  | 0 | 43 | N-FT | V-GY-MNA:07/12 > JAS:07/12
VESSEL | ATHENA | FT | JAS | MNA | 2025-07-12 | 18 | 2025-07-13 | 2 | 24 |  | 0 | 24 | N-FT | V-AT-JAS:07/12 > MNA:07/13
VESSEL | NEPTUNE | IN | MNA | STH | 2025-07-13 | 2 | 2025-07-13 | 10 | 27 |  | 0 | 27 | N-IN | V-TC-MNA:07/13 > STH:07/13
VESSEL | SUMMER | IN | WN | SKL | 2025-07-11 | 18 | 2025-07-12 | 6 | 27 |  | 0 | 27 | S-IN | V-SM-WN:07/11 > SKL:07/12
VESSEL | NEPTUNE | OUT | STH | MNA | 2025-07-14 | 9 | 2025-07-14 | 17 | 27 |  | 12 | 15 | N-OUT | V-TC-STH:07/14 > MNA:07/14
VESSEL | SUMMER | OUT | SKL | WN | 2025-07-12 | 18 | 2025-07-13 | 6 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:07/12 > WN:07/13
VESSEL | GANYA | IN | JAS | STH | 2025-07-18 | 18 | 2025-07-19 | 6 | 43 |  | 24 | 19 | N-IN | V-GY-JAS:07/18 > STH:07/19
VESSEL | GANYA | OUT | STH | MNA | 2025-07-19 | 21 | 2025-07-20 | 6 | 43 |  | 45 | -2 | N-OUT | V-GY-STH:07/19 > MNA:07/20
VESSEL | GALAXY | IN | WN | SKL | 2025-07-14 | 18 | 2025-07-15 | 6 | 33 |  | 7 | 26 | S-IN | V-GX-WN:07/14 > SKL:07/15
VESSEL | GALAXY | OUT | SKL | NY | 2025-07-15 | 18 | 2025-07-16 | 7 | 33 |  | 15 | 18 | S-OUT | V-GX-SKL:07/15 > NY:07/16
VESSEL | GALAXY | IN | NY | WN | 2025-07-20 | 7 | 2025-07-20 | 11 | 33 |  | 0 | 33 | S-IN | V-GX-NY:07/20 > WN:07/20
VESSEL | GALAXY |  | WN | SKL | 2025-07-20 | 17 | 2025-07-21 | 6 | 33 |  | 0 | 33 | FALSE | V-GX-WN:07/20 > SKL:07/21
VESSEL | GALAXY | OUT | SKL | WN | 2025-07-22 | 17 | 2025-07-23 | 6 | 33 |  | 0 | 33 | S-OUT | V-GX-SKL:07/22 > WN:07/23
VESSEL | SUMMER | IN | WN | NY | 2025-07-23 | 8 | 2025-07-23 | 13 | 27 |  | 0 | 27 | S-IN | V-SM-WN:07/23 > NY:07/23
VESSEL | SUMMER |  | NY | SKL | 2025-07-23 | 17 | 2025-07-24 | 7 | 27 |  | 0 | 27 | FALSE | V-SM-NY:07/23 > SKL:07/24
VESSEL | NATA | IN | MNA | STH | 2025-06-30 | 1 | 2025-06-30 | 10 | 43 |  | 0 | 43 | N-IN | V-NT-MNA:06/30 > STH:06/30
VESSEL | NATA | OUT | STH | WN | 2025-06-30 | 23 | 2025-07-02 | 19 | 43 |  | 0 | 43 | S-OUT | V-NT-STH:06/30 > WN:07/02
VESSEL | NATA | OUT | STH | JAS | 2025-07-30 | 18 | 2025-07-31 | 6 | 43 |  | 0 | 43 | N-OUT | V-NT-STH:07/30 > JAS:07/31
VESSEL | ATHENA | IN | MNA | STH | 2025-07-16 | 20 | 2025-07-17 | 6 | 24 |  | 0 | 24 | N-IN | V-AT-MNA:07/16 > STH:07/17
VESSEL | ATHENA | OUT | STH | JAS | 2025-07-17 | 17 | 2025-07-18 | 6 | 24 |  | 9 | 15 | N-OUT | V-AT-STH:07/17 > JAS:07/18
VESSEL | ATHENA | IN | JAS | SKL | 2025-07-31 | 10 | 2025-08-02 | 6 | 24 |  | 0 | 24 | N-IN | V-AT-JAS:07/31 > SKL:08/02
VESSEL | SUMMER | OUT | SKL | NY | 2025-07-25 | 17 | 2025-07-26 | 8 | 27 |  | 24 | 3 | S-OUT | V-SM-SKL:07/25 > NY:07/26
VESSEL | GLORY5 | IN | JAS | MNA | 2025-07-26 | 8 | 2025-07-26 | 12 | 90 |  | 0 | 90 | N-IN | V-G5-JAS:07/26 > MNA:07/26
VESSEL | GLORY5 |  | MNA | STH | 2025-07-26 | 13 | 2025-07-26 | 17 | 90 |  | 0 | 90 | FALSE | V-G5-MNA:07/26 > STH:07/26
VESSEL | GLORY5 | OUT | STH | JAS | 2025-07-26 | 20 | 2025-07-27 | 5 | 90 |  | 26 | 64 | N-OUT | V-G5-STH:07/26 > JAS:07/27
VESSEL | UNIVERSE | IN | NY | SKL | 2025-07-26 | 17 | 2025-07-27 | 7 | 27 |  | 14 | 13 | S-IN | V-UV-NY:07/26 > SKL:07/27
VESSEL | GANYA | FT | MNA | JAS | 2025-07-26 | 8 | 2025-07-26 | 16 | 43 |  | 0 | 43 | N-FT | V-GY-MNA:07/26 > JAS:07/26
VESSEL | GANYA | IN | JAS | MNA | 2025-07-27 | 10 | 2025-07-27 | 17 | 43 |  | 0 | 43 | N-IN | V-GY-JAS:07/27 > MNA:07/27
VESSEL | GANYA |  | MNA | STH | 2025-07-27 | 21 | 2025-07-28 | 6 | 43 |  | 0 | 43 | FALSE | V-GY-MNA:07/27 > STH:07/28
VESSEL | UNIVERSE | OUT | SKL | NY | 2025-07-28 | 17 | 2025-07-29 | 7 | 27 |  | 4 | 23 | S-OUT | V-UV-SKL:07/28 > NY:07/29
VESSEL | GANYA | OUT | STH | JAS | 2025-07-29 | 18 | 2025-07-30 | 6 | 43 |  | 18 | 25 | N-OUT | V-GY-STH:07/29 > JAS:07/30
VESSEL | SUMMER | IN | NY | WN | 2025-07-29 | 7 | 2025-07-29 | 12 | 27 |  | 0 | 27 | S-IN | V-SM-NY:07/29 > WN:07/29
VESSEL | SUMMER |  | WN | SKL | 2025-07-29 | 17 | 2025-07-30 | 6 | 27 |  | 0 | 27 | FALSE | V-SM-WN:07/29 > SKL:07/30
VESSEL | NEPTUNE | IN | MNA | STH | 2025-08-02 | 20 | 2025-08-03 | 6 | 27 |  | 22 | 5 | N-IN | V-TC-MNA:08/02 > STH:08/03
VESSEL | NATA | FT | JAS | MNA | 2025-08-02 | 12 | 2025-08-02 | 20 | 43 |  | 0 | 43 | N-FT | V-NT-JAS:08/02 > MNA:08/02
VESSEL | NATA | FT | MNA | JAS | 2025-08-04 | 19 | 2025-08-05 | 3 | 43 |  | 0 | 43 | N-FT | V-NT-MNA:08/04 > JAS:08/05
VESSEL | SUMMER | OUT | SKL | NY | 2025-08-02 | 16 | 2025-08-03 | 6 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:08/02 > NY:08/03
VESSEL | SUMMER | FT | NY | WN | 2025-08-03 | 10 | 2025-08-03 | 15 | 27 |  | 0 | 27 | S-FT | V-SM-NY:08/03 > WN:08/03
VESSEL | GALAXY | IN | WN | SKL | 2025-08-03 | 18 | 2025-08-04 | 7 | 33 |  | 0 | 33 | S-IN | V-GX-WN:08/03 > SKL:08/04
VESSEL | NEPTUNE | OUT | STH | STH | 2025-08-04 | 9 | 2025-08-04 | 17 | 27 |  | 0 | 27 | FALSE | V-TC-STH:08/04 > STH:08/04
VESSEL | GALAXY | OUT | SKL | WN | 2025-08-05 | 18 | 2025-08-06 | 6 | 33 |  | 27 | 6 | S-OUT | V-GX-SKL:08/05 > WN:08/06
VESSEL | NATA | IN | JAS | STH | 2025-08-05 | 18 | 2025-08-06 | 6 | 43 |  | 4 | 39 | N-IN | V-NT-JAS:08/05 > STH:08/06
VESSEL | SUMMER | IN | WN | NY | 2025-08-06 | 7 | 2025-08-06 | 12 | 27 |  | 0 | 27 | S-IN | V-SM-WN:08/06 > NY:08/06
VESSEL | SUMMER |  | NY | SKL | 2025-08-06 | 17 | 2025-08-07 | 7 | 27 |  | 0 | 27 | FALSE | V-SM-NY:08/06 > SKL:08/07
VESSEL | NATA | OUT | STH | JAS | 2025-08-07 | 18 | 2025-08-08 | 6 | 43 |  | 29 | 14 | N-OUT | V-NT-STH:08/07 > JAS:08/08
VESSEL | GLORY5 | IN | JAS | STH | 2025-08-08 | 8 | 2025-08-08 | 16 | 90 |  | 0 | 90 | N-IN | V-G5-JAS:08/08 > STH:08/08
VESSEL | GLORY5 | OUT | STH | JAS | 2025-08-10 | 8 | 2025-08-10 | 16 | 90 |  | 0 | 90 | N-OUT | V-G5-STH:08/10 > JAS:08/10
VESSEL | GANYA | IN | JAS | STH | 2025-08-11 | 18 | 2025-08-12 | 6 | 43 |  | 31 | 12 | N-IN | V-GY-JAS:08/11 > STH:08/12
VESSEL | SUMMER | OUT | SKL | NY | 2025-08-11 | 17 | 2025-08-12 | 7 | 27 |  | 25 | 2 | S-OUT | V-SM-SKL:08/11 > NY:08/12
VESSEL | UNIVERSE | IN | NY | SKL | 2025-08-12 | 17 | 2025-08-13 | 7 | 27 |  | 27 | 0 | S-IN | V-UV-NY:08/12 > SKL:08/13
VESSEL | GANYA | OUT | STH | JAS | 2025-08-13 | 18 | 2025-08-14 | 6 | 43 |  | 8 | 35 | N-OUT | V-GY-STH:08/13 > JAS:08/14
VESSEL | UNIVERSE | OUT | SKL | NY | 2025-08-14 | 17 | 2025-08-15 | 7 | 27 |  | 0 | 27 | S-OUT | V-UV-SKL:08/14 > NY:08/15
VESSEL | NEPTUNE | IN | MNA | STH | 2025-08-18 | 20 | 2025-08-19 | 6 | 27 |  | 0 | 27 | N-IN | V-TC-MNA:08/18 > STH:08/19
VESSEL | NATA | FT | JAS | MNA | 2025-08-18 | 12 | 2025-08-18 | 20 | 43 |  | 0 | 43 | N-FT | V-NT-JAS:08/18 > MNA:08/18
VESSEL | NATA | FT | MNA | JAS | 2025-08-21 | 7 | 2025-08-21 | 15 | 43 |  | 0 | 43 | N-FT | V-NT-MNA:08/21 > JAS:08/21
VESSEL | SUMMER | FT | NY | WN | 2025-08-19 | 18 | 2025-08-19 | 23 | 27 |  | 9 | 18 | S-FT | V-SM-NY:08/19 > WN:08/19
VESSEL | GALAXY | IN | WN | SKL | 2025-08-20 | 8 | 2025-08-20 | 20 | 33 |  | 0 | 33 | S-IN | V-GX-WN:08/20 > SKL:08/20
VESSEL | NEPTUNE | OUT | STH | STH | 2025-08-20 | 20 | 2025-08-21 | 5 | 27 |  | 0 | 27 | FALSE | V-TC-STH:08/20 > STH:08/21
VESSEL | GALAXY | OUT | SKL | WN | 2025-08-22 | 17 | 2025-08-23 | 6 | 33 |  | 5 | 28 | S-OUT | V-GX-SKL:08/22 > WN:08/23
VESSEL | NATA | IN | JAS | STH | 2025-08-23 | 18 | 2025-08-24 | 6 | 43 |  | 8 | 35 | N-IN | V-NT-JAS:08/23 > STH:08/24
VESSEL | SUMMER | IN | WN | NY | 2025-08-23 | 7 | 2025-08-23 | 12 | 27 |  | 0 | 27 | S-IN | V-SM-WN:08/23 > NY:08/23
VESSEL | SUMMER |  | NY | SKL | 2025-08-23 | 17 | 2025-08-24 | 7 | 27 |  | 0 | 27 | FALSE | V-SM-NY:08/23 > SKL:08/24
VESSEL | NATA | OUT | STH | JAS | 2025-08-25 | 18 | 2025-08-26 | 6 | 43 |  | 7 | 36 | N-OUT | V-NT-STH:08/25 > JAS:08/26
VESSEL | SUMMER | OUT | SKL | NY | 2025-08-27 | 17 | 2025-08-28 | 7 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:08/27 > NY:08/28
VESSEL | UNIVERSE | IN | NY | SKL | 2025-08-28 | 17 | 2025-08-29 | 7 | 27 |  | 27 | 0 | S-IN | V-UV-NY:08/28 > SKL:08/29
VESSEL | GANYA | IN | JAS | STH | 2025-08-30 | 18 | 2025-08-31 | 6 | 43 |  | 12 | 31 | N-IN | V-GY-JAS:08/30 > STH:08/31
VESSEL | UNIVERSE | OUT | SKL | NY | 2025-08-30 | 17 | 2025-08-31 | 7 | 27 |  | 15 | 12 | S-OUT | V-UV-SKL:08/30 > NY:08/31
VESSEL | SUMMER | IN | NY | WN | 2025-08-31 | 8 | 2025-08-31 | 13 | 27 |  | 0 | 27 | S-IN | V-SM-NY:08/31 > WN:08/31
VESSEL | SUMMER |  | WN | SKL | 2025-08-31 | 17 | 2025-09-01 | 6 | 27 |  | 0 | 27 | FALSE | V-SM-WN:08/31 > SKL:09/01
VESSEL | GANYA | OUT | STH | MNA | 2025-09-01 | 18 | 2025-09-02 | 4 | 43 |  | 0 | 43 | N-OUT | V-GY-STH:09/01 > MNA:09/02
VESSEL | GANYA |  | MNA | JAS | 2025-09-02 | 6 | 2025-09-02 | 14 | 43 |  | 0 | 43 | FALSE | V-GY-MNA:09/02 > JAS:09/02
VESSEL | NATA | IN | JAS | STH | 2025-09-02 | 18 | 2025-09-03 | 7 | 43 |  | 17 | 26 | N-IN | V-NT-JAS:09/02 > STH:09/03
VESSEL | NATA | OUT | STH | JAS | 2025-09-04 | 18 | 2025-09-05 | 7 | 43 |  | 0 | 43 | N-OUT | V-NT-STH:09/04 > JAS:09/05
VESSEL | SUMMER | OUT | SKL | NY | 2025-09-04 | 16 | 2025-09-05 | 7 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:09/04 > NY:09/05
VESSEL | SUMMER | FT | NY | WN | 2025-09-05 | 10 | 2025-09-05 | 15 | 27 |  | 0 | 27 | S-FT | V-SM-NY:09/05 > WN:09/05
VESSEL | GANYA | FT | JAS | MNA | 2025-09-05 | 12 | 2025-09-05 | 20 | 43 |  | 0 | 43 | N-FT | V-GY-JAS:09/05 > MNA:09/05
VESSEL | GANYA |  | MNA | JAS | 2025-09-08 | 7 | 2025-09-08 | 15 | 43 |  | 0 | 43 | FALSE | V-GY-MNA:09/08 > JAS:09/08
VESSEL | NEPTUNE | IN | MNA | STH | 2025-09-05 | 20 | 2025-09-06 | 6 | 27 |  | 0 | 27 | N-IN | V-TC-MNA:09/05 > STH:09/06
VESSEL | GALAXY | IN | WN | SKL | 2025-09-05 | 18 | 2025-09-06 | 6 | 33 |  | 0 | 33 | S-IN | V-GX-WN:09/05 > SKL:09/06
VESSEL | NEPTUNE | OUT | STH | MNA | 2025-09-07 | 20 | 2025-09-08 | 6 | 27 |  | 0 | 27 | N-OUT | V-TC-STH:09/07 > MNA:09/08
VESSEL | GALAXY | OUT | SKL | WN | 2025-09-07 | 17 | 2025-09-08 | 6 | 33 |  | 0 | 33 | S-OUT | V-GX-SKL:09/07 > WN:09/08
VESSEL | SUMMER | IN | WN | NY | 2025-09-08 | 7 | 2025-09-08 | 12 | 27 |  | 0 | 27 | S-IN | V-SM-WN:09/08 > NY:09/08
VESSEL | SUMMER |  | NY | SKL | 2025-09-08 | 16 | 2025-09-09 | 7 | 27 |  | 0 | 27 | FALSE | V-SM-NY:09/08 > SKL:09/09
VESSEL | SUMMER | OUT | SKL | NY | 2025-09-10 | 16 | 2025-09-11 | 7 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:09/10 > NY:09/11
VESSEL | GLORY5 | IN | JAS | STH | 2025-09-12 | 8 | 2025-09-12 | 16 | 90 |  | 0 | 90 | N-IN | V-G5-JAS:09/12 > STH:09/12
VESSEL | GLORY5 | OUT | STH | JAS | 2025-09-14 | 8 | 2025-09-14 | 16 | 90 |  | 0 | 90 | N-OUT | V-G5-STH:09/14 > JAS:09/14
VESSEL | GANYA | IN | JAS | STH | 2025-09-15 | 18 | 2025-09-16 | 7 | 43 |  | 18 | 25 | N-IN | V-GY-JAS:09/15 > STH:09/16
VESSEL | UNIVERSE | IN | NY | SKL | 2025-09-15 | 17 | 2025-09-16 | 7 | 27 |  | 0 | 27 | S-IN | V-UV-NY:09/15 > SKL:09/16
VESSEL | GANYA | OUT | STH | JAS | 2025-09-17 | 18 | 2025-09-18 | 7 | 43 |  | 38 | 5 | N-OUT | V-GY-STH:09/17 > JAS:09/18
VESSEL | UNIVERSE | OUT | SKL | NY | 2025-09-17 | 16 | 2025-09-18 | 7 | 27 |  | 0 | 27 | S-OUT | V-UV-SKL:09/17 > NY:09/18
VESSEL | NATA | IN | JAS | STH | 2025-09-18 | 18 | 2025-09-19 | 7 | 43 |  | 0 | 43 | N-IN | V-NT-JAS:09/18 > STH:09/19
VESSEL | SUMMER | IN | NY | WN | 2025-09-18 | 9 | 2025-09-18 | 14 | 27 |  | 0 | 27 | S-IN | V-SM-NY:09/18 > WN:09/18
VESSEL | SUMMER |  | WN | SKL | 2025-09-18 | 18 | 2025-09-19 | 7 | 27 |  | 0 | 27 | FALSE | V-SM-WN:09/18 > SKL:09/19
VESSEL | NATA | OUT | STH | JAS | 2025-09-20 | 18 | 2025-09-21 | 7 | 43 |  | 0 | 43 | N-OUT | V-NT-STH:09/20 > JAS:09/21
VESSEL | SUMMER | OUT | SKL | NY | 2025-09-21 | 16 | 2025-09-22 | 7 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:09/21 > NY:09/22
VESSEL | SUMMER | FT | NY | WN | 2025-09-22 | 10 | 2025-09-22 | 15 | 27 |  | 0 | 27 | S-FT | V-SM-NY:09/22 > WN:09/22
VESSEL | GALAXY | IN | WN | SKL | 2025-09-22 | 18 | 2025-09-23 | 6 | 33 |  | 0 | 33 | S-IN | V-GX-WN:09/22 > SKL:09/23
VESSEL | GALAXY | OUT | SKL | WN | 2025-09-24 | 17 | 2025-09-25 | 6 | 33 |  | 15 | 18 | S-OUT | V-GX-SKL:09/24 > WN:09/25
VESSEL | NEPTUNE | IN | MNA | STH | 2025-09-25 | 20 | 2025-09-26 | 6 | 27 |  | 18 | 9 | N-IN | V-TC-MNA:09/25 > STH:09/26
VESSEL | GANYA | FT | JAS | MNA | 2025-09-25 | 12 | 2025-09-25 | 20 | 43 |  | 0 | 43 | N-FT | V-GY-JAS:09/25 > MNA:09/25
VESSEL | GANYA | FT | MNA | JAS | 2025-10-01 | 12 | 2025-10-01 | 20 | 43 |  | 0 | 43 | N-FT | V-GY-MNA:10/01 > JAS:10/01
VESSEL | SUMMER | IN | WN | NY | 2025-09-25 | 8 | 2025-09-25 | 13 | 27 |  | 0 | 27 | S-IN | V-SM-WN:09/25 > NY:09/25
VESSEL | SUMMER |  | NY | SKL | 2025-09-25 | 17 | 2025-09-26 | 8 | 27 |  | 0 | 27 | FALSE | V-SM-NY:09/25 > SKL:09/26
VESSEL | NEPTUNE | OUT | STH | MNA | 2025-09-27 | 8 | 2025-09-27 | 17 | 27 |  | 0 | 27 | N-OUT | V-TC-STH:09/27 > MNA:09/27
VESSEL | SUMMER | OUT | SKL | NY | 2025-09-30 | 16 | 2025-10-01 | 7 | 27 |  | 0 | 27 | S-OUT | V-SM-SKL:09/30 > NY:10/01

## Chopper_Plan
Type | Vessel | Dir | Origin | Destination | DEP. Date | ARR Date | MAX SEAT | Regular Crew | BOOK SEAT | AVAILABLE SEAT | Code | Trip ID
CHOPPER | HN | OUT | UTP | JAS | 2025-02-01 | 2025-02-01 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:02/01 > JAS:02/01
CHOPPER | HN | IN | JAS | UTP | 2025-02-01 | 2025-02-01 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:02/01 > UTP:02/01
CHOPPER | HN | OUT | UTP | MNA | 2025-02-01 | 2025-02-01 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:02/01 > MNA:02/01
CHOPPER | HN | IN | MNA | UTP | 2025-02-01 | 2025-02-01 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:02/01 > UTP:02/01
CHOPPER | HN | OUT | UTP | JAS | 2025-02-03 | 2025-02-03 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:02/03 > JAS:02/03
CHOPPER | HN | IN | JAS | UTP | 2025-02-03 | 2025-02-03 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:02/03 > UTP:02/03
CHOPPER | HN | OUT | UTP | MNA | 2025-02-03 | 2025-02-03 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:02/03 > MNA:02/03
CHOPPER | HN | IN | MNA | UTP | 2025-02-03 | 2025-02-03 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:02/03 > UTP:02/03
CHOPPER | HS | OUT | SKL | NY | 2025-02-05 | 2025-02-05 | 12 | 12 | 0 | 0 | S-OUT | C-HS-SKL:02/05 > NY:02/05
CHOPPER | HS | IN | NY | SKL | 2025-02-05 | 2025-02-05 | 12 | 12 | 0 | 0 | S-IN | C-HS-NY:02/05 > SKL:02/05
CHOPPER | HS | OUT | SKL | WN | 2025-02-05 | 2025-02-05 | 12 | 5 | 0 | 7 | S-OUT | C-HS-SKL:02/05 > WN:02/05
CHOPPER | HS | IN | WN | SKL | 2025-02-05 | 2025-02-05 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:02/05 > SKL:02/05
CHOPPER | HS | OUT | SKL | WN | 2025-02-07 | 2025-02-07 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:02/07 > WN:02/07
CHOPPER | HS | IN | WN | SKL | 2025-02-07 | 2025-02-07 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:02/07 > SKL:02/07
CHOPPER | HN | OUT | UTP | JAS | 2025-02-08 | 2025-02-08 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:02/08 > JAS:02/08
CHOPPER | HN | IN | JAS | UTP | 2025-02-08 | 2025-02-08 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:02/08 > UTP:02/08
CHOPPER | HN | OUT | UTP | MNA | 2025-02-08 | 2025-02-08 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:02/08 > MNA:02/08
CHOPPER | HN | IN | MNA | UTP | 2025-02-08 | 2025-02-08 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:02/08 > UTP:02/08
CHOPPER | HS | OUT | SKL | NY | 2025-02-08 | 2025-02-08 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:02/08 > NY:02/08
CHOPPER | HS | IN | NY | SKL | 2025-02-08 | 2025-02-08 | 12 |  | 0 | 12 | S-IN | C-HS-NY:02/08 > SKL:02/08
CHOPPER | HN | OUT | UTP | JAS | 2025-02-10 | 2025-02-10 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:02/10 > JAS:02/10
CHOPPER | HN | IN | JAS | UTP | 2025-02-10 | 2025-02-10 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:02/10 > UTP:02/10
CHOPPER | HS | OUT | SKL | NY | 2025-02-12 | 2025-02-12 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:02/12 > NY:02/12
CHOPPER | HS | IN | NY | SKL | 2025-02-12 | 2025-02-12 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:02/12 > SKL:02/12
CHOPPER | HS | OUT | SKL | WN | 2025-02-12 | 2025-02-12 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:02/12 > WN:02/12
CHOPPER | HS | IN | WN | SKL | 2025-02-12 | 2025-02-12 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:02/12 > SKL:02/12
CHOPPER | HN | OUT | UTP | JAS | 2025-02-13 | 2025-02-13 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:02/13 > JAS:02/13
CHOPPER | HN | IN | JAS | UTP | 2025-02-13 | 2025-02-13 | 12 | 10 | 0 | 2 | N-IN | C-HN-JAS:02/13 > UTP:02/13
CHOPPER | HS | OUT | SKL | WN | 2025-02-14 | 2025-02-14 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:02/14 > WN:02/14
CHOPPER | HS | IN | WN | SKL | 2025-02-14 | 2025-02-14 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:02/14 > SKL:02/14
CHOPPER | HN | OUT | UTP | JAS | 2025-02-15 | 2025-02-15 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:02/15 > JAS:02/15
CHOPPER | HN | IN | JAS | UTP | 2025-02-15 | 2025-02-15 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:02/15 > UTP:02/15
CHOPPER | HN | OUT | UTP | MNA | 2025-02-15 | 2025-02-15 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:02/15 > MNA:02/15
CHOPPER | HN | FT | MNA | JAS | 2025-02-15 | 2025-02-15 | 12 | 11 | 0 | 1 | N-FT | C-HN-MNA:02/15 > JAS:02/15
CHOPPER | HN | OUT | UTP | JAS | 2025-02-17 | 2025-02-17 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:02/17 > JAS:02/17
CHOPPER | HN | IN | JAS | UTP | 2025-02-17 | 2025-02-17 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:02/17 > UTP:02/17
CHOPPER | HN | OUT | UTP | MNA | 2025-02-17 | 2025-02-17 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:02/17 > MNA:02/17
CHOPPER | HN | IN | MNA | UTP | 2025-02-17 | 2025-02-17 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:02/17 > UTP:02/17
CHOPPER | HS | OUT | SKL | NY | 2025-02-19 | 2025-02-19 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:02/19 > NY:02/19
CHOPPER | HS | IN | NY | SKL | 2025-02-19 | 2025-02-19 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:02/19 > SKL:02/19
CHOPPER | HS | OUT | SKL | WN | 2025-02-19 | 2025-02-19 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:02/19 > WN:02/19
CHOPPER | HS | IN | WN | SKL | 2025-02-19 | 2025-02-19 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:02/19 > SKL:02/19
CHOPPER | HN | OUT | UTP | JAS | 2025-02-22 | 2025-02-22 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:02/22 > JAS:02/22
CHOPPER | HN | IN | JAS | UTP | 2025-02-22 | 2025-02-22 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:02/22 > UTP:02/22
CHOPPER | HN | OUT | UTP | MNA | 2025-02-22 | 2025-02-22 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:02/22 > MNA:02/22
CHOPPER | HN | IN | MNA | UTP | 2025-02-22 | 2025-02-22 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:02/22 > UTP:02/22
CHOPPER | HS | OUT | SKL | NY | 2025-02-22 | 2025-02-22 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:02/22 > NY:02/22
CHOPPER | HS | IN | NY | SKL | 2025-02-22 | 2025-02-22 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:02/22 > SKL:02/22
CHOPPER | HN | OUT | UTP | JAS | 2025-02-24 | 2025-02-24 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:02/24 > JAS:02/24
CHOPPER | HN | IN | JAS | UTP | 2025-02-24 | 2025-02-24 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:02/24 > UTP:02/24
CHOPPER | HS | OUT | SKL | NY | 2025-02-26 | 2025-02-26 | 12 | 12 | 0 | 0 | S-OUT | C-HS-SKL:02/26 > NY:02/26
CHOPPER | HS | IN | NY | SKL | 2025-02-26 | 2025-02-26 | 12 | 12 | 0 | 0 | S-IN | C-HS-NY:02/26 > SKL:02/26
CHOPPER | HS | OUT | SKL | WN | 2025-02-26 | 2025-02-26 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:02/26 > WN:02/26
CHOPPER | HS | IN | WN | SKL | 2025-02-26 | 2025-02-26 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:02/26 > SKL:02/26
CHOPPER | HN | OUT | UTP | JAS | 2025-02-27 | 2025-02-27 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:02/27 > JAS:02/27
CHOPPER | HN | IN | JAS | UTP | 2025-02-27 | 2025-02-27 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:02/27 > UTP:02/27
CHOPPER | HS | OUT | SKL | WN | 2025-02-28 | 2025-02-28 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:02/28 > WN:02/28
CHOPPER | HS | IN | WN | SKL | 2025-02-28 | 2025-02-28 | 12 | 11 | 0 | 1 | S-IN | C-HS-WN:02/28 > SKL:02/28
CHOPPER | HN | OUT | UTP | JAS | 2025-03-01 | 2025-03-01 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:03/01 > JAS:03/01
CHOPPER | HN | IN | JAS | UTP | 2025-03-01 | 2025-03-01 | 12 | 12 | 0 | 0 | N-IN | C-HN-JAS:03/01 > UTP:03/01
CHOPPER | HN | OUT | UTP | MNA | 2025-03-01 | 2025-03-01 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:03/01 > MNA:03/01
CHOPPER | HN | IN | MNA | UTP | 2025-03-01 | 2025-03-01 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:03/01 > UTP:03/01
CHOPPER | HS | OUT | SKL | NY | 2025-03-01 | 2025-03-01 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:03/01 > NY:03/01
CHOPPER | HS | IN | NY | SKL | 2025-03-01 | 2025-03-01 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:03/01 > SKL:03/01
CHOPPER | HS | OUT | SKL | NY | 2025-03-05 | 2025-03-05 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:03/05 > NY:03/05
CHOPPER | HS | IN | NY | SKL | 2025-03-05 | 2025-03-05 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:03/05 > SKL:03/05
CHOPPER | HS | OUT | SKL | WN | 2025-03-05 | 2025-03-05 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:03/05 > WN:03/05
CHOPPER | HS | IN | WN | SKL | 2025-03-05 | 2025-03-05 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:03/05 > SKL:03/05
CHOPPER | HN | OUT | UTP | JAS | 2025-03-06 | 2025-03-06 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:03/06 > JAS:03/06
CHOPPER | HN | IN | JAS | UTP | 2025-03-06 | 2025-03-06 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:03/06 > UTP:03/06
CHOPPER | HS | OUT | SKL | WN | 2025-03-07 | 2025-03-07 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:03/07 > WN:03/07
CHOPPER | HS | IN | WN | SKL | 2025-03-07 | 2025-03-07 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:03/07 > SKL:03/07
CHOPPER | HN | OUT | UTP | JAS | 2025-03-08 | 2025-03-08 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:03/08 > JAS:03/08
CHOPPER | HN | IN | JAS | UTP | 2025-03-08 | 2025-03-08 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:03/08 > UTP:03/08
CHOPPER | HN | OUT | UTP | MNA | 2025-03-08 | 2025-03-08 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:03/08 > MNA:03/08
CHOPPER | HN | IN | MNA | UTP | 2025-03-08 | 2025-03-08 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:03/08 > UTP:03/08
CHOPPER | HS | OUT | SKL | NY | 2025-03-08 | 2025-03-08 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:03/08 > NY:03/08
CHOPPER | HS | IN | NY | SKL | 2025-03-08 | 2025-03-08 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:03/08 > SKL:03/08
CHOPPER | HN | OUT | UTP | JAS | 2025-03-10 | 2025-03-10 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:03/10 > JAS:03/10
CHOPPER | HN | IN | JAS | UTP | 2025-03-10 | 2025-03-10 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:03/10 > UTP:03/10
CHOPPER | HS | OUT | SKL | NY | 2025-03-12 | 2025-03-12 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:03/12 > NY:03/12
CHOPPER | HS | IN | NY | SKL | 2025-03-12 | 2025-03-12 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:03/12 > SKL:03/12
CHOPPER | HS | OUT | SKL | WN | 2025-03-12 | 2025-03-12 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:03/12 > WN:03/12
CHOPPER | HS | IN | WN | SKL | 2025-03-12 | 2025-03-12 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:03/12 > SKL:03/12
CHOPPER | HN | OUT | UTP | JAS | 2025-03-13 | 2025-03-13 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:03/13 > JAS:03/13
CHOPPER | HN | IN | JAS | UTP | 2025-03-13 | 2025-03-13 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:03/13 > UTP:03/13
CHOPPER | HS | OUT | SKL | WN | 2025-03-14 | 2025-03-14 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:03/14 > WN:03/14
CHOPPER | HS | IN | WN | SKL | 2025-03-14 | 2025-03-14 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:03/14 > SKL:03/14
CHOPPER | HN | OUT | UTP | JAS | 2025-03-15 | 2025-03-15 | 12 | 4 | 0 | 8 | N-OUT | C-HN-UTP:03/15 > JAS:03/15
CHOPPER | HN | IN | JAS | UTP | 2025-03-15 | 2025-03-15 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:03/15 > UTP:03/15
CHOPPER | HN | OUT | UTP | MNA | 2025-03-15 | 2025-03-15 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:03/15 > MNA:03/15
CHOPPER | HN | IN | MNA | UTP | 2025-03-15 | 2025-03-15 | 12 | 7 | 0 | 5 | N-IN | C-HN-MNA:03/15 > UTP:03/15
CHOPPER | HN | OUT | UTP | JAS | 2025-03-17 | 2025-03-17 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:03/17 > JAS:03/17
CHOPPER | HN | IN | JAS | UTP | 2025-03-17 | 2025-03-17 | 12 | 10 | 0 | 2 | N-IN | C-HN-JAS:03/17 > UTP:03/17
CHOPPER | HN | OUT | UTP | MNA | 2025-03-17 | 2025-03-17 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:03/17 > MNA:03/17
CHOPPER | HN | IN | MNA | UTP | 2025-03-17 | 2025-03-17 | 12 | 12 | 0 | 0 | N-IN | C-HN-MNA:03/17 > UTP:03/17
CHOPPER | HS | OUT | SKL | NY | 2025-03-19 | 2025-03-19 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:03/19 > NY:03/19
CHOPPER | HS | IN | NY | SKL | 2025-03-19 | 2025-03-19 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:03/19 > SKL:03/19
CHOPPER | HS | OUT | SKL | WN | 2025-03-19 | 2025-03-19 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:03/19 > WN:03/19
CHOPPER | HS | IN | WN | SKL | 2025-03-19 | 2025-03-19 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:03/19 > SKL:03/19
CHOPPER | HN | OUT | UTP | JAS | 2025-03-22 | 2025-03-22 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:03/22 > JAS:03/22
CHOPPER | HN | IN | JAS | UTP | 2025-03-22 | 2025-03-22 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:03/22 > UTP:03/22
CHOPPER | HN | OUT | UTP | MNA | 2025-03-22 | 2025-03-22 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:03/22 > MNA:03/22
CHOPPER | HN | IN | MNA | UTP | 2025-03-22 | 2025-03-22 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:03/22 > UTP:03/22
CHOPPER | HS | OUT | SKL | NY | 2025-03-22 | 2025-03-22 | 12 |  | 0 | 12 | S-OUT | C-HS-SKL:03/22 > NY:03/22
CHOPPER | HS | IN | NY | SKL | 2025-03-22 | 2025-03-22 | 12 |  | 0 | 12 | S-IN | C-HS-NY:03/22 > SKL:03/22
CHOPPER | HN | OUT | UTP | JAS | 2025-03-24 | 2025-03-24 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:03/24 > JAS:03/24
CHOPPER | HN | IN | JAS | UTP | 2025-03-24 | 2025-03-24 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:03/24 > UTP:03/24
CHOPPER | HS | OUT | SKL | NY | 2025-03-26 | 2025-03-26 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:03/26 > NY:03/26
CHOPPER | HS | IN | NY | SKL | 2025-03-26 | 2025-03-26 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:03/26 > SKL:03/26
CHOPPER | HS | OUT | SKL | WN | 2025-03-26 | 2025-03-26 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:03/26 > WN:03/26
CHOPPER | HS | IN | WN | SKL | 2025-03-26 | 2025-03-26 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:03/26 > SKL:03/26
CHOPPER | HN | OUT | UTP | JAS | 2025-03-27 | 2025-03-27 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:03/27 > JAS:03/27
CHOPPER | HN | IN | JAS | UTP | 2025-03-27 | 2025-03-27 | 12 | 10 | 0 | 2 | N-IN | C-HN-JAS:03/27 > UTP:03/27
CHOPPER | HS | OUT | SKL | WN | 2025-03-28 | 2025-03-28 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:03/28 > WN:03/28
CHOPPER | HS | IN | WN | SKL | 2025-03-28 | 2025-03-28 | 12 | 11 | 0 | 1 | S-IN | C-HS-WN:03/28 > SKL:03/28
CHOPPER | HN | OUT | UTP | JAS | 2025-03-29 | 2025-03-29 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:03/29 > JAS:03/29
CHOPPER | HN | IN | JAS | UTP | 2025-03-29 | 2025-03-29 | 12 | 12 | 0 | 0 | N-IN | C-HN-JAS:03/29 > UTP:03/29
CHOPPER | HN | OUT | UTP | MNA | 2025-03-29 | 2025-03-29 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:03/29 > MNA:03/29
CHOPPER | HN | IN | MNA | UTP | 2025-03-29 | 2025-03-29 | 12 | 11 | 0 | 1 | N-IN | C-HN-MNA:03/29 > UTP:03/29
CHOPPER | HN | OUT | UTP | JAS | 2025-03-31 | 2025-03-31 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:03/31 > JAS:03/31
CHOPPER | HN | IN | JAS | UTP | 2025-03-31 | 2025-03-31 | 12 | 10 | 0 | 2 | N-IN | C-HN-JAS:03/31 > UTP:03/31
CHOPPER | HN | OUT | UTP | MNA | 2025-03-31 | 2025-03-31 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:03/31 > MNA:03/31
CHOPPER | HN | IN | MNA | UTP | 2025-03-31 | 2025-03-31 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:03/31 > UTP:03/31
CHOPPER | HS | OUT | SKL | NY | 2025-04-01 | 2025-04-01 | 12 | 0 | 0 | 12 | S-OUT | C-HS-SKL:04/01 > NY:04/01
CHOPPER | HS | IN | NY | SKL | 2025-04-01 | 2025-04-01 | 12 | 0 | 0 | 12 | S-IN | C-HS-NY:04/01 > SKL:04/01
CHOPPER | HS | OUT | SKL | NY | 2025-04-02 | 2025-04-02 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:04/02 > NY:04/02
CHOPPER | HS | IN | NY | SKL | 2025-04-02 | 2025-04-02 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:04/02 > SKL:04/02
CHOPPER | HS | OUT | SKL | WN | 2025-04-02 | 2025-04-02 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:04/02 > WN:04/02
CHOPPER | HS | IN | WN | SKL | 2025-04-02 | 2025-04-02 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:04/02 > SKL:04/02
CHOPPER | HS | OUT | SKL | WN | 2025-04-04 | 2025-04-04 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:04/04 > WN:04/04
CHOPPER | HS | IN | WN | SKL | 2025-04-04 | 2025-04-04 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:04/04 > SKL:04/04
CHOPPER | HN | OUT | UTP | JAS | 2025-04-05 | 2025-04-05 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:04/05 > JAS:04/05
CHOPPER | HN | IN | JAS | UTP | 2025-04-05 | 2025-04-05 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:04/05 > UTP:04/05
CHOPPER | HN | OUT | UTP | MNA | 2025-04-05 | 2025-04-05 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:04/05 > MNA:04/05
CHOPPER | HN | IN | MNA | UTP | 2025-04-05 | 2025-04-05 | 12 | 4 | 0 | 8 | N-IN | C-HN-MNA:04/05 > UTP:04/05
CHOPPER | HS | OUT | SKL | NY | 2025-04-05 | 2025-04-05 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:04/05 > NY:04/05
CHOPPER | HS | IN | NY | SKL | 2025-04-05 | 2025-04-05 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:04/05 > SKL:04/05
CHOPPER | HN | OUT | UTP | JAS | 2025-04-07 | 2025-04-07 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:04/07 > JAS:04/07
CHOPPER | HN | IN | JAS | UTP | 2025-04-07 | 2025-04-07 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:04/07 > UTP:04/07
CHOPPER | HS | OUT | SKL | NY | 2025-04-09 | 2025-04-09 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:04/09 > NY:04/09
CHOPPER | HS | IN | NY | SKL | 2025-04-09 | 2025-04-09 | 12 | 11 | 0 | 1 | S-IN | C-HS-NY:04/09 > SKL:04/09
CHOPPER | HS | OUT | SKL | WN | 2025-04-09 | 2025-04-09 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:04/09 > WN:04/09
CHOPPER | HS | IN | WN | SKL | 2025-04-09 | 2025-04-09 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:04/09 > SKL:04/09
CHOPPER | HN | OUT | UTP | JAS | 2025-04-10 | 2025-04-10 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:04/10 > JAS:04/10
CHOPPER | HN | IN | JAS | UTP | 2025-04-10 | 2025-04-10 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:04/10 > UTP:04/10
CHOPPER | HS | OUT | SKL | WN | 2025-04-11 | 2025-04-11 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:04/11 > WN:04/11
CHOPPER | HS | IN | WN | SKL | 2025-04-11 | 2025-04-11 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:04/11 > SKL:04/11
CHOPPER | HN | OUT | UTP | JAS | 2025-04-12 | 2025-04-12 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:04/12 > JAS:04/12
CHOPPER | HN | IN | JAS | UTP | 2025-04-12 | 2025-04-12 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:04/12 > UTP:04/12
CHOPPER | HN | OUT | UTP | MNA | 2025-04-12 | 2025-04-12 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:04/12 > MNA:04/12
CHOPPER | HN | IN | MNA | UTP | 2025-04-12 | 2025-04-12 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:04/12 > UTP:04/12
CHOPPER | HS | OUT | SKL | NY | 2025-04-12 | 2025-04-12 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:04/12 > NY:04/12
CHOPPER | HS | IN | NY | SKL | 2025-04-12 | 2025-04-12 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:04/12 > SKL:04/12
CHOPPER | HN | OUT | UTP | JAS | 2025-04-14 | 2025-04-14 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:04/14 > JAS:04/14
CHOPPER | HN | IN | JAS | UTP | 2025-04-14 | 2025-04-14 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:04/14 > UTP:04/14
CHOPPER | HN | OUT | UTP | MNA | 2025-04-14 | 2025-04-14 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:04/14 > MNA:04/14
CHOPPER | HN | IN | MNA | UTP | 2025-04-14 | 2025-04-14 | 12 | 12 | 0 | 0 | N-IN | C-HN-MNA:04/14 > UTP:04/14
CHOPPER | HS | OUT | SKL | NY | 2025-04-16 | 2025-04-16 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:04/16 > NY:04/16
CHOPPER | HS | IN | NY | SKL | 2025-04-16 | 2025-04-16 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:04/16 > SKL:04/16
CHOPPER | HS | OUT | SKL | WN | 2025-04-16 | 2025-04-16 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:04/16 > WN:04/16
CHOPPER | HS | IN | WN | SKL | 2025-04-16 | 2025-04-16 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:04/16 > SKL:04/16
CHOPPER | HN | OUT | UTP | JAS | 2025-04-17 | 2025-04-17 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:04/17 > JAS:04/17
CHOPPER | HN | IN | JAS | UTP | 2025-04-17 | 2025-04-17 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:04/17 > UTP:04/17
CHOPPER | HN | OUT | UTP | JAS | 2025-04-19 | 2025-04-19 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:04/19 > JAS:04/19
CHOPPER | HN | IN | JAS | UTP | 2025-04-19 | 2025-04-19 | 12 | 10 | 0 | 2 | N-IN | C-HN-JAS:04/19 > UTP:04/19
CHOPPER | HN | OUT | UTP | MNA | 2025-04-19 | 2025-04-19 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:04/19 > MNA:04/19
CHOPPER | HN | IN | MNA | UTP | 2025-04-19 | 2025-04-19 | 12 | 12 | 0 | 0 | N-IN | C-HN-MNA:04/19 > UTP:04/19
CHOPPER | HS | OUT | SKL | NY | 2025-04-19 | 2025-04-19 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:04/19 > NY:04/19
CHOPPER | HS | IN | NY | SKL | 2025-04-19 | 2025-04-19 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:04/19 > SKL:04/19
CHOPPER | HN | OUT | UTP | JAS | 2025-04-21 | 2025-04-21 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:04/21 > JAS:04/21
CHOPPER | HN | IN | JAS | UTP | 2025-04-21 | 2025-04-21 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:04/21 > UTP:04/21
CHOPPER | HS | OUT | SKL | NY | 2025-04-23 | 2025-04-23 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:04/23 > NY:04/23
CHOPPER | HS | IN | NY | SKL | 2025-04-23 | 2025-04-23 | 12 | 11 | 0 | 1 | S-IN | C-HS-NY:04/23 > SKL:04/23
CHOPPER | HS | OUT | SKL | WN | 2025-04-23 | 2025-04-23 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:04/23 > WN:04/23
CHOPPER | HS | IN | WN | SKL | 2025-04-23 | 2025-04-23 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:04/23 > SKL:04/23
CHOPPER | HN | OUT | UTP | JAS | 2025-04-24 | 2025-04-24 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:04/24 > JAS:04/24
CHOPPER | HN | IN | JAS | UTP | 2025-04-24 | 2025-04-24 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:04/24 > UTP:04/24
CHOPPER | HS | OUT | SKL | WN | 2025-04-25 | 2025-04-25 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:04/25 > WN:04/25
CHOPPER | HS | IN | WN | SKL | 2025-04-25 | 2025-04-25 | 12 | 11 | 0 | 1 | S-IN | C-HS-WN:04/25 > SKL:04/25
CHOPPER | HN | OUT | UTP | JAS | 2025-04-26 | 2025-04-26 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:04/26 > JAS:04/26
CHOPPER | HN | IN | JAS | UTP | 2025-04-26 | 2025-04-26 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:04/26 > UTP:04/26
CHOPPER | HN | OUT | UTP | MNA | 2025-04-26 | 2025-04-26 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:04/26 > MNA:04/26
CHOPPER | HN | IN | MNA | UTP | 2025-04-26 | 2025-04-26 | 12 | 5 | 0 | 7 | N-IN | C-HN-MNA:04/26 > UTP:04/26
CHOPPER | HN | OUT | UTP | JAS | 2025-04-28 | 2025-04-28 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:04/28 > JAS:04/28
CHOPPER | HN | IN | JAS | UTP | 2025-04-28 | 2025-04-28 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:04/28 > UTP:04/28
CHOPPER | HN | OUT | UTP | MNA | 2025-04-28 | 2025-04-28 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:04/28 > MNA:04/28
CHOPPER | HN | IN | MNA | UTP | 2025-04-28 | 2025-04-28 | 12 | 0 | 0 | 12 | N-IN | C-HN-MNA:04/28 > UTP:04/28
CHOPPER | HS | OUT | SKL | NY | 2025-04-30 | 2025-04-30 | 12 | 12 | 0 | 0 | S-OUT | C-HS-SKL:04/30 > NY:04/30
CHOPPER | HS | IN | NY | SKL | 2025-04-30 | 2025-04-30 | 12 | 12 | 0 | 0 | S-IN | C-HS-NY:04/30 > SKL:04/30
CHOPPER | HS | OUT | SKL | WN | 2025-04-30 | 2025-04-30 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:04/30 > WN:04/30
CHOPPER | HS | IN | WN | SKL | 2025-04-30 | 2025-04-30 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:04/30 > SKL:04/30
CHOPPER | HS | OUT | SKL | WN | 2025-05-02 | 2025-05-02 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:05/02 > WN:05/02
CHOPPER | HS | IN | WN | SKL | 2025-05-02 | 2025-05-02 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:05/02 > SKL:05/02
CHOPPER | HN | OUT | UTP | JAS | 2025-05-03 | 2025-05-03 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:05/03 > JAS:05/03
CHOPPER | HN | IN | JAS | UTP | 2025-05-03 | 2025-05-03 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:05/03 > UTP:05/03
CHOPPER | HN | OUT | UTP | MNA | 2025-05-03 | 2025-05-03 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:05/03 > MNA:05/03
CHOPPER | HN | IN | MNA | UTP | 2025-05-03 | 2025-05-03 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:05/03 > UTP:05/03
CHOPPER | HS | OUT | SKL | NY | 2025-05-03 | 2025-05-03 | 12 |  | 0 | 12 | S-OUT | C-HS-SKL:05/03 > NY:05/03
CHOPPER | HS | IN | NY | SKL | 2025-05-03 | 2025-05-03 | 12 |  | 0 | 12 | S-IN | C-HS-NY:05/03 > SKL:05/03
CHOPPER | HN | OUT | UTP | JAS | 2025-05-05 | 2025-05-05 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:05/05 > JAS:05/05
CHOPPER | HN | IN | JAS | UTP | 2025-05-05 | 2025-05-05 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:05/05 > UTP:05/05
CHOPPER | HS | OUT | SKL | NY | 2025-05-07 | 2025-05-07 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:05/07 > NY:05/07
CHOPPER | HS | IN | NY | SKL | 2025-05-07 | 2025-05-07 | 12 | 7 | 0 | 5 | S-IN | C-HS-NY:05/07 > SKL:05/07
CHOPPER | HS | OUT | SKL | WN | 2025-05-07 | 2025-05-07 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:05/07 > WN:05/07
CHOPPER | HS | IN | WN | SKL | 2025-05-07 | 2025-05-07 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:05/07 > SKL:05/07
CHOPPER | HN | OUT | UTP | JAS | 2025-05-08 | 2025-05-08 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:05/08 > JAS:05/08
CHOPPER | HN | IN | JAS | UTP | 2025-05-08 | 2025-05-08 | 12 | 9 | 0 | 3 | N-IN | C-HN-JAS:05/08 > UTP:05/08
CHOPPER | HS | OUT | SKL | WN | 2025-05-09 | 2025-05-09 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:05/09 > WN:05/09
CHOPPER | HS | IN | WN | SKL | 2025-05-09 | 2025-05-09 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:05/09 > SKL:05/09
CHOPPER | HN | OUT | UTP | JAS | 2025-05-10 | 2025-05-10 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:05/10 > JAS:05/10
CHOPPER | HN | IN | JAS | UTP | 2025-05-10 | 2025-05-10 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:05/10 > UTP:05/10
CHOPPER | HN | OUT | UTP | MNA | 2025-05-10 | 2025-05-10 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:05/10 > MNA:05/10
CHOPPER | HN | IN | MNA | UTP | 2025-05-10 | 2025-05-10 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:05/10 > UTP:05/10
CHOPPER | HN | OUT | UTP | JAS | 2025-05-12 | 2025-05-12 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:05/12 > JAS:05/12
CHOPPER | HN | IN | JAS | UTP | 2025-05-12 | 2025-05-12 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:05/12 > UTP:05/12
CHOPPER | HN | OUT | UTP | MNA | 2025-05-12 | 2025-05-12 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:05/12 > MNA:05/12
CHOPPER | HN | IN | MNA | UTP | 2025-05-12 | 2025-05-12 | 12 | 0 | 0 | 12 | N-IN | C-HN-MNA:05/12 > UTP:05/12
CHOPPER | HS | OUT | SKL | NY | 2025-05-14 | 2025-05-14 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:05/14 > NY:05/14
CHOPPER | HS | IN | NY | SKL | 2025-05-14 | 2025-05-14 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:05/14 > SKL:05/14
CHOPPER | HS | OUT | SKL | WN | 2025-05-14 | 2025-05-14 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:05/14 > WN:05/14
CHOPPER | HS | IN | WN | SKL | 2025-05-14 | 2025-05-14 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:05/14 > SKL:05/14
CHOPPER | HN | OUT | UTP | JAS | 2025-05-17 | 2025-05-17 | 12 | 4 | 0 | 8 | N-OUT | C-HN-UTP:05/17 > JAS:05/17
CHOPPER | HN | IN | JAS | UTP | 2025-05-17 | 2025-05-17 | 12 | 4 | 0 | 8 | N-IN | C-HN-JAS:05/17 > UTP:05/17
CHOPPER | HN | OUT | UTP | MNA | 2025-05-17 | 2025-05-17 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:05/17 > MNA:05/17
CHOPPER | HN | IN | MNA | UTP | 2025-05-17 | 2025-05-17 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:05/17 > UTP:05/17
CHOPPER | HS | OUT | SKL | NY | 2025-05-17 | 2025-05-17 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:05/17 > NY:05/17
CHOPPER | HS | IN | NY | SKL | 2025-05-17 | 2025-05-17 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:05/17 > SKL:05/17
CHOPPER | HN | OUT | UTP | JAS | 2025-05-19 | 2025-05-19 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:05/19 > JAS:05/19
CHOPPER | HN | IN | JAS | UTP | 2025-05-19 | 2025-05-19 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:05/19 > UTP:05/19
CHOPPER | HS | OUT | SKL | NY | 2025-05-21 | 2025-05-21 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:05/21 > NY:05/21
CHOPPER | HS | IN | NY | SKL | 2025-05-21 | 2025-05-21 | 12 | 11 | 0 | 1 | S-IN | C-HS-NY:05/21 > SKL:05/21
CHOPPER | HS | OUT | SKL | WN | 2025-05-21 | 2025-05-21 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:05/21 > WN:05/21
CHOPPER | HS | IN | WN | SKL | 2025-05-21 | 2025-05-21 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:05/21 > SKL:05/21
CHOPPER | HN | OUT | UTP | JAS | 2025-05-22 | 2025-05-22 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:05/22 > JAS:05/22
CHOPPER | HN | IN | JAS | UTP | 2025-05-22 | 2025-05-22 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:05/22 > UTP:05/22
CHOPPER | HS | OUT | SKL | WN | 2025-05-23 | 2025-05-23 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:05/23 > WN:05/23
CHOPPER | HS | IN | WN | SKL | 2025-05-23 | 2025-05-23 | 12 | 11 | 0 | 1 | S-IN | C-HS-WN:05/23 > SKL:05/23
CHOPPER | HN | OUT | UTP | JAS | 2025-05-24 | 2025-05-24 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:05/24 > JAS:05/24
CHOPPER | HN | IN | JAS | UTP | 2025-05-24 | 2025-05-24 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:05/24 > UTP:05/24
CHOPPER | HN | OUT | UTP | MNA | 2025-05-24 | 2025-05-24 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:05/24 > MNA:05/24
CHOPPER | HN | IN | MNA | UTP | 2025-05-24 | 2025-05-24 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:05/24 > UTP:05/24
CHOPPER | HS | OUT | SKL | NY | 2025-05-24 | 2025-05-24 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:05/24 > NY:05/24
CHOPPER | HS | IN | NY | SKL | 2025-05-24 | 2025-05-24 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:05/24 > SKL:05/24
CHOPPER | HN | OUT | UTP | JAS | 2025-05-26 | 2025-05-26 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:05/26 > JAS:05/26
CHOPPER | HN | IN | JAS | UTP | 2025-05-26 | 2025-05-26 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:05/26 > UTP:05/26
CHOPPER | HN | OUT | UTP | MNA | 2025-05-26 | 2025-05-26 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:05/26 > MNA:05/26
CHOPPER | HN | IN | MNA | UTP | 2025-05-26 | 2025-05-26 | 12 | 0 | 0 | 12 | N-IN | C-HN-MNA:05/26 > UTP:05/26
CHOPPER | HS | OUT | SKL | NY | 2025-05-28 | 2025-05-28 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:05/28 > NY:05/28
CHOPPER | HS | IN | NY | SKL | 2025-05-28 | 2025-05-28 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:05/28 > SKL:05/28
CHOPPER | HS | OUT | SKL | WN | 2025-05-28 | 2025-05-28 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:05/28 > WN:05/28
CHOPPER | HS | IN | WN | SKL | 2025-05-28 | 2025-05-28 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:05/28 > SKL:05/28
CHOPPER | HN | OUT | UTP | JAS | 2025-05-29 | 2025-05-29 | 12 | 3 | 0 | 9 | N-OUT | C-HN-UTP:05/29 > JAS:05/29
CHOPPER | HN | IN | JAS | UTP | 2025-05-29 | 2025-05-29 | 12 | 3 | 0 | 9 | N-IN | C-HN-JAS:05/29 > UTP:05/29
CHOPPER | HS | OUT | SKL | WN | 2025-05-30 | 2025-05-30 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:05/30 > WN:05/30
CHOPPER | HS | IN | WN | SKL | 2025-05-30 | 2025-05-30 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:05/30 > SKL:05/30
CHOPPER | HN | OUT | UTP | JAS | 2025-05-31 | 2025-05-31 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:05/31 > JAS:05/31
CHOPPER | HN | IN | JAS | UTP | 2025-05-31 | 2025-05-31 | 12 | 12 | 0 | 0 | N-IN | C-HN-JAS:05/31 > UTP:05/31
CHOPPER | HN | OUT | UTP | MNA | 2025-05-31 | 2025-05-31 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:05/31 > MNA:05/31
CHOPPER | HN | IN | MNA | UTP | 2025-05-31 | 2025-05-31 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:05/31 > UTP:05/31
CHOPPER | HS | OUT | SKL | NY | 2025-05-31 | 2025-05-31 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:05/31 > NY:05/31
CHOPPER | HS | IN | NY | SKL | 2025-05-31 | 2025-05-31 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:05/31 > SKL:05/31
CHOPPER | HN | OUT | UTP | JAS | 2025-06-02 | 2025-06-02 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:06/02 > JAS:06/02
CHOPPER | HN | IN | JAS | UTP | 2025-06-02 | 2025-06-02 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:06/02 > UTP:06/02
CHOPPER | HS | OUT | SKL | NY | 2025-06-04 | 2025-06-04 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:06/04 > NY:06/04
CHOPPER | HS | IN | NY | SKL | 2025-06-04 | 2025-06-04 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:06/04 > SKL:06/04
CHOPPER | HS | OUT | SKL | WN | 2025-06-04 | 2025-06-04 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:06/04 > WN:06/04
CHOPPER | HS | IN | WN | SKL | 2025-06-04 | 2025-06-04 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:06/04 > SKL:06/04
CHOPPER | HN | OUT | UTP | JAS | 2025-06-05 | 2025-06-05 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:06/05 > JAS:06/05
CHOPPER | HN | IN | JAS | UTP | 2025-06-05 | 2025-06-05 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:06/05 > UTP:06/05
CHOPPER | HN | OUT | UTP | JAS | 2025-06-06 | 2025-06-06 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:06/06 > JAS:06/06
CHOPPER | HN | IN | JAS | UTP | 2025-06-06 | 2025-06-06 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:06/06 > UTP:06/06
CHOPPER | HS | OUT | SKL | WN | 2025-06-06 | 2025-06-06 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:06/06 > WN:06/06
CHOPPER | HS | IN | WN | SKL | 2025-06-06 | 2025-06-06 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:06/06 > SKL:06/06
CHOPPER | HN | OUT | UTP | JAS | 2025-06-07 | 2025-06-07 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:06/07 > JAS:06/07
CHOPPER | HN | IN | JAS | UTP | 2025-06-07 | 2025-06-07 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:06/07 > UTP:06/07
CHOPPER | HN | OUT | UTP | MNA | 2025-06-07 | 2025-06-07 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:06/07 > MNA:06/07
CHOPPER | HN | IN | MNA | UTP | 2025-06-07 | 2025-06-07 | 12 | 7 | 0 | 5 | N-IN | C-HN-MNA:06/07 > UTP:06/07
CHOPPER | HN | OUT | UTP | JAS | 2025-06-09 | 2025-06-09 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:06/09 > JAS:06/09
CHOPPER | HN | IN | JAS | UTP | 2025-06-09 | 2025-06-09 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:06/09 > UTP:06/09
CHOPPER | HN | OUT | UTP | MNA | 2025-06-09 | 2025-06-09 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:06/09 > MNA:06/09
CHOPPER | HN | IN | MNA | UTP | 2025-06-09 | 2025-06-09 | 12 | 11 | 0 | 1 | N-IN | C-HN-MNA:06/09 > UTP:06/09
CHOPPER | HS | OUT | SKL | NY | 2025-06-11 | 2025-06-11 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:06/11 > NY:06/11
CHOPPER | HS | IN | NY | SKL | 2025-06-11 | 2025-06-11 | 12 | 12 | 0 | 0 | S-IN | C-HS-NY:06/11 > SKL:06/11
CHOPPER | HS | OUT | SKL | WN | 2025-06-11 | 2025-06-11 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:06/11 > WN:06/11
CHOPPER | HS | IN | WN | SKL | 2025-06-11 | 2025-06-11 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:06/11 > SKL:06/11
CHOPPER | HN | OUT | UTP | JAS | 2025-06-14 | 2025-06-14 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:06/14 > JAS:06/14
CHOPPER | HN | IN | JAS | UTP | 2025-06-14 | 2025-06-14 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:06/14 > UTP:06/14
CHOPPER | HN | OUT | UTP | MNA | 2025-06-14 | 2025-06-14 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:06/14 > MNA:06/14
CHOPPER | HN | IN | MNA | UTP | 2025-06-14 | 2025-06-14 | 12 | 8 | 0 | 4 | N-IN | C-HN-MNA:06/14 > UTP:06/14
CHOPPER | HS | OUT | SKL | NY | 2025-06-14 | 2025-06-14 | 24 | 21 | 0 | 3 | S-OUT | C-HS-SKL:06/14 > NY:06/14
CHOPPER | HS | IN | NY | SKL | 2025-06-14 | 2025-06-14 | 24 | 21 | 0 | 3 | S-IN | C-HS-NY:06/14 > SKL:06/14
CHOPPER | HN | OUT | UTP | JAS | 2025-06-16 | 2025-06-16 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:06/16 > JAS:06/16
CHOPPER | HN | IN | JAS | UTP | 2025-06-16 | 2025-06-16 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:06/16 > UTP:06/16
CHOPPER | HS | OUT | SKL | NY | 2025-06-18 | 2025-06-18 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:06/18 > NY:06/18
CHOPPER | HS | IN | NY | SKL | 2025-06-18 | 2025-06-18 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:06/18 > SKL:06/18
CHOPPER | HS | OUT | SKL | WN | 2025-06-18 | 2025-06-18 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:06/18 > WN:06/18
CHOPPER | HS | IN | WN | SKL | 2025-06-18 | 2025-06-18 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:06/18 > SKL:06/18
CHOPPER | HN | OUT | UTP | JAS | 2025-06-19 | 2025-06-19 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:06/19 > JAS:06/19
CHOPPER | HN | IN | JAS | UTP | 2025-06-19 | 2025-06-19 | 12 | 9 | 0 | 3 | N-IN | C-HN-JAS:06/19 > UTP:06/19
CHOPPER | HS | OUT | SKL | WN | 2025-06-20 | 2025-06-20 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:06/20 > WN:06/20
CHOPPER | HS | IN | WN | SKL | 2025-06-20 | 2025-06-20 | 12 | 11 | 0 | 1 | S-IN | C-HS-WN:06/20 > SKL:06/20
CHOPPER | HN | OUT | UTP | JAS | 2025-06-21 | 2025-06-21 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:06/21 > JAS:06/21
CHOPPER | HN | IN | JAS | UTP | 2025-06-21 | 2025-06-21 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:06/21 > UTP:06/21
CHOPPER | HN | OUT | UTP | MNA | 2025-06-21 | 2025-06-21 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:06/21 > MNA:06/21
CHOPPER | HN | IN | MNA | UTP | 2025-06-21 | 2025-06-21 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:06/21 > UTP:06/21
CHOPPER | HN | OUT | UTP | JAS | 2025-06-23 | 2025-06-23 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:06/23 > JAS:06/23
CHOPPER | HN | IN | JAS | UTP | 2025-06-23 | 2025-06-23 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:06/23 > UTP:06/23
CHOPPER | HN | OUT | UTP | MNA | 2025-06-23 | 2025-06-23 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:06/23 > MNA:06/23
CHOPPER | HN | IN | MNA | UTP | 2025-06-23 | 2025-06-23 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:06/23 > UTP:06/23
CHOPPER | HS | OUT | SKL | NY | 2025-06-25 | 2025-06-25 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:06/25 > NY:06/25
CHOPPER | HS | IN | NY | SKL | 2025-06-25 | 2025-06-25 | 12 | 11 | 0 | 1 | S-IN | C-HS-NY:06/25 > SKL:06/25
CHOPPER | HS | OUT | SKL | WN | 2025-06-25 | 2025-06-25 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:06/25 > WN:06/25
CHOPPER | HS | IN | WN | SKL | 2025-06-25 | 2025-06-25 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:06/25 > SKL:06/25
CHOPPER | HS | OUT | SKL | WN | 2025-06-27 | 2025-06-27 | 12 | 7 | 4 | 1 | S-OUT | C-HS-SKL:06/27 > WN:06/27
CHOPPER | HS | IN | WN | SKL | 2025-06-27 | 2025-06-27 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:06/27 > SKL:06/27
CHOPPER | HN | OUT | UTP | JAS | 2025-06-28 | 2025-06-28 | 12 | 6 | 5 | 1 | N-OUT | C-HN-UTP:06/28 > JAS:06/28
CHOPPER | HN | IN | JAS | UTP | 2025-06-28 | 2025-06-28 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:06/28 > UTP:06/28
CHOPPER | HN | OUT | UTP | MNA | 2025-06-28 | 2025-06-28 | 12 | 3 | 0 | 9 | N-OUT | C-HN-UTP:06/28 > MNA:06/28
CHOPPER | HN | IN | MNA | UTP | 2025-06-28 | 2025-06-28 | 12 | 3 | 0 | 9 | N-IN | C-HN-MNA:06/28 > UTP:06/28
CHOPPER | HS | OUT | SKL | NY | 2025-06-28 | 2025-06-28 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:06/28 > NY:06/28
CHOPPER | HS | IN | NY | SKL | 2025-06-28 | 2025-06-28 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:06/28 > SKL:06/28
CHOPPER | HN | OUT | UTP | JAS | 2025-06-30 | 2025-06-30 | 12 | 7 | 2 | 3 | N-OUT | C-HN-UTP:06/30 > JAS:06/30
CHOPPER | HN | IN | JAS | UTP | 2025-06-30 | 2025-06-30 | 12 | 7 | 5 | 0 | N-IN | C-HN-JAS:06/30 > UTP:06/30
CHOPPER | HS | OUT | SKL | NY | 2025-07-02 | 2025-07-02 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:07/02 > NY:07/02
CHOPPER | HS | IN | NY | SKL | 2025-07-02 | 2025-07-02 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:07/02 > SKL:07/02
CHOPPER | HS | OUT | SKL | WN | 2025-07-02 | 2025-07-02 | 12 | 8 | 1 | 3 | S-OUT | C-HS-SKL:07/02 > WN:07/02
CHOPPER | HS | IN | WN | SKL | 2025-07-02 | 2025-07-02 | 12 | 8 | 4 | 0 | S-IN | C-HS-WN:07/02 > SKL:07/02
CHOPPER | HN | OUT | UTP | JAS | 2025-07-03 | 2025-07-03 | 12 | 7 | 2 | 3 | N-OUT | C-HN-UTP:07/03 > JAS:07/03
CHOPPER | HN | IN | JAS | UTP | 2025-07-03 | 2025-07-03 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:07/03 > UTP:07/03
CHOPPER | HS | OUT | SKL | WN | 2025-07-04 | 2025-07-04 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:07/04 > WN:07/04
CHOPPER | HS | IN | WN | SKL | 2025-07-04 | 2025-07-04 | 12 | 8 | 1 | 3 | S-IN | C-HS-WN:07/04 > SKL:07/04
CHOPPER | HN | OUT | UTP | JAS | 2025-07-05 | 2025-07-05 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:07/05 > JAS:07/05
CHOPPER | HN | IN | JAS | UTP | 2025-07-05 | 2025-07-05 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:07/05 > UTP:07/05
CHOPPER | HN | OUT | UTP | MNA | 2025-07-05 | 2025-07-05 | 12 | 10 | 1 | 1 | N-OUT | C-HN-UTP:07/05 > MNA:07/05
CHOPPER | HN | IN | MNA | UTP | 2025-07-05 | 2025-07-05 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:07/05 > UTP:07/05
CHOPPER | HS | OUT | SKL | NY | 2025-07-05 | 2025-07-05 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:07/05 > NY:07/05
CHOPPER | HS | IN | NY | SKL | 2025-07-05 | 2025-07-05 | 12 | 10 | 1 | 1 | S-IN | C-HS-NY:07/05 > SKL:07/05
CHOPPER | HN | OUT | UTP | JAS | 2025-07-07 | 2025-07-07 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:07/07 > JAS:07/07
CHOPPER | HN | IN | JAS | UTP | 2025-07-07 | 2025-07-07 | 12 | 8 | 1 | 3 | N-IN | C-HN-JAS:07/07 > UTP:07/07
CHOPPER | HN | OUT | UTP | MNA | 2025-07-07 | 2025-07-07 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:07/07 > MNA:07/07
CHOPPER | HN | IN | MNA | UTP | 2025-07-07 | 2025-07-07 | 12 | 11 | 0 | 1 | N-IN | C-HN-MNA:07/07 > UTP:07/07
CHOPPER | HS | OUT | SKL | NY | 2025-07-09 | 2025-07-09 | 12 | 6 | 0 | 6 | S-OUT | C-HS-SKL:07/09 > NY:07/09
CHOPPER | HS | IN | NY | SKL | 2025-07-09 | 2025-07-09 | 12 | 6 | 0 | 6 | S-IN | C-HS-NY:07/09 > SKL:07/09
CHOPPER | HS | OUT | SKL | WN | 2025-07-09 | 2025-07-09 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:07/09 > WN:07/09
CHOPPER | HS | IN | WN | SKL | 2025-07-09 | 2025-07-09 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:07/09 > SKL:07/09
CHOPPER | HN | OUT | UTP | JAS | 2025-07-10 | 2025-07-10 | 12 | 3 | 0 | 9 | N-OUT | C-HN-UTP:07/10 > JAS:07/10
CHOPPER | HN | IN | JAS | UTP | 2025-07-10 | 2025-07-10 | 12 | 3 | 2 | 7 | N-IN | C-HN-JAS:07/10 > UTP:07/10
CHOPPER | HN | OUT | UTP | JAS | 2025-07-12 | 2025-07-12 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:07/12 > JAS:07/12
CHOPPER | HN | IN | JAS | UTP | 2025-07-12 | 2025-07-12 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:07/12 > UTP:07/12
CHOPPER | HN | OUT | UTP | MNA | 2025-07-12 | 2025-07-12 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:07/12 > MNA:07/12
CHOPPER | HN | IN | MNA | UTP | 2025-07-12 | 2025-07-12 | 12 | 9 | 1 | 2 | N-IN | C-HN-MNA:07/12 > UTP:07/12
CHOPPER | HN | OUT | UTP | JAS | 2025-07-14 | 2025-07-14 | 12 | 7 | 1 | 4 | N-OUT | C-HN-UTP:07/14 > JAS:07/14
CHOPPER | HN | IN | JAS | UTP | 2025-07-14 | 2025-07-14 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:07/14 > UTP:07/14
CHOPPER | HS | OUT | SKL | NY | 2025-07-16 | 2025-07-16 | 12 | 7 | 2 | 3 | S-OUT | C-HS-SKL:07/16 > NY:07/16
CHOPPER | HS | IN | NY | SKL | 2025-07-16 | 2025-07-16 | 12 | 7 | 0 | 5 | S-IN | C-HS-NY:07/16 > SKL:07/16
CHOPPER | HS | OUT | SKL | WN | 2025-07-16 | 2025-07-16 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:07/16 > WN:07/16
CHOPPER | HS | IN | WN | SKL | 2025-07-16 | 2025-07-16 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:07/16 > SKL:07/16
CHOPPER | HN | OUT | UTP | JAS | 2025-07-17 | 2025-07-17 | 12 | 6 | 3 | 3 | N-OUT | C-HN-UTP:07/17 > JAS:07/17
CHOPPER | HN | IN | JAS | UTP | 2025-07-17 | 2025-07-17 | 12 | 6 | 1 | 5 | N-IN | C-HN-JAS:07/17 > UTP:07/17
CHOPPER | HS | OUT | SKL | WN | 2025-07-18 | 2025-07-18 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:07/18 > WN:07/18
CHOPPER | HS | IN | WN | SKL | 2025-07-18 | 2025-07-18 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:07/18 > SKL:07/18
CHOPPER | HN | OUT | UTP | JAS | 2025-07-19 | 2025-07-19 | 12 | 5 | 1 | 6 | N-OUT | C-HN-UTP:07/19 > JAS:07/19
CHOPPER | HN | IN | JAS | UTP | 2025-07-19 | 2025-07-19 | 12 | 5 | 1 | 6 | N-IN | C-HN-JAS:07/19 > UTP:07/19
CHOPPER | HN | OUT | UTP | MNA | 2025-07-19 | 2025-07-19 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:07/19 > MNA:07/19
CHOPPER | HN | IN | MNA | UTP | 2025-07-19 | 2025-07-19 | 12 | 5 | 2 | 5 | N-IN | C-HN-MNA:07/19 > UTP:07/19
CHOPPER | HN | OUT | UTP | JAS | 2025-07-21 | 2025-07-21 | 12 | 8 | 4 | 0 | N-OUT | C-HN-UTP:07/21 > JAS:07/21
CHOPPER | HN | IN | JAS | UTP | 2025-07-21 | 2025-07-21 | 12 | 8 | 2 | 2 | N-IN | C-HN-JAS:07/21 > UTP:07/21
CHOPPER | HN | OUT | UTP | MNA | 2025-07-21 | 2025-07-21 | 12 | 10 | 2 | 0 | N-OUT | C-HN-UTP:07/21 > MNA:07/21
CHOPPER | HN | IN | MNA | UTP | 2025-07-21 | 2025-07-21 | 12 | 10 | 1 | 1 | N-IN | C-HN-MNA:07/21 > UTP:07/21
CHOPPER | HS | OUT | SKL | NY | 2025-07-23 | 2025-07-23 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:07/23 > NY:07/23
CHOPPER | HS | IN | NY | SKL | 2025-07-23 | 2025-07-23 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:07/23 > SKL:07/23
CHOPPER | HS | OUT | SKL | WN | 2025-07-23 | 2025-07-23 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:07/23 > WN:07/23
CHOPPER | HS | IN | WN | SKL | 2025-07-23 | 2025-07-23 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:07/23 > SKL:07/23
CHOPPER | HS | OUT | SKL | WN | 2025-07-25 | 2025-07-25 | 12 | 7 | 0 | 5 | S-OUT | C-HS-SKL:07/25 > WN:07/25
CHOPPER | HS | IN | WN | SKL | 2025-07-25 | 2025-07-25 | 12 | 7 | 0 | 5 | S-IN | C-HS-WN:07/25 > SKL:07/25
CHOPPER | HN | OUT | UTP | JAS | 2025-07-26 | 2025-07-26 | 12 | 12 | 0 | 0 | N-OUT | C-HN-UTP:07/26 > JAS:07/26
CHOPPER | HN | IN | JAS | UTP | 2025-07-26 | 2025-07-26 | 12 | 12 | 0 | 0 | N-IN | C-HN-JAS:07/26 > UTP:07/26
CHOPPER | HN | OUT | UTP | MNA | 2025-07-26 | 2025-07-26 | 12 | 6 | 2 | 4 | N-OUT | C-HN-UTP:07/26 > MNA:07/26
CHOPPER | HN | IN | MNA | UTP | 2025-07-26 | 2025-07-26 | 12 | 6 | 6 | 0 | N-IN | C-HN-MNA:07/26 > UTP:07/26
CHOPPER | HS | OUT | SKL | NY | 2025-07-26 | 2025-07-26 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:07/26 > NY:07/26
CHOPPER | HS | IN | NY | SKL | 2025-07-26 | 2025-07-26 | 12 | 10 | 1 | 1 | S-IN | C-HS-NY:07/26 > SKL:07/26
CHOPPER | HN | OUT | UTP | JAS | 2025-07-28 | 2025-07-28 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:07/28 > JAS:07/28
CHOPPER | HN | IN | JAS | UTP | 2025-07-28 | 2025-07-28 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:07/28 > UTP:07/28
CHOPPER | HS | OUT | SKL | NY | 2025-07-30 | 2025-07-30 | 12 | 6 | 1 | 5 | S-OUT | C-HS-SKL:07/30 > NY:07/30
CHOPPER | HS | IN | NY | SKL | 2025-07-30 | 2025-07-30 | 12 | 6 | 1 | 5 | S-IN | C-HS-NY:07/30 > SKL:07/30
CHOPPER | HS | OUT | SKL | WN | 2025-07-30 | 2025-07-30 | 12 | 9 | 1 | 2 | S-OUT | C-HS-SKL:07/30 > WN:07/30
CHOPPER | HS | IN | WN | SKL | 2025-07-30 | 2025-07-30 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:07/30 > SKL:07/30
CHOPPER | HN | OUT | UTP | JAS | 2025-07-31 | 2025-07-31 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:07/31 > JAS:07/31
CHOPPER | HN | IN | JAS | UTP | 2025-07-31 | 2025-07-31 | 12 | 9 | 0 | 3 | N-IN | C-HN-JAS:07/31 > UTP:07/31
CHOPPER | HS | OUT | SKL | WN | 2025-08-01 | 2025-08-01 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:08/01 > WN:08/01
CHOPPER | HS | IN | WN | SKL | 2025-08-01 | 2025-08-01 | 12 | 8 | 1 | 3 | S-IN | C-HS-WN:08/01 > SKL:08/01
CHOPPER | HN | OUT | UTP | JAS | 2025-08-02 | 2025-08-02 | 12 | 11 | 1 | 0 | N-OUT | C-HN-UTP:08/02 > JAS:08/02
CHOPPER | HN | IN | JAS | UTP | 2025-08-02 | 2025-08-02 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:08/02 > UTP:08/02
CHOPPER | HN | OUT | UTP | MNA | 2025-08-02 | 2025-08-02 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:08/02 > MNA:08/02
CHOPPER | HN | IN | MNA | UTP | 2025-08-02 | 2025-08-02 | 12 | 10 | 2 | 0 | N-IN | C-HN-MNA:08/02 > UTP:08/02
CHOPPER | HN | OUT | UTP | JAS | 2025-08-04 | 2025-08-04 | 12 | 7 | 2 | 3 | N-OUT | C-HN-UTP:08/04 > JAS:08/04
CHOPPER | HN | IN | JAS | UTP | 2025-08-04 | 2025-08-04 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:08/04 > UTP:08/04
CHOPPER | HN | OUT | UTP | MNA | 2025-08-04 | 2025-08-04 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:08/04 > MNA:08/04
CHOPPER | HN | IN | MNA | UTP | 2025-08-04 | 2025-08-04 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:08/04 > UTP:08/04
CHOPPER | HS | OUT | SKL | NY | 2025-08-06 | 2025-08-06 | 12 | 10 | 1 | 1 | S-OUT | C-HS-SKL:08/06 > NY:08/06
CHOPPER | HS | IN | NY | SKL | 2025-08-06 | 2025-08-06 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:08/06 > SKL:08/06
CHOPPER | HS | OUT | SKL | WN | 2025-08-06 | 2025-08-06 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:08/06 > WN:08/06
CHOPPER | HS | IN | WN | SKL | 2025-08-06 | 2025-08-06 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:08/06 > SKL:08/06
CHOPPER | HN | OUT | UTP | JAS | 2025-08-09 | 2025-08-09 | 12 | 6 | 1 | 5 | N-OUT | C-HN-UTP:08/09 > JAS:08/09
CHOPPER | HN | IN | JAS | UTP | 2025-08-09 | 2025-08-09 | 12 | 6 | 1 | 5 | N-IN | C-HN-JAS:08/09 > UTP:08/09
CHOPPER | HN | OUT | UTP | MNA | 2025-08-09 | 2025-08-09 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:08/09 > MNA:08/09
CHOPPER | HN | IN | MNA | UTP | 2025-08-09 | 2025-08-09 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:08/09 > UTP:08/09
CHOPPER | HN | OUT | UTP | JAS | 2025-08-11 | 2025-08-11 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:08/11 > JAS:08/11
CHOPPER | HN | IN | JAS | UTP | 2025-08-11 | 2025-08-11 | 12 | 8 | 3 | 1 | N-IN | C-HN-JAS:08/11 > UTP:08/11
CHOPPER | HS | OUT | SKL | NY | 2025-08-13 | 2025-08-13 | 12 | 12 | 0 | 0 | S-OUT | C-HS-SKL:08/13 > NY:08/13
CHOPPER | HS | IN | NY | SKL | 2025-08-13 | 2025-08-13 | 12 | 12 | 0 | 0 | S-IN | C-HS-NY:08/13 > SKL:08/13
CHOPPER | HS | OUT | SKL | WN | 2025-08-13 | 2025-08-13 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:08/13 > WN:08/13
CHOPPER | HS | IN | WN | SKL | 2025-08-13 | 2025-08-13 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:08/13 > SKL:08/13
CHOPPER | HN | OUT | UTP | JAS | 2025-08-14 | 2025-08-14 | 12 | 6 | 2 | 4 | N-OUT | C-HN-UTP:08/14 > JAS:08/14
CHOPPER | HN | IN | JAS | UTP | 2025-08-14 | 2025-08-14 | 12 | 6 | 1 | 5 | N-IN | C-HN-JAS:08/14 > UTP:08/14
CHOPPER | HS | OUT | SKL | WN | 2025-08-15 | 2025-08-15 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:08/15 > WN:08/15
CHOPPER | HS | IN | WN | SKL | 2025-08-15 | 2025-08-15 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:08/15 > SKL:08/15
CHOPPER | HN | OUT | UTP | JAS | 2025-08-16 | 2025-08-16 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:08/16 > JAS:08/16
CHOPPER | HN | IN | JAS | UTP | 2025-08-16 | 2025-08-16 | 12 | 11 | 1 | 0 | N-IN | C-HN-JAS:08/16 > UTP:08/16
CHOPPER | HN | OUT | UTP | MNA | 2025-08-16 | 2025-08-16 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:08/16 > MNA:08/16
CHOPPER | HN | IN | MNA | UTP | 2025-08-16 | 2025-08-16 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:08/16 > UTP:08/16
CHOPPER | HS | OUT | SKL | NY | 2025-08-16 | 2025-08-16 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:08/16 > NY:08/16
CHOPPER | HS | IN | NY | SKL | 2025-08-16 | 2025-08-16 | 12 | 10 | 2 | 0 | S-IN | C-HS-NY:08/16 > SKL:08/16
CHOPPER | HN | OUT | UTP | JAS | 2025-08-18 | 2025-08-18 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:08/18 > JAS:08/18
CHOPPER | HN | IN | JAS | UTP | 2025-08-18 | 2025-08-18 | 12 | 8 | 1 | 3 | N-IN | C-HN-JAS:08/18 > UTP:08/18
CHOPPER | HN | OUT | UTP | MNA | 2025-08-18 | 2025-08-18 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:08/18 > MNA:08/18
CHOPPER | HN | IN | MNA | UTP | 2025-08-18 | 2025-08-18 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:08/18 > UTP:08/18
CHOPPER | HS | OUT | SKL | NY | 2025-08-20 | 2025-08-20 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:08/20 > NY:08/20
CHOPPER | HS | IN | NY | SKL | 2025-08-20 | 2025-08-20 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:08/20 > SKL:08/20
CHOPPER | HS | OUT | SKL | WN | 2025-08-20 | 2025-08-20 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:08/20 > WN:08/20
CHOPPER | HS | IN | WN | SKL | 2025-08-20 | 2025-08-20 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:08/20 > SKL:08/20
CHOPPER | HN | OUT | UTP | JAS | 2025-08-21 | 2025-08-21 | 12 | 4 | 0 | 8 | N-OUT | C-HN-UTP:08/21 > JAS:08/21
CHOPPER | HN | IN | JAS | UTP | 2025-08-21 | 2025-08-21 | 12 | 4 | 0 | 8 | N-IN | C-HN-JAS:08/21 > UTP:08/21
CHOPPER | HS | OUT | SKL | WN | 2025-08-22 | 2025-08-22 | 12 | 8 | 3 | 1 | S-OUT | C-HS-SKL:08/22 > WN:08/22
CHOPPER | HS | IN | WN | SKL | 2025-08-22 | 2025-08-22 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:08/22 > SKL:08/22
CHOPPER | HN | OUT | UTP | JAS | 2025-08-23 | 2025-08-23 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:08/23 > JAS:08/23
CHOPPER | HN | IN | JAS | UTP | 2025-08-23 | 2025-08-23 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:08/23 > UTP:08/23
CHOPPER | HN | OUT | UTP | MNA | 2025-08-23 | 2025-08-23 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:08/23 > MNA:08/23
CHOPPER | HN | IN | MNA | UTP | 2025-08-23 | 2025-08-23 | 12 | 6 | 0 | 6 | N-IN | C-HN-MNA:08/23 > UTP:08/23
CHOPPER | HS | OUT | SKL | NY | 2025-08-23 | 2025-08-23 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:08/23 > NY:08/23
CHOPPER | HS | IN | NY | SKL | 2025-08-23 | 2025-08-23 | 12 | 8 | 0 | 4 | S-IN | C-HS-NY:08/23 > SKL:08/23
CHOPPER | HN | OUT | UTP | JAS | 2025-08-25 | 2025-08-25 | 12 | 6 | 0 | 6 | N-OUT | C-HN-UTP:08/25 > JAS:08/25
CHOPPER | HN | IN | JAS | UTP | 2025-08-25 | 2025-08-25 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:08/25 > UTP:08/25
CHOPPER | HS | OUT | SKL | NY | 2025-08-27 | 2025-08-27 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:08/27 > NY:08/27
CHOPPER | HS | IN | NY | SKL | 2025-08-27 | 2025-08-27 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:08/27 > SKL:08/27
CHOPPER | HS | OUT | SKL | WN | 2025-08-27 | 2025-08-27 | 12 | 9 | 2 | 1 | S-OUT | C-HS-SKL:08/27 > WN:08/27
CHOPPER | HS | IN | WN | SKL | 2025-08-27 | 2025-08-27 | 12 | 9 | 2 | 1 | S-IN | C-HS-WN:08/27 > SKL:08/27
CHOPPER | HN | OUT | UTP | JAS | 2025-08-28 | 2025-08-28 | 12 | 8 | 2 | 2 | N-OUT | C-HN-UTP:08/28 > JAS:08/28
CHOPPER | HN | IN | JAS | UTP | 2025-08-28 | 2025-08-28 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:08/28 > UTP:08/28
CHOPPER | HS | OUT | SKL | WN | 2025-08-29 | 2025-08-29 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:08/29 > WN:08/29
CHOPPER | HS | IN | WN | SKL | 2025-08-29 | 2025-08-29 | 12 | 8 | 3 | 1 | S-IN | C-HS-WN:08/29 > SKL:08/29
CHOPPER | HN | OUT | UTP | JAS | 2025-08-30 | 2025-08-30 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:08/30 > JAS:08/30
CHOPPER | HN | IN | JAS | UTP | 2025-08-30 | 2025-08-30 | 12 | 5 | 2 | 5 | N-IN | C-HN-JAS:08/30 > UTP:08/30
CHOPPER | HN | OUT | UTP | MNA | 2025-08-30 | 2025-08-30 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:08/30 > MNA:08/30
CHOPPER | HN | IN | MNA | UTP | 2025-08-30 | 2025-08-30 | 12 | 8 | 0 | 4 | N-IN | C-HN-MNA:08/30 > UTP:08/30
CHOPPER | HN | OUT | UTP | JAS | 2025-09-01 | 2025-09-01 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:09/01 > JAS:09/01
CHOPPER | HN | IN | JAS | UTP | 2025-09-01 | 2025-09-01 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:09/01 > UTP:09/01
CHOPPER | HN | OUT | UTP | MNA | 2025-09-01 | 2025-09-01 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:09/01 > MNA:09/01
CHOPPER | HN | IN | MNA | UTP | 2025-09-01 | 2025-09-01 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:09/01 > UTP:09/01
CHOPPER | HS | OUT | SKL | NY | 2025-09-03 | 2025-09-03 | 12 | 11 | 0 | 1 | S-OUT | C-HS-SKL:09/03 > NY:09/03
CHOPPER | HS | IN | NY | SKL | 2025-09-03 | 2025-09-03 | 12 | 11 | 0 | 1 | S-IN | C-HS-NY:09/03 > SKL:09/03
CHOPPER | HS | OUT | SKL | WN | 2025-09-03 | 2025-09-03 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:09/03 > WN:09/03
CHOPPER | HS | IN | WN | SKL | 2025-09-03 | 2025-09-03 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:09/03 > SKL:09/03
CHOPPER | HN | OUT | UTP | JAS | 2025-09-06 | 2025-09-06 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:09/06 > JAS:09/06
CHOPPER | HN | IN | JAS | UTP | 2025-09-06 | 2025-09-06 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:09/06 > UTP:09/06
CHOPPER | HN | OUT | UTP | MNA | 2025-09-06 | 2025-09-06 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:09/06 > MNA:09/06
CHOPPER | HN | IN | MNA | UTP | 2025-09-06 | 2025-09-06 | 12 | 8 | 0 | 4 | N-IN | C-HN-MNA:09/06 > UTP:09/06
CHOPPER | HS | OUT | SKL | NY | 2025-09-06 | 2025-09-06 | 12 | 19 | 0 | -7 | S-OUT | C-HS-SKL:09/06 > NY:09/06
CHOPPER | HS | IN | NY | SKL | 2025-09-06 | 2025-09-06 | 12 | 19 | 0 | -7 | S-IN | C-HS-NY:09/06 > SKL:09/06
CHOPPER | HN | OUT | UTP | JAS | 2025-09-08 | 2025-09-08 | 12 | 8 | 2 | 2 | N-OUT | C-HN-UTP:09/08 > JAS:09/08
CHOPPER | HN | IN | JAS | UTP | 2025-09-08 | 2025-09-08 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:09/08 > UTP:09/08
CHOPPER | HS | OUT | SKL | NY | 2025-09-10 | 2025-09-10 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:09/10 > NY:09/10
CHOPPER | HS | IN | NY | SKL | 2025-09-10 | 2025-09-10 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:09/10 > SKL:09/10
CHOPPER | HS | OUT | SKL | WN | 2025-09-10 | 2025-09-10 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:09/10 > WN:09/10
CHOPPER | HS | IN | WN | SKL | 2025-09-10 | 2025-09-10 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:09/10 > SKL:09/10
CHOPPER | HN | OUT | UTP | JAS | 2025-09-11 | 2025-09-11 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:09/11 > JAS:09/11
CHOPPER | HN | IN | JAS | UTP | 2025-09-11 | 2025-09-11 | 12 | 10 | 2 | 0 | N-IN | C-HN-JAS:09/11 > UTP:09/11
CHOPPER | HS | OUT | SKL | WN | 2025-09-12 | 2025-09-12 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:09/12 > WN:09/12
CHOPPER | HS | IN | WN | SKL | 2025-09-12 | 2025-09-12 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:09/12 > SKL:09/12
CHOPPER | HN | OUT | UTP | JAS | 2025-09-13 | 2025-09-13 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:09/13 > JAS:09/13
CHOPPER | HN | IN | JAS | UTP | 2025-09-13 | 2025-09-13 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:09/13 > UTP:09/13
CHOPPER | HN | OUT | UTP | MNA | 2025-09-13 | 2025-09-13 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:09/13 > MNA:09/13
CHOPPER | HN | IN | MNA | UTP | 2025-09-13 | 2025-09-13 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:09/13 > UTP:09/13
CHOPPER | HN | OUT | UTP | JAS | 2025-09-15 | 2025-09-15 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:09/15 > JAS:09/15
CHOPPER | HN | IN | JAS | UTP | 2025-09-15 | 2025-09-15 | 12 | 8 | 0 | 4 | N-IN | C-HN-JAS:09/15 > UTP:09/15
CHOPPER | HN | OUT | UTP | MNA | 2025-09-15 | 2025-09-15 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:09/15 > MNA:09/15
CHOPPER | HN | IN | MNA | UTP | 2025-09-15 | 2025-09-15 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:09/15 > UTP:09/15
CHOPPER | HS | OUT | SKL | NY | 2025-09-17 | 2025-09-17 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:09/17 > NY:09/17
CHOPPER | HS | IN | NY | SKL | 2025-09-17 | 2025-09-17 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:09/17 > SKL:09/17
CHOPPER | HS | OUT | SKL | WN | 2025-09-17 | 2025-09-17 | 12 | 9 | 0 | 3 | S-OUT | C-HS-SKL:09/17 > WN:09/17
CHOPPER | HS | IN | WN | SKL | 2025-09-17 | 2025-09-17 | 12 | 9 | 0 | 3 | S-IN | C-HS-WN:09/17 > SKL:09/17
CHOPPER | HS | OUT | SKL | WN | 2025-09-19 | 2025-09-19 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:09/19 > WN:09/19
CHOPPER | HS | IN | WN | SKL | 2025-09-19 | 2025-09-19 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:09/19 > SKL:09/19
CHOPPER | HN | OUT | UTP | JAS | 2025-09-20 | 2025-09-20 | 12 | 5 | 0 | 7 | N-OUT | C-HN-UTP:09/20 > JAS:09/20
CHOPPER | HN | IN | JAS | UTP | 2025-09-20 | 2025-09-20 | 12 | 5 | 0 | 7 | N-IN | C-HN-JAS:09/20 > UTP:09/20
CHOPPER | HN | OUT | UTP | MNA | 2025-09-20 | 2025-09-20 | 12 | 4 | 0 | 8 | N-OUT | C-HN-UTP:09/20 > MNA:09/20
CHOPPER | HN | IN | MNA | UTP | 2025-09-20 | 2025-09-20 | 12 | 4 | 0 | 8 | N-IN | C-HN-MNA:09/20 > UTP:09/20
CHOPPER | HS | OUT | SKL | NY | 2025-09-20 | 2025-09-20 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:09/20 > NY:09/20
CHOPPER | HS | IN | NY | SKL | 2025-09-20 | 2025-09-20 | 12 | 9 | 0 | 3 | S-IN | C-HS-NY:09/20 > SKL:09/20
CHOPPER | HN | OUT | UTP | JAS | 2025-09-22 | 2025-09-22 | 12 | 7 | 0 | 5 | N-OUT | C-HN-UTP:09/22 > JAS:09/22
CHOPPER | HN | IN | JAS | UTP | 2025-09-22 | 2025-09-22 | 12 | 7 | 0 | 5 | N-IN | C-HN-JAS:09/22 > UTP:09/22
CHOPPER | HS | OUT | SKL | NY | 2025-09-24 | 2025-09-24 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:09/24 > NY:09/24
CHOPPER | HS | IN | NY | SKL | 2025-09-24 | 2025-09-24 | 12 | 11 | 0 | 1 | S-IN | C-HS-NY:09/24 > SKL:09/24
CHOPPER | HS | OUT | SKL | WN | 2025-09-24 | 2025-09-24 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:09/24 > WN:09/24
CHOPPER | HS | IN | WN | SKL | 2025-09-24 | 2025-09-24 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:09/24 > SKL:09/24
CHOPPER | HN | OUT | UTP | JAS | 2025-09-25 | 2025-09-25 | 12 | 6 | 1 | 5 | N-OUT | C-HN-UTP:09/25 > JAS:09/25
CHOPPER | HN | IN | JAS | UTP | 2025-09-25 | 2025-09-25 | 12 | 6 | 0 | 6 | N-IN | C-HN-JAS:09/25 > UTP:09/25
CHOPPER | HS | OUT | SKL | WN | 2025-09-26 | 2025-09-26 | 12 | 8 | 0 | 4 | S-OUT | C-HS-SKL:09/26 > WN:09/26
CHOPPER | HS | IN | WN | SKL | 2025-09-26 | 2025-09-26 | 12 | 8 | 0 | 4 | S-IN | C-HS-WN:09/26 > SKL:09/26
CHOPPER | HN | OUT | UTP | JAS | 2025-09-27 | 2025-09-27 | 12 | 11 | 0 | 1 | N-OUT | C-HN-UTP:09/27 > JAS:09/27
CHOPPER | HN | IN | JAS | UTP | 2025-09-27 | 2025-09-27 | 12 | 11 | 0 | 1 | N-IN | C-HN-JAS:09/27 > UTP:09/27
CHOPPER | HN | OUT | UTP | MNA | 2025-09-27 | 2025-09-27 | 12 | 9 | 0 | 3 | N-OUT | C-HN-UTP:09/27 > MNA:09/27
CHOPPER | HN | IN | MNA | UTP | 2025-09-27 | 2025-09-27 | 12 | 9 | 0 | 3 | N-IN | C-HN-MNA:09/27 > UTP:09/27
CHOPPER | HS | OUT | SKL | NY | 2025-09-27 | 2025-09-27 | 12 | 10 | 0 | 2 | S-OUT | C-HS-SKL:09/27 > NY:09/27
CHOPPER | HS | IN | NY | SKL | 2025-09-27 | 2025-09-27 | 12 | 10 | 0 | 2 | S-IN | C-HS-NY:09/27 > SKL:09/27
CHOPPER | HN | OUT | UTP | JAS | 2025-09-29 | 2025-09-29 | 12 | 8 | 0 | 4 | N-OUT | C-HN-UTP:09/29 > JAS:09/29
CHOPPER | HN | IN | JAS | UTP | 2025-09-29 | 2025-09-29 | 12 | 8 | 1 | 3 | N-IN | C-HN-JAS:09/29 > UTP:09/29
CHOPPER | HN | OUT | UTP | MNA | 2025-09-29 | 2025-09-29 | 12 | 10 | 0 | 2 | N-OUT | C-HN-UTP:09/29 > MNA:09/29
CHOPPER | HN | IN | MNA | UTP | 2025-09-29 | 2025-09-29 | 12 | 10 | 0 | 2 | N-IN | C-HN-MNA:09/29 > UTP:09/29

## Field_Bed_Capacity
ID | Field | Bed_Capacity
1 | JAS | 101
2 | G1 | 80
3 | G11 | 80
4 | NYC | 50
5 | G10 | 46
6 | G10_FSO | 45

## Regular_Crew
ID | Field | Date_Start | Date_End | Person_On_Board
1 | JAS | 2025-07-01 | 2025-07-16 | 66
2 | JAS | 2025-07-17 | 2025-07-18 | 67
3 | JAS | 2025-07-19 | 2025-09-30 | 70
4 | G1 | 2025-07-01 | 2025-07-16 | 52
5 | G1 | 2025-07-17 | 2025-07-26 | 48
6 | G1 | 2025-07-27 | 2025-09-30 | 52
7 | G11 | 2025-07-01 | 2025-09-30 | 49
8 | NYC | 2025-07-01 | 2025-07-04 | 15
10 | NYC | 2025-07-07 | 2025-07-11 | 15
12 | NYC | 2025-07-14 | 2025-07-18 | 15
14 | NYC | 2025-07-21 | 2025-07-25 | 15
16 | NYC | 2025-07-28 | 2025-08-01 | 15
18 | NYC | 2025-08-04 | 2025-08-08 | 15
20 | NYC | 2025-08-11 | 2025-08-15 | 15
22 | NYC | 2025-08-18 | 2025-08-22 | 15
24 | NYC | 2025-08-25 | 2025-08-29 | 15
26 | NYC | 2025-09-01 | 2025-09-05 | 15
28 | NYC | 2025-09-08 | 2025-09-12 | 15
30 | NYC | 2025-09-15 | 2025-09-19 | 15
32 | NYC | 2025-09-22 | 2025-09-26 | 15
34 | NYC | 2025-09-29 | 2025-10-03 | 15
36 | NYC | 2025-10-06 | 2025-10-10 | 15
38 | NYC | 2025-07-05 | 2025-07-06 | 17
40 | NYC | 2025-07-12 | 2025-07-13 | 17
42 | NYC | 2025-07-19 | 2025-07-20 | 17
44 | NYC | 2025-07-26 | 2025-07-27 | 17
46 | NYC | 2025-08-02 | 2025-08-03 | 17
48 | NYC | 2025-08-09 | 2025-08-10 | 17
50 | NYC | 2025-08-16 | 2025-08-17 | 17
52 | NYC | 2025-08-23 | 2025-08-24 | 17
54 | NYC | 2025-08-30 | 2025-08-31 | 17
56 | NYC | 2025-09-06 | 2025-09-07 | 17
58 | NYC | 2025-09-13 | 2025-09-14 | 17
60 | NYC | 2025-09-20 | 2025-09-21 | 17
62 | NYC | 2025-09-27 | 2025-09-28 | 17
64 | G10 | 2025-07-01 | 2025-09-30 | 26
66 | G10_FSO | 2025-07-01 | 2025-09-30 | 26